## Common
e
[5 empty] | Doc No: | [11 empty] | Previous Update:
Energypac Engineering Ltd |  |  |  |  | Format No: | [11 empty] | Last Update:
PROJECT AUDIT DIVISION |  |  |  |  | Rev No: | 0 | [10 empty] | Today's Date: | 2017-09-07
Serial no | Project | Client | Name of Project | Site ID | Site name | Responsible Project Manager |  |  |  | Starting | Finish |  | Site info | Project Status (Previous Update- Last week) | Present Status | Deviations | Reason of Deviation | Remarks
[7 empty] | Name | Designation | Phone | Date | Date | Description of work
1 | DDP (Nayarhat, Birulia, Jalshiri & Nazarpur) | BREB | DDP (Nayarhat, Birulia, Jalshiri & Nazarpur) Client - BREB | 1.1 | Nayarhat | Md.Azharul Haque 01732761574 SAE. Shahjalal 01755445178 Shafiul Azam- 01755506232 | Md.Azharul Haque |  | 1732761574 | - | - | Deed Agreement | Nayarhat Project Manager Md.Azharul Haque 01732761574 SAE. Shahjalal 01755445178 Shafiul Azam- 01755506232 | 26.10.2016 -12 Nos of base casting is complete for control building. 03.11.2016 -12 Nos of short column casting is complete, 1000 mm sand filling going on for control building, 400 mm sand filling is complete in switchyard area to start CC work for gantry foundation. 10.11.2016 -08 Nos of base of gantry casting is complete, Sand filling is complete up to grade beam of control building area & compaction is going on, excavation complete of 03 nos of base for boundary wall column. 17.11.2016 -08 Nos column of gantry foundation casting is complete, Rod fabrication is complete for grade beam. 24.11.2016 -Control room short column casting complete.Grade beam shuttering complete.Gantry tower base and short column casting complete.One base for XFR is complete.6 Nos of bases for boundary wall complete. 01.12.2016 -Control building: grade beam and column (FGL to PL) RCC casting complete.XFR : 01 Nos RCC base and 01 Nos base PCC casting complete and reinforcement binding & shuttering complete.2 Nos of EM tower base PCC casting complete. Boundary wall: 06 Nos short column RCC casting complete. 08.12.2016 -One base of XFR's RCC casting has been completed and another base’s two pedestals’ RCC casting has been completed.02 Nos of EM tower base RCC casting has been completed.02 Nos of boundary short column RCC and 02 Nos of boundary base PCC+RCC casting has been completed.Brick work has been completed from grade beam to PL of control building's.Some sand filling completed in front of control building. 15.12.2016 Two pedestal of another base RCC casting has been completed. 02.Twi nos of EM tower column RCC casting has been completed. 03.8nos of Gantry tower Columbus RCC casting has been completed.04.four nos column of control building's RCc casting has been completed. 05.Boundary wall: 6nos base RCC +7nos short column+10 nos base PCC casting has been completed. 22.12.2016 -4 Nos column of control building RCC casting has been completed.Boundary wall: 7 Nos RCC base +9 Nos short column +RCC Grade Beam 30m long+11nos base PCC casting has been completed. 29.12.2016 Boundary wall: 7nos RCC base+14nos short column Grade beam 10m long +9nos base PCC casting has been Completed.3 Nos control building columns half of above RCC casting has been completed.Septic tank & Soak well 's Brick work has been completed.Stair base:Earth work+ base(PCC+RCC)+2nos column RCC casting has been completed.LA,CB,CT base earthwork has been completed. 05.01.2017 -Boundary wall:12nos short column and 50m long Grade beam RCC casting has been completed.Stair base and column casting has been completed and first flight shuttering has been completed.Septic tank plaster completed.First Floor shuttering going on. 12.01.2017 --Boundary wall:05 Nos short column and 30m long Grade beam RCC casting has been completed.Base casting work has done for LA,CT foundation.05 Nos of base casting has done for Boundary. 19.01.2017 -Control building first floor RCC casting has been completed. 26.01.2017 -Control Building 12nos column(half of the below) RCC casting has been completed.VCB&CT base RCC casting has been completed. Boundary wall:20nos short column & 27m long Grade beam RCC casting has been completed.+ 45m long Brick work has been completed.Setting of transformer base plate has been completed. 02.02.2017 -VCB,CT,LA &VCB,CT column casting and net finishing has been completed. Control building beam shuttering and dasha setting has been completed.60% sand filling completed and running. 09.02.2017 -24m long grade beam RCC casting & 18 m long boundary brick work has been completed.Aux.XFR soling,RCC base & brick wall has been completed.Control building Roof slab shuttering & Rod binding completed. Switchyard earthing main mesh completed. 16.02.2017 -Control building Roof slab RCC casting has been completed and Ground floor ready for casting.25.6m long boundary grade beam RCC casting & some brick work has been completed. 23.02.2017 -RCC casting in ground floor of control room,27 meter long grade beam complete for boundary.05 Nos short column done for boundary wall. 02.03.2017 -25 m out side plaster work has been done for Boundary wall.Top slab plaster and plaster with net finishing work has been completed. -Celling plaster work is going on for control building. Approx. 65% sand filling work has been done. 09.03.2017 -4 Nos base PCC & 4 Nos RCC base & 4 Nos short column RCC casting completed,Boundary wall-35 m long copying RCC casting completed.10 no column(FGL to copying) RCC casting completed. RAMPS,RCC casting completed & porch slab shuttering ,rod binding completed. control cabletrench18 m long base RCC casting completed 25m long power cable trench PCC casting completed.sand filling 90%completed. 16.03.2017 -Control cable trench 2Nos wall 15m long RCC casting done.Guard house grade beam RCC casting completed. Control building,linten,porch,slab ,sunshed,brick work (80%),ceiling plaster complete.Boundary wall:9Nos base (PCC+RCC),9Nos short column RCC casting ,boundary wall 25% has been completed. 23.03.2017 -Power cable trench wall 40m long RCC casting Completed. Stair slab casting completed. Control building Ground floor and First floor brick work, lintel,fols Chad, plaster completed, Parapet wall brick work and inside plaster Completed. Boundary wall 6 Nos base (pcc+RCC+short column) casting completed. 30.03.2017 -80% plaster work and net finishing work has been done at Side wall in power & control cable trench.25m grad beam for boundary wall has done. 06.04.2017 -100% plaster work and net finishing work at Side wall in power & control cable trench. -45m grad beam for boundary wall has been done.14 Nos short column casting has been done. 13.04.2017 -12 Nos short column & 13m grade beam work for boundary wall and 06m Cable trench wall work has been completed. 20.04.2017 -07 Nos short column for boundary wall.27m long grade beam casting completed,45m long brick work completed.Power XFR er guide wall & pedestal RCC casting with net finishing.Sand filling 95% completed.Paint work,Mosaic work,tiles work, fencing bricks work is running, 27.04.2017 -10 Nos long column for boundary wall & 23m long grade beam casting has been completed.Control building ground floor & first floor mosaic Patten stone casting & grill fitting work has been completed. Guard house floor cast has done.Control building & boundary color work is continuing.27.04.2017-10 Nos long column for boundary wall & 23m long grade beam casting has been completed.Control building ground floor & first floor mosaic Patten stone casting & grill fitting work has been completed. -Guard house floor cast has done.Control building & boundary color work is continuing. 04.05.2017 -30m long brick wall making work has been completed.23m cosing casting and 02 Nos column casting work has been completed. 11.05.2017 -Road making work has been completed in front of control building.Fancy brick work is going on.Main gate installed & Paint work has been done. 18.05.2017 -3m wide road RCC casting has been completed. Fencing base casting completed.Tiles work completed and mosaic cutting work is going on.23m long Boundary wall plaster completed in both side. 25.05.2017 Outside skirting with net finishing work in control building has been completed. Color work is going on. Fencing work 50% & Mosaic work 70% has been done. 01.06.2017 Facing brick work fully completed.control building surface drain brick soling,pcc casting, brick work, cable duct rough casting has done.Gurd house brick work (up to lintel),lintel casting &Sanitary work 50% & Boundary wall angle fitting has been completed. Color work is going on. 08.06.2017 Control building surface drain plaster with net finishing 50%completed and running.Water roof work 30% done. Guard house brick work & plaster work has been completed.Switchyard guide wall& soling work has done. Pannel materials setting going on. 15.06.2017 Control building surface drain plaster with net finishing 100%,Water roof work 60% and Switchyard guide wall has been completed.Panel materials setting work is going on. 22.06.2017 -Water roof work 100% has done. -Panel materials setting work has been completed. 29.06.2017 -No further update. 06.07.2017 -Control cable laying work is going on.House wiring work is continuing at control building and guard room. 13.07.2017 -20 Nos Slab making has done for power cable trench.
[7 empty] | SAE. Shahjalal |  | 1755445178 | - | - | Contract Date
[7 empty] | Shafiul Azam- |  | 1755506232 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Jun 14' 16 | Declaration of completion
1 | DDP (Nayarhat, Birulia, Jalshiri & Nazarpur) | BREB | DDP (Nayarhat, Birulia, Jalshiri & Nazarpur) Client - BREB | 1.2 | Birulia | Md.Azharul Haque 01732761574 Site Eng Usuf-01763521032 Shafiul Azam- 01755506232 | Md.Azharul Haque |  | 1732761574 | - | - | Deed Agreement | Birulia Project Manager Md.Azharul Haque 01732761574 Site Eng Usuf-01763521032 Shafiul Azam- 01755506232 | 26.10.2016 -12 Nos of base casting is complete for control building. 03.11.2016 -12 Nos of short column casting is complete, 1000 mm sand filling going on for control building, 400 mm sand filling is complete in switchyard area to start CC work for gantry foundation. 10.11.2016 -08 Nos of base of gantry casting is complete, Sand filling is complete up to grade beam of control building area & compaction is going on, excavation complete of 03 nos of base for boundary wall column. 17.11.2016 -08 Nos column of gantry foundation casting is complete, Rod fabrication is complete for grade beam. 24.11.2016 -Control room short column casting complete.Grade beam shuttering complete.Gantry tower base and short column casting complete.One base for XFR is complete.6 Nos of bases for boundary wall complete. 01.12.2016 -Control building: grade beam and column (FGL to PL) RCC casting complete.XFR : 01 Nos RCC base and 01 Nos base PCC casting complete and reinforcement binding & shuttering complete.2 Nos of EM tower base PCC casting complete.Boundary wall: 06 Nos short column RCC casting complete. 08.12.2016 -One base of XFR's RCC casting has been completed and another base’s two pedestals’ RCC casting has been completed.02 Nos of EM tower base RCC casting has been completed.02 Nos of boundary short column RCC and 02 Nos of boundary base PCC+RCC casting has been completed.Brick work has been completed from grade beam to PL of control building's.Some sand filling completed in front of control building. 15.12.2016 Two pedestal of another base RCC casting has been completed. 02.Twi nos of EM tower column RCC casting has been completed. 03.8nos of Gantry tower Columbus RCC casting has been completed.04.four nos column of control building's RCc casting has been completed. 05.Boundary wall: 6nos base RCC +7nos short column+10 nos base PCC casting has been completed. 22.12.2016 -4 Nos column of control building RCC casting has been completed.Boundary wall: 7 Nos RCC base +9 Nos short column +RCC Grade Beam 30m long+11nos base PCC casting has been completed. 29.12.2016 Boundary wall: 7nos RCC base+14nos short column Grade beam 10m long +9nos base PCC casting has been Completed.3 Nos control building columns half of above RCC casting has been completed.Septic tank & Soak well 's Brick work has been completed.Stair base:Earth work+ base(PCC+RCC)+2nos column RCC casting has been completed.LA,CB,CT base earthwork has been completed. 05.01.2017 -Boundary wall:12nos short column and 50m long Grade beam RCC casting has been completed.Stair base and column casting has been completed and first flight shuttering has been completed.Septic tank plaster completed.First Floor shuttering going on. 12.01.2017 --Boundary wall:05 Nos short column and 30m long Grade beam RCC casting has been completed.Base casting work has done for LA,CT foundation.05 Nos of base casting has done for Boundary. 19.01.2017 -Control building first floor RCC casting has been completed. 26.01.2017 -Control Building 12nos column(half of the below) RCC casting has been completed.VCB&CT base RCC casting has been completed.Boundary wall:20nos short column & 27m long Grade beam RCC casting has been completed.+ 45m long Brick work has been completed.Setting of transformer base plate has been completed. 02.02.2017 -VCB,CT,LA &VCB,CT column casting and net finishing has been completed. Control building beam shuttering and dasha setting has been completed.60% sand filling completed and running. 09.02.2017 -24m long grade beam RCC casting & 18 m long boundary brick work has been completed.Aux.XFR soling,RCC base & brick wall has been completed.Control building Roof slab shuttering & Rod binding completed. Switchyard earthing main mesh completed. 16.02.2017 -Control building Roof slab RCC casting has been completed and Ground floor ready for casting.25.6m long boundary grade beam RCC casting & some brick work has been completed. 23.02.2017 -RCC casting in ground floor of control room,27 meter long grade beam complete for boundary.05 Nos short column done for boundary wall. 02.03.2017 -25 m out side plaster work has been done for Boundary wall.Top slab plaster and plaster with net finishing work has been completed. -Celling plaster work is going on for control building. Approx. 65% sand filling work has been done. 09.03.2017 -4 Nos base PCC & 4 Nos RCC base & 4 Nos short column RCC casting completed,Boundary wall-35 m long copying RCC casting completed.10 no column(FGL to copying) RCC casting completed. RAMPS,RCC casting completed & porch slab shuttering ,rod binding completed. -control cabletrench18 m long base RCC casting completed 25m long power cable trench PCC casting completed -sand filling 90%completed. 16.03.2017 -Control cable trench 2Nos wall 15m long RCC casting done.Guard house grade beam RCC casting completed.Control building,linten,porch,slab,sunshed,brick work (80%),ceiling plaster complete.Boundary wall:9Nos base (PCC+RCC),9Nos short column RCC casting ,boundary wall 25% has been completed. 23.03.2017 -Power cable trench wall 40m long RCC casting Completed. Stair slab casting completed. Control building Ground floor and First floor brick work, lintel,fols Chad, plaster completed, Parapet wall brick work and inside plaster Completed. Boundary wall 6 Nos base (pcc+RCC+short column) casting completed. 30.03.2017 -80% plaster work and net finishing work has been done at Side wall in power & control cable trench.25m grad beam for boundary wall has done. 06.04.2017 -100% plaster work and net finishing work at Side wall in power & control cable trench. -45m grad beam for boundary wall has been done.14 Nos short column casting has been done. 13.04.2017 -12 Nos short column & 13m grade beam work for boundary wall and 06m Cable trench wall work has been completed. 20.04.2017 -07 Nos short column for boundary wall.27m long grade beam casting completed,45m long brick work completed.Power XFR er guide wall & pedestal RCC casting with net finishing.Sand filling 95% completed.Paint work,Mosaic work,tiles work, fencing bricks work is running, 27.04.2017 -10 Nos long column for boundary wall & 23m long grade beam casting has been completed.Control building ground floor & first floor mosaic Patten stone casting & grill fitting work has been completed. Guard house floor cast has done.Control building & boundary color work is continuing.27.04.2017-10 Nos long column for boundary wall & 23m long grade beam casting has been completed.Control building ground floor & first floor mosaic Patten stone casting & grill fitting work has been completed. -Guard house floor cast has done.Control building & boundary color work is continuing. 04.05.2017 -30m long brick wall making work has been completed.23m cosing casting and 02 Nos column casting work has been completed. 11.05.2017 -Road making work has been completed in front of control building.Fancy brick work is going on.Main gate installed & Paint work has been done. 18.05.2017 -3m wide road RCC casting has been completed. Fencing base casting completed.Tiles work completed and mosaic cutting work is going on.23m long Boundary wall plaster completed in both side. 25.05.2017 Fork work at roof floor & RCC casting of retaining wall and Sand filling work is continuing.Re-bar work for retaining wall work has been completed. 01.06.2017 Brick soling work done at control building ground floor,Brick masonry done at ground floor beam to plinth level.Form work is continuing at roof floor.RCC casting & Re-bar work done at retaining all.02 Nos RCC casting of gantry tower.Sand filling is going on. 08.06.2017 5” thickness Brick masonry work has done at boundary wall.Re-Bar work has been for Roof floor & retaining wall.08 Nos RCC casting of Gantry tower.Sand filling work is going on. 15.06.2017 Levelling & dressing work,Re-bar work for roof floor.70% RCC casting of retaining wall completed. Sand filling work is going on.Re-bar work for retaining wall has 80% completed. 22.06.2017 -Roof slab casting done. Leveling & dressing work has done.RCC casting done in retaining wall. Re bar work 80% has done.Sand filling work is going on. 29.06.2017 -Eid festival holidays, so No further update. 13.07.2017 Gantry tower casting complete(8Nos). 50% sand filling complete. RCC casting of retaining wall(Continuously) 90% complete. Ceiling plaster complete(Ground floor). Brick masonry for ground floor ( ground to lintel)
[7 empty] | Site Eng Usuf- |  | 1763521032 | - | - | Contract Date
[7 empty] | Shafiul Azam- |  | 1755506232 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Jun 14' 16 | Declaration of completion
1 | DDP (Nayarhat, Birulia, Jalshiri & Nazarpur) | BREB | DDP (Nayarhat, Birulia, Jalshiri & Nazarpur) Client - BREB | 1.3 | Jalshiri | Md.Azharul Haque 01732761574 Shafiul Azam- 01755506232 Sae-Nurislam 01883506757 | Md.Azharul Haque |  | 1732761574 | - | - | Deed Agreement | Jalshiri Project Manager Md.Azharul Haque 01732761574 Shafiul Azam- 01755506232 Sae-Nurislam 01883506757 | 27.10.2016 -Local problem solve.Deep tube well work done. 03.11.2016 -Store area is ready by brick soling to keep stone chips & sand, one house is also ready to keep clay of pile. 10.11.2016 -We are waiting for stone chips to start pile for retaining wall. 17.11.2016 Earth excavation and rod fabrication going on for boundary wall, construction materials arrived at site for pile. 24.11.2016 -Water leveling -Pointing & leveling of pilling for retaining wall..2 no CC casting of boundary wall base done. 01.12.2016 -RCC casting of short column (14 Nos).Sand filling of column base.Pile boring of retaining wall. 08.12.2016 -Approx. 5487 cft. Sand has been filled.Grade beam prepare work is going on. 15.12.2016 -Sand filling completed only for control building (EGL to column base).Pilling layout done.02 Nos casting done for grade beam. 22.12.2016 -30.48 meter length ,0.7 meter height and 0.250 meter thick brick work done for boundary wall (partially.) -Cast in C2 pile (12nos),drilling ,washing & casting done. 29.12.2016 -Lay out details of control building.Pile boring, washing & casting work has been done of retaining wall (total 22 Nos). 05.01.2017 -Pile work has been completed for retaining wall (33 Nos).Earth excavation has completed for control building footing (12 Nos). 12.01.2017 -10 Nos ofCC casting work has done for footing base of control building. 19.01.2017 -10 Nos RCC casting has been done for footing base in control building.10 Nos footing or short column shuttering has been completed. 26.01.2017 -10 Nos RCC casting has been done for footing or short column (control building). 02.02.2017 -12 Nos RCC footing casting work has done in control building.30 running meter grade beam casting work done for boundary wall. -Back filling,levelling and dressing work is going on. 09.02.2017 -Pile broken,Back filling,leveling and compaction work is going on.Layout of septic tank, soak well has been completed. 16.02.2017 -Brick wall is running for septic tank.Soil digging work done for Soak well.Back filling work has been finished up to Grade beam of Building.03 Nos pile broken done.15 Nos Shuttering work have been finished in boundary wall. 23.02.2017 -Pile breaking work is running.Back filling,leveling & compaction has been done.Brick work of septic tank has been done. Excavation complete of soak well.12 Nos RCC column casting done of boundary wall. 02.03.2017 -Shuttering work done for Grade beam in control building.Brick wall has been make at boundary wall.20 Nos Pile break work has been done. 09.03.2017 -Grade beam casting in control building. -15 Nos Pile cap shuttering has been done. -27 Nos pile has been done. 16.03.2017 -RCC column casting in control building. -CC casting of pile (17Nos) completed -Pile break completed. 23.03.2107 -Brick masonry 10”thikness(grade beam to plinth level).CC casting of pile has done.Final layout of switchyard.Re-bar work for pile cap. 30.03.2017 -08Nos RCC casting of pile cap.08 Nos CC base casting work has been done in 33kV gantry structure.Rebar work for pile cap & gantry column. -Brick masonry 10” thickness for soak well. 06.04.2017 -23Nos RCC casting of pile cap.Revar work has been done in 33kV gantry structure.Rebar work for pile cap & gantry column.First grad beam work has been done. 13.04.2017 -Slab casting work done at first floor.23 Nos RCC pile cap has been caste.bar work is running for retaining wall. 20.04.2017 -33 Nos RCC pile cap has been caste.Rebar work is running for Gantry structure.Shuttering work is going on for boundary wall.Sand filling work is going on. 27.04.2017 -02 Nos boundary gate column and 04 Nos guard house column casting is completed. -Mosaic work is going on.paint work is going on. -Control building right side plaster work is going on. -Control and power cable trench plaster work and tra work is completed. -02 Nos mk box work completed -Sand filling is going on. 04.05.2017 -08 Nos base casting work has been completed for Gantry tower.30ft long & 5ft height retaining wall work has been completed 08 Nos column casting work is continuing at control building 2nd floor. 11.05.2017 -04 Nos column casting work has been completed.Rebar work is going on at retaining wall. 18.05.2017 -40% retaining wall has completed. 12Nos column cast has completed at control building in first floor.Sand filling work is going on. 25.05.2017 Boundary wall plaster work, Fencing work, electrical wiring ,sanitary work for control building is going on.01 No Bath room tiles work & RCC casting work has been completed.15 Nos Fencing RCC column casting has been done. 01.06.2017 Boundary plaster work is going on.Mosaic work at first floor & Celling work has been completed.Paint work & Fencing work is going on. 01 No bathroom & complain room work is completed. 08.06.2017 Boundary plaster work, paint work is going on.Mosaic work for ground floor, celling work,2 bathroom and office and rest room work, Fire alarming work, Fencing brick work, Window Thai work for Ist floor,02 Nos pit work has been completed.Surface drain work is going on for out side of control building.Guard house 10 mm brick work is completed. 15.06.2017 Boundary plaster work, paint work & Guard house plaster work is going on.Control building front side surface drain and apron work,SS work, Window Thai work for ground floor,AC connection work,Electrical wiring, fitting work, switch yard flat soling and NFC work (half) for laying gravel stone work has been done. 22.06.2017 -Boundary plaster work and paint work is going on.Switch yard flat soling and ncf work has been completed for laying gravel stone.Guard house plaster work has completed . 29.06.2017 -Boundary plaster work & paint work is going on. -Pump house has been completed. -Earth cutting work is going on for boundary surface drain. 06.07.2017 -Boundary outside plaster work is going on. paint work is going on. swing door work is going on. guard house thai work is going on. surface drain work is going. 13.07.2017 Boundary outside plaster work is complete. Lime terracing work is going on. 4nos pit work is complete surface drain plaster work is complete.
[7 empty] | Shafiul Azam- |  | 1755506232 | - | - | Contract Date
[7 empty] | Sae-Nurislam |  | 1883506757 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Jun 14' 16 | Declaration of completion
1 | DDP (Nayarhat, Birulia, Jalshiri & Nazarpur) | BREB | DDP (Nayarhat, Birulia, Jalshiri & Nazarpur) Client - BREB | 1.4 | Nazarpur | Md.Azharul Haque 01732761574 SAE. Monjurul-01766736720 Shafiul Azam- 01755506232 | Md.Azharul Haque |  | 1732761574 | - | - | Deed Agreement | Nazarpur Project Manager Md.Azharul Haque 01732761574 SAE. Monjurul-01766736720 Shafiul Azam- 01755506232 | 26.10.2016 -CC work is complete, 06 Nos of base ready for casting of control building. 03.11.2016 12 Nos of short column casting is complete of control building, 05 Nos of CC work is complete for gantry foundation. 10.11.2016 -12 Nos of base casting complete of gantry foundation, preparation is going on for grade beam casting of control building. 17.11.2016 -02 Nos column of gantry foundation, one base of transformer foundation and grade beam of control building casting is complete. 24.11.2016 -Gantry tower and Main building of 04 nos of Column shuttering is completed. -XFR foundation partially complete. 01.12.2016 -Septic tank bricks work is going on. 08.12.2016 -72 m3 Back filling done for gantry tower area. -Popping work is going on for roof beam -Septic tank brick work is going on. -04 Nos column (half of above) of control building shuttering is complete.Grade beam & column stirrup. -02 pcc casting complete for CB,CT,LA and CB,CT base. -Earth excavation is going on for boundary wall. 15.12.2016 -Earth excavation work is going on for boundary wall.Casting work is complete for CB, CT, LA & CB, CT Base foundation & control room 03 nos column (half of above).Frame work is going on for 1st floor beam. 22.12.2016 Earth excavation work is going on for boundary wall. Casting work is complete for CB, LA & CB, CT column foundation & 08 Nos boundary wall column base foundation. Form work is complete for 1st floor beam & slab.Rod fabrication is going on for 1st floor beam. 29.12.2016 Earth excavation work is going on for boundary wall north side. Casting work is complete for 04 Nos CB wall 01 Nos CT, LA column.Form work is complete for first floor beam,slab and satir.we are ready for first floor slab casting. 13 Nos boundary column base pcc casting is complete. 05.01.2017 -Earth excavation work is going on for boundary wall north side Casting work is complete for 1st floor slab,stair 08 Nos base and 6 Nos column for boundary wall. 13 Nos pcc casting is complete for boundary base. 12.01.2017 -Earthing connection works has done for power cable in Search monitor. 19.01.2017 -02 Nos XFR floor.08 Nos control room column and 15 Nos boundary base RCC casting has been completed.12 Nos PCC for boundary wall has done. 26.01.2017 -Frame work is going on for 06 Nos control building column,and 06 Nos short column for boundary wall. 02.02.2017 -Roof slab and stair slab casting is complete.03 nos column casting is complete for control building 1st floor.01 nos casting is complete for transportation foundation floor side wall. 16.02.2017 -11 Nos base,20 Nos short column RCC casting has been completed.Earth excavation in front side & 250 mm bricks works is going on for boundary wall.Sand filling and mechanical structure work is going on. 23.02.2017 -Sand filling is going on, -09 Nos base RCC casting is completed for boundary wall,Rod binding is going on for 2nd grade beam.ground floor ceiling plaster,250 mm brick works height 600mm & sand filling is completed for 08 nos gantry tower. 02.03.2017 -Ground floor brick flat soling & rod binding work has been completed.Auxiliary TR work,First floor brick work,Sand filling work and control cable trench work is going on. 09.03.2017 -11 Nos short column,01 Nos grade beam Rcc casting is complete for boundary wall. Ground floor and ramp Rcc casting is complete. 1st floor brick work is going on. 03 Nos sunshade casting is complete. Sand filling is going on. Roof top parapet brick work is complete. 16.03.2017 -13 Nos short column Rcc casting is completed for boundary wall. 1st floor & ground floor brick work is going on. 05 Nos sunshade casting is completed. -Sand filling is going on. -10 m control cable trench wall RCC casting is completed. front side boundary wall brick work is completed (1st to 2nd GB). 23.03.2017 -14 Nos long column RCC casting is completed for boundary wall. 1st floor brick work completed & ground floor brick work is going on. 04 Nos guard house short column casting is completed. Sand filling is going on.8 m control cable trench wall RCC casting is completed. 30.03.2017 -14 Nos long column RCC casting is completed for boundary wall.ist floor plaster work is completed. ground floor 2 Nos false slab and 03 Nos casting work is completed. south side brick work is going on for boundary wall.sand filling is going on. control and power cable trench work is going on.30m Grade Beam casting is completed for boundary wall. 06.04.2017 -21 Nos long column RCC casting is completed for boundary wall. Ground floor plaster work is going on. Front side brick work is going on for boundary wall.sand filling is going on. control and power cable trench work is going on.35 m g.b casting is completed for boundary wall. 13.04.2017 21 Nos long column RCC casting is completed for boundary wall.brick work is going on for boundary wall.Sand filling is going on.Control and power cable trench work is going on. 20.04.2017 -02 Nos long column RCC casting is completed for boundary wall.Brick work is going on for boundary wall. Sand filling is going on.Control and power cable trench work is going on.Sanitary work is going on. -Building plaster work is going on. 27.04.2017 02 Nos & 04 Nos RCC casting has completed for gate column & guard house column.Plaster work is continuing in Boundary wall & control building right side. 150 ft coping cast work has been done. 04.05.2017 -150 ft coping & 75 ft guide wall casting has been completed.Rain water pipe has completed.Sand filling work & mosaic work is going on at control building right side. 11.05.2017 -Boundary coping casting work and Duct work has been completed. Mosaic work,Paint work, Fencing brick work is going on. 3 side control building apron work is completed. Sand filling and internal road guide wall has been completed. 18.05.2017 -Road guide wall & leveling dressing is completed.herring brick work is going on.Facing tiles & paint work is going on.Mosaic cutting has completed.Guard room drop wall casting is completed.Deck wall plaster,boundary plaster is going on. 25.05.2017 25 Nos pile cast has been done.15 Nos short column cast work has done at top of grade beam. 01.06.2017 16 Nos pile casting for control room.01 No grade beam casting for boundary south side.03 Nos long column casting for boundary north side. Earth work is continuing for retaining wall. 15.06.2017 73 m base cast work for retaining wall.05 Nos long column casting has been completed for boundary. 22.06.2017 -02 Nos long column cast has been completed.01 m height & 43 m length retaining wall steam has done. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -45m lenth,01m height retaining wall work has done.Brick work has done at boundary wall.05 base CC casting has done. 13.07.2017 Retaining wall stem casting length -25m, height-1m.Control building 6 base casting.CC casting for another retaining wall road side.
[7 empty] | SAE. Monjurul- |  | 1766736720 | - | - | Contract Date
[7 empty] | Shafiul Azam- |  | 1755506232 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Jun 14' 16 | Declaration of completion
2 | Bindur Mour, Rajshahi | BREB | Bindur Mour, Rajshahi Client - BREB | 2 | Rajshahi | Md.Azharul Haque 01732761574 Selim 01787680493 | Md.Azharul Haque |  | 1732761574 | - | - | Deed Agreement | Rajshahi Project Manager Md.Azharul Haque 01732761574 Selim 01787680493 | 20.10.2016 26.10.2016 03.11.2016 Site is under water. 10.11.2016 Soil test is going on from 07Nov,2016. 17.11.2016 -Soil test is complete and earth filling preparation is going on. 24.11.2016 -Pipe setting (7400 ft ) work done for dredger.Land measure work doing for doing the remaining sand filling. 01.12.2016 -Approximate 18600 cft Sand filling work done. 08.12.2016 -Sand filling done approx. 1,23,300 cft. 15.12.2016 -Sand filling done approx 2,25,000 ( 1,09,700 cft this week). 22.12.2016 -Sand filling done approx. 36,300 cft. 29.12.2016 -Sand filling done approx. 83300 cft. 05.01.2017 -Earth filling work has done. 12.01.2017 -Temporary Office room,Labour shed and Materials shed has maked. 19.01.2017 -House for piling is under process. 02.02.2017 -Pile work & boundary wall work is going on. 09.02.2017 -No further update. 16.02.2017 -Submersible pump has been installed. 23.02.2017 -No further update. 02.03.2017 -Making of new platform for rod placing(70’ x 30’). -Site layout has been completed. 09.03.2017 -Soil digging work done for pile point. -Rod,Cement arrived at site. 16.03.2017 -No further update. 23.3.2017 -70 Nos pile point has make,Stone,Sand arrived at site. 30.03.2017 -25 Nos pile point has been made-Stone, Sand arrived at site. 06.04.2017 -Soil excavation work done for base foundation both (north,south) side, 13.04.2017 20 Nos base shuttering work has been done at boundary wall. 20.04.2017 19 Nos CC work has been done in base at boundary wall.10 Nos rod binding work has been done in base at boundary wall. 27.04.2017 -14 Nos base casting work has been done for boundary wall.Rod binding work is going on. 04.05.2017 -04 Nos base and 19 Nos short column casting work has been done for boundary wall. 11.05.2017 -03 Nos base casting work has been done for boundary. 01 No grade beam casting & 09 Nos short column cast has been completed in up grade beam.01 No pile has been cast (size-400*400*700). 18.05.2017 -35 Nos pile work has been cast.02 Nos grade beam cast in boundary wall. 25.05.2017 Air conditioner fitting work is going on. New electrical wiring work is continuing. 01.06.2017 Air conditioner fitting work and Electrical work is continuing. 08.06.2017 Air conditioner fitting work is continuing. 15.06.2017 -Air conditioner fitting work is going on. 22.06.2017 -No further update 29.06.2017 -No further update. (01 Air conditioner yet to be installed.) PDB Division-04 will be shift to Bindur more. 06.07.2017 13.07.2017 -No further update, | 20.07.2017 -No further update,
[7 empty] | Selim |  | 1787680493 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Mar 31' 16 | Declaration of completion
3 | Supply,Installation,Testing & Commissioning of 33/11 kV, 2x10/14 MVA,Substation on Turnkey under Dhaka PBS-1 Client-BREB | BREB | Supply,Installation,Testing & Commissioning of 33/11 kV, 2x10/14 MVA,Substation on Turnkey under Dhaka PBS-1 Client-BREB Client - BREB | 3 | SAVAR-16 (Nabinagor) | Md.Azharul Haque 01732761574 SAE. Shahjalal 01755445178 Shafiul Azam- 01755506232 | Md.Azharul Haque |  | 1732761574 | - | - | Deed Agreement | SAVAR-16 (Nabinagor) Project Manager Md.Azharul Haque 01732761574 SAE. Shahjalal 01755445178 Shafiul Azam- 01755506232 | Sand filling done approx. 110000cft,Two months ago start filling work. 25.05.2017 06 Nos pile casting has been done. 01.06.2017 12nos pile RCC casting of control building has been completed and Pile layout for Boundary wall has been done. 08.06.2017 Pile work has been finished for retaining wall & control building.soil excavation has been completed for boundary wall. 15.06.2017 Boundary column base & short column has been completed up to first grade beam.Pile work has been completed. 22.06.2017 -21 Nos short column casting has been completed.22m long grade beam work has done.07 Nos Base casting has been completed. 29.06.2017 -No further update. 06.07.2017 Retaining wall soil cutting work is going on.Earth excavation work has been completed for control building.06 Nos pile head broken work has been completed.04 Nos short column has been completed. 13.07.2017 Control building's 3nos base earth work completed,7nos pile head breaking completed & 6nos base casting completed. Boundary Grade beam 43m long, 14nos long column casting completed & Brick work running.
[7 empty] | SAE. Shahjalal |  | 1755445178 | - | - | Contract Date
[7 empty] | Shafiul Azam- |  | 1755506232 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Jun 14' 16 | Declaration of completion
4 | Turnkey contract for design,supply,construction,Installation,Testing & Commissioning for 33kV Bay Extension work and Bus-Bar related works at PABNA 132/33 kV Grid substation for PABNA PBS-1 & 2 under BREB. Client–BREB | BREB | Turnkey contract for design,supply,construction,Installation,Testing & Commissioning for 33kV Bay Extension work and Bus-Bar related works at PABNA 132/33 kV Grid substation for PABNA PBS-1 & 2 under BREB. Client–BREB | 4 | PABNA | Md.Azharul Haque 01732761574 Sae,Rahul bishwas 01708131718 Shafiul Azam- 01755506232 | Md.Azharul Haque |  | 1732761574 | - | - | Deed Agreement | PABNA Project Manager Md.Azharul Haque 01732761574 Sae,Rahul bishwas 01708131718 Shafiul Azam- 01755506232 | Soil excavation work is going on.Lay out work has been done.All design ,drawing has been approved by BREB.Soil test has been finished. 25.05.2017 -Soil excavation work is going on. 01.06.2017 Levelling & dressing Started .900 cft soil excavated for levelling and dressing. Levelling dressing & layout complete. Foundation excavation is going on. 08.06.2017 Cc casting work has been completed for Gantry tower & equipment's. Rebar work also going on. 15.06.2017 Gantry tower re-bar work & base casting completed.VCB 7 CT foundation CC casting completed.DS & LA foundation excavation work has started. 22.06.2017 -Gantry tower cast work has been done, equipment base work yet to be done. 29.06.2017 -04 Nos gantry tower base casting has done.02 Nos VCB base casting has been done. 06.07.2017 03 Nos column has been done for VCB, 04 Nos base has been completed for DS. 13.07.2017 DS 1set ,VCB 1set ,LA 2set.column CC with RCC are completed
[7 empty] | Sae,Rahul bishwas |  | 1708131718 | - | - | Contract Date
[7 empty] | Shafiul Azam- |  | 1755506232 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Jun 14' 16 | Declaration of completion
5 | CSDP (Banskhali, Dagonbhuyan ,Daudkandi ,Sylhet) | BREB | CSDP (Banskhali, Dagonbhuyan ,Daudkandi ,Sylhet) Client - BREB | 5.1 | Banskhali | Shafiq Ahmed 01713147024 | Shafiq Ahmed |  | 1713147024 | - | - | Deed Agreement | Banskhali Project Manager Shafiq Ahmed 01713147024 | 26.10.2016 -Control wiring is delayed due to control cable and it's accessories. 03.11.2016 -Control cable arrived at site, wiring going on, 33 & 11 kV GIS panels are waiting for vacuum pump for gas filling and electrical operation, order of power cable plug placed to Engr Reza, 33 kV 300 rm & 11 kV 500 rm Power cable arrived at site, slab for septic tank & sock well casting complete. 10.11.2016 Panel wiring complete, remaining earthing work going on, gas filling start from 08 Nov,2016. 17.11.2016 -Gas filling complete except one panel,Power cable laying processing going on. 24.11.2016 -Auxiliary Transformer carrying to site.Power cable (300rm,500rm) laying done for 33kV & 11kV. 01.12.2016 -33/11 kV electrical site GIS test completed.Cable ladder making work going on.XFR shifted to katakhali from Bindurmour. 08.12.2016 -TR:1 XFR have been installed.Control cable wiring is completed in Tap changer MRL box.02 Nos Fan fitting completed.02 Nos of dropout wall mount fuse have been installed for auxiliary XFR. 15.12.2016 -260 m Cable laying (120rm) from auxiliary XFR to AC distribution panel going on.Pipe fittings completed for auxiliary XFR.Jumping wire/ hook up work done for LA to isolator. 22.12.2016 -Auxiliary & 11kV out site power cable termination completed. 29.12.2016 -Termination has been done for XFR (11kV,33kV) part in side of control room. 05.01.2017 -Motor coil repair work has done in side of GIS. 12.01.2017 -Earthing work has done for power cable near pole area. 19.01.2017 -No update yet. 26.01.2017 -Fire fighting work is going on. 02.02.2017 -Fire fighting work is continuing in control building. 09.02.2017 -Fire fighting set-up work is continuing in control building. 16.02.2017 -04 Nos Air-conditioner has been installed. 23.02.2017 -Air-conditioner work is going on. 02.03.2017 -Channel work for Air-conditioner work is going on. 09.03.2017 Fire fighting set-up work is continued in control building. 16.03.2017 23.03.2017 30.03.2017 -No further update. 06.04.2017 -CC work is going on in ground floor. 13.04.2017 -GIS termination work is going on.Pad stone work has been for 2Nos XFR & Auxiliary XFR. 20.04.2017 -GIS termination and Pad stone work has been completed. 27.04.2017 -Pre commissioning work is going on. 04.05.2017 -Pre commissioning work has been finished. 11.05.2017 -Air conditioner fitting work is going on.PVC pipe has been laid from ground floor MDB box to first floor DB box. 18.05.2017 -No further update. 25.05.2017 Retaining wall second lift has completed. Plaster work has been completed in control building first floor. As installed work has done.CC cast work done for all cable trench. 01.06.2017 Plaster work is going on at first floor in control building.Brick work has been finished at ground floor in control building. 08.06.2017 Plaster work is going on at ground floor in control building.Facing brick work is going on.Slab work is continuing for cable trench. 15.06.2017 Ground floor plaster work done.First floor tiles work done, Safety tank brick work done. DS & CB erection work done. 22.06.2017 -Tiles work has done at control building. Facing brick work done at out side. Ground floor plaster work has been done.Window setting work has been completed. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -Plaster work has been done.Facing brick work has been completed. 13.07.2017 Control room building out side plaster work running.Retaining wall grad beam 2 casting running.Erection work running.Earth boring work running.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Jun 14' 17 | Declaration of completion
5 | CSDP (Banskhali, Dagonbhuyan ,Daudkandi ,Sylhet) | BREB | CSDP (Banskhali, Dagonbhuyan ,Daudkandi ,Sylhet) Client - BREB | 5.2 | Dagonbhuyan, Feni | Shafiq Ahmed 01713147024 | Shafiq Ahmed |  | 1713147024 | - | - | Deed Agreement | Dagonbhuyan, Feni Project Manager Shafiq Ahmed 01713147024 | 16.10.2016 Earth filling is going on.Materilas mobilization started. Pilling team also mobilized. Hope the piliing can be started from 18 Oct 2016. 23.10.2016 -Civil works started. 27.10.2016 -Pilling work start. 03.11.2016 Pilling work going on. 10.11.2016 -Pilling work running. 17.1.2016 -Boundary wall piling is continued (46 Nos complete.) -Land filling halted for local govt. administration interference. 24.11.2016 -Civil works continued. 01.12.2016 -90 Nos of piling completed of boundary wall out of 111 Nos. -Land Filling continues. 08.12.2016 -Pile work for Boundary wall have been completed. 15.12.2016 -Pile head breaking work has been completed in retaining wall area.Sand filling continuing. 22.12.2016 -Boundary retaining wall work is continued.Building pile work has been done.-Back filling work is going on for switch yard area. 29.12.2016 -Switch yard Gantry foundation work has been continued. 05.01.2017 -Boundary wall Piling Head broken has Continue. -Land Filling stop, For local administration. -4 Nos base has complete for Gantry foundation. 12.01.2017 -Sand filling has continued. -Boundary wall Piling Head broken has Continued. -Gantry foundation. 50% has complete. 19.01.2017 -XFR foundation work is continued.VCB foundation work is going on.Pile cap breaking work of control building is continued. 26.01.2017 -Building pile head broken work has completed. -01 No foundation & base work has been done for XFR.Sand Filling is continuing. 02.02.2017 -Sand filling is continuing. -Building pile cap CC work has completed.Civil works for CB foundation has been completed. 09.02.2017 -02 Nos CB foundation work has been done.06 Nos building base has been completed. 16.02.2017 -Same as before. 23.02.2017 -Back filling work done approx.3500ft.01 No XFR pad making done. Base,grade beam,long column,short column is completed in control building. 02.03.2017 -Preparation work has been done for Roof top Casting. -XFR set on pad. -Gantry structure ,tower beam has been completed. 09.03.2017 -Retaining wall works is going on. -Slab works is going on for building 2nd floor, -Structure has been completed for tower beam. 16.03.2017 -Preparation work for 2nd floor casting. 23.03.2017 -Retaining wall work is going on. 30.03.2017 -Casting work for Retaining wall is going on. 06.04.2017 -Casting work for Retaining wall is going on. Brick work for control building has been continued.Cable work is going on. 13.04.2017 53m Retaining wall work has been completed. Building bricks works & cable trench works is going on.Safety tank & soak coil work going on. 20.04.2017 -Retaining wall and Building bricks works is going on. 27.04.2017 -Brick work is continuing for control building.Retaining wall work has been done in control building. 04.05.2017 -13m base casting done for cable trench work.Brick wall work has been done first floor of Control room building.XFR base-2 column has been completed.All Base work has been completed in ground floor of control building. 11.05.2017 -Brick wall work is continuing for control building.RCC casting work has been done in Cable trench at Switchyard.RCC casting work has been completed in retaining wall. 18.05.2017 -Plaster work is going on at control building. Cable trench work is going on. 25.05.2017 Out side Plaster work is going on at control building. Cable trench work has been completed. 01.06.2017 Tiles work is going on.Column casting at XFR foundation. 08.06.2017 Tiles work is going on. Surface drain & Toilet tank making work is going on. 15.06.2017 Brick wall making work is going on.Column work has been completed for XFR.Surface drain work and Sand filling work is continuing. 22.06.2017 -Sand filling work is continuing.Brick wall work is going on. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 XFR foundation base column,Sand filling work is going on.Building brick work is going on. 13.07.2017 Wiring work running. Mechanical work running.Earth-ing 85% work finished.Building paint work running.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Jun 14' 17 | Declaration of completion
5 | CSDP (Banskhali, Dagonbhuyan ,Daudkandi ,Sylhet) | BREB | CSDP (Banskhali, Dagonbhuyan ,Daudkandi ,Sylhet) Client - BREB | 5.3 | Daudkandi | Shafiq Ahmed 01713147024 Site Engr Golam Morshed-01787687953 | Shafiq Ahmed |  | 1713147024 | - | - | Deed Agreement | Daudkandi Project Manager Shafiq Ahmed 01713147024 Site Engr Golam Morshed-01787687953 | 16.10.2016 -Earth Filling is going on. Started mobilization, Layout given. Pilling works can be started at the earliest. 23.10.2016 -Civil works started. 27.10.2016 -Mobilization complete. 03.11.2016 - Pile work will be started on 08 Nov,2016 (Expected) 10.11.2016 -Pilling work going on. 17.11.2016 -Boundary Piling Continues. -Land Filling not continued for payment. 24.11.2016 -Civil works continued. 01.12.2016 -Building & Boundary wall Piling Completed.Land Filling is continuing. 08.12.2016 -Switchyard foundation work is going on. 15.12.2016 -Pile head broken work has completed in retaining wall area.Switchyard foundation work is going on.Sand filling continuing. 22.12.2016 -Boundary retaining wall work is continued.Switchyard foundation work is going on -Back filling work is going on for switch yard area. 29.12.2016 -Switch yard Gantry foundation work has been continued. 05.01.2017 -Boundary Retaining wall RCC complete only top cover incomplete.Transformer foundation has continue -Building Colum Base CC has completed.Land Filling stop, For local administration.4 Nos base has complete for Gantry foundation. 12.01.2017 -Switchyard foundation work has 70% completed. -Rod cutting and other preparation work has started for Control building. 19.01.2017 -Column and base work has been completed in control building.Sand filling continued for switch yard. 26.01.2017 -Building grade beam & shutter column work has completed.Sand Filling is continuing. 02.02.2017 -Column work has been done in first floor.Beam shuttering work is going on in first floor. 09.02.2017 -Slab work & rod binding work is continuing at first floor. 16.02.2017 -Preparation work is going on for RCC Casting.Tower erection work is going on. 23.02.2017 -RCC casting is going on in control building first floor roof.XFR top base plate setting work is going on, 02.03.2017 -Rod binding work has been doing for column.Column Structure work done for beam. 09.03.2017 -Slab works is going on for building 2nd floor, -Structure has been completed for switchyard. 16.03.2017 -2ND floor casting has been done. 23.03.2017 -Brick work for building and Electrical work is going on. 30.03.2017 -Brick work for control building.Coffin cast for retaining wall. 06.04.2017 -Brick work is going on for control building.Coffin cast for retaining wall. 13.04.2017 Building bricks works & cable trench works is going on. 20.04.2017 Building bricks works is continuing. 27.04.2017 Bas errection work is continuing.Brick work is continuing for control building. 04.05.2017 -Bas bar errection work has been completed.Brick wall work is continuing for control building.Power cable trench work is going on. 11.05.2017 Plaster work is going on at control building.Cable trench work is going on. 18.05.2017 Plaster work is going on at control building. Cable trench work is going on. 25.05.2017 Control building brick work. Lenten & sun shed RCC cast work has been done. 01.06.2017 Control room brick work & plaster work has been done.Grill fittings work has been done at ground floor in control building.Filling work is going on.Brick work & plaster work for retaining wall is going on. 08.06.2017 Plaster work for control building,Base wall cast has been done for Retaining wall & guide wall. Limestone cast has been done at control building roof top. Sand filling work is continuing. 15.06.2017 Control room first floor plaster completed.Tiles work & Cable trench work is going on.Roof slab lime terracing Pump boring has been completed. Approach road filling work filling work on going. 22.06.2017 -Tiles work & Cable trench work is going on. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -Boundary wall rod binding work is going on.Plaster work for control building. 13.07.2017 Civil work running. Control room plaster work running. Boundary wall plaster running.Fencing post column running. |  |  |  | 17.11.2016 Work stopped for payment issue.
[7 empty] | Site Engr Golam Morshed- |  | 1787687953 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Jun 14' 17 | Declaration of completion
5 | CSDP (Banskhali, Dagonbhuyan ,Daudkandi ,Sylhet) | BREB | CSDP (Banskhali, Dagonbhuyan ,Daudkandi ,Sylhet) Client - BREB | 5.4 | Sylhet | Shafiq Ahmed 01713147024 | Shafiq Ahmed |  | 1713147024 | - | - | Deed Agreement | Sylhet Project Manager Shafiq Ahmed 01713147024 | 16.10.2016 -Layout given on Oct09, 2016 but it was changed by REB on Oct10,2016. As per new layout earth filling area will be increased & civil design needs to be changed. Letter given to REB .Contractor:Builders Aid 23.10.2016 27.10.2016 -No further update 03.11.2016 -Revised drawing submitted. 10.11.2016 -Earth filling start. 17.11.2016 -Site Mobilization Complete. -Land Filling continues. 24.11.2016 -No further update. 01.12.2016 -Electricity line, Labor Shade, Temporary Water Pump are complete.Land Filling continued. 08.12.2016 -Earth filling is going on. -Approach road making work is continued. 15.12.2016 -Switchyard foundation work is going on.Sand filling continuing. 22.12.2016 -Switchyard foundation work is continued.Sand filling work is continued. 29.12.2016 -Building finishing work has been continued. 05.01.2017 -6 Nos base has complete for Gantry foundation.Transformer foundation has continue. -CB foundation work has continued.Land Filling has continue. 12.01.2017 -Foundation of gantry structure has completed. -VCB foundation work has been completed. -XFR foundation work has done approx. 70%. -Sand filling has continued. 19.01.2017 -Sand filling is going on. 26.01.2017 -Cable trench slab making work is continuing. -Sand Filling is continuing. 09.02.2017 -Pile work has completed for control building. 16.02.2017 -Pile work has been done for control building & retaining wall.Cable trench work is going on in side of switchyard. 23.02.2017 -Cable trench work has been done in side of switchyard.06 Nos pile cap work is done at control room.approx.50% Back filling work is done. 02.03.2017 -Grade beam of control room RCC casting work has been done.01 No XFR top pad RCC casting work done. 09.03.2017 -Slab works is going on for building 1st floor, 16.03.2017 -Roof casting work is going on,Earth excavation for retaining wall is going on. XFR arrived at site. 23.03.2017 -10m Column casting work has done for retaining wall.Gantry structure work is going on. 30.03.2017 -Partial Column casting work has done for retaining wall.12 Nos column has done in Ist floor for control building. 06.04.2017 -Creeker work for column, Roof slab work has been done.CC casting work is going on for Safety tank. 13.04.2017 -Second floor casting has been completed.Retaining wall & Boundary wall work is going on. 20.04.2017 -Retaining wall work is going on.Ceiling plaster work has been done. 27.04.2017 -Brick work is continuing for Boundary wall. 04.05.2017 -Sand filling work is going on in control building.Retaining wall work is continuing (brick work, base foundation, grade beam etc.) 11.05.2017 -Plaster work has been completed at Control building.Guide wall making work is going on. 18.05.2017 -Brick work for control building is going on.Boundary wall brick work, column work & beam work is going on. 25.05.2017 Lenten and Brick work is going on at ground floor. Cable trench CC & Rod binding work has been completed.Sand filling work is going on. 01.06.2017 Brick work is going on at first floor in control building.Centering open work has been completed at first floor. 08.06.2017 Brick work has been finished for control building 2nd floor.Cable trench wall casting work has been done. 15.06.2017 Plaster work has been completed at ground & first floor in control building. 22.06.2017 -Plaster work & finishing work has been done at control building. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 Saftitank,Toilet making work has been completed.Electrical wiring preparation work is going on. 13.07.2017 Building outside plaster, Toilet roof , parapet wall work running.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Jun 14' 17 | Declaration of completion
6 | 33kV GIS & 11kV AIS installation at Shyampur | DPDC | 33kV GIS & 11kV AIS installation at Shyampur Client - DPDC | 6 | Shyampur | Shafiq Ahmed 01713147024 | Shafiq Ahmed |  | 1713147024 | - | - | Deed Agreement | Shyampur Project Manager Shafiq Ahmed 01713147024 | 23.10.2016 -Contractor not yet started mobilization. 27.10.2016 -Mobilization Started. 03.11.2016 -Mobilization completed. 10.11.2016 -Mobilization going on 24.11.2016 -No further update. 01.12.2016 -Site Mobilization Complete. -Pile Purpose soil digging continued. 08.12.2016 -Switchyard foundation: soil digging work is going on. 15.12.2106 -Building pile work is going on. 22.12.2016 -Switchyard gantry foundation work is going on.Boundary pile work is continued.Pile for building work has been completed. 29.12.2016 -XFR base RCC work has going on. -Foundation work is continued. 05.01.2017 -03 Nos Gantry base RCC work has done.43 Nos of Boundary Pile has done. -Building pile head broken work has continuing. 12.01.2017 -CC casting work has continued for Retaining wall. -CC work has started after pile cap broken. 19-01-2017 -Retaining wall work is continued.04 Nos Switchyard gantry foundation work is completed.Building column’s CC casting work completed. 26.01.2017 -06 Nos Building base has been completed. -Boundary retaining wall base has been completed. -04 Nos Switchyard gantry foundation work is completed. 02.02.2017 -Retaining wall works is going on.XFR foundation work is continuing. Building all base has been complete. 09.02.2017 -Retaining wall works is going on approx.310 ft. & 6 ft.height done.Grade beam rod binding work is going on. 16.02.2017 -Approx. 80% of Retaining wall work has done. 23.02.2017 -Approx. 90% of Retaining wall work is done. 02.03.2017 -07 Nos gantry tower foundation work done. 16.03.2017 -Foundation work is going on for XFR.Retaining wall work is going on.20% wok done for control building. 23.03.2017 -Shuttering work has been done for first floor slab. 30.03.2017 -Rod binding work is going on for control building Ist floor. 06.04.2017 -Preparation work is going on for RCC casting (centering) in control room first floor. 13.04.2017 -Tower errection work is going on.First floor slab casting has been completed. Second floor column work is going on. 20.04.2017 -Guide wall has been make in XFR.Control building 2nd floor column work is going on.Structure work has been done for gantry tower, beam switchyard. 27.04.2017 -Control building 2nd floor column work has been completed & slab shuttering work is going on.Conservator, radiator accembelling work is continuing in power XFR. Tower beam structure work has been done at switchyard. 04.05.2017 -Guide wall work has been completed for XFR-1. Shuttering work is going on at 2nd floor in control building. 11.05.2017 -First floor roof RCC casting work has been completed. Stair roof also RCC casting has been done.Sand filling work done in side the control building ground floor room.Brick wall work is going on. 18.05.2017 -RCC cast work has been done in ground floor.Brick work is continuing. 25.05.2017 13 Nos 11kv AIS breaker installed at channel. Ground floor cast has done.Road crossing work is going on. 01.06.2017 Road casting work is going on.Brick wall work is continuing.33kV control panel is placement has been completed. 08.06.2017 Control panel wiring is going on. 15.06.2017 33kV control panel wiring is continuing.Brick wall & plaster work is continuing of new building. 22.06.2017 -33kV control panel wiring work is going on.Brick wall & plaster work has been completed. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -33 kV GIS & 33 kV control Panel wiring is going on. 13.07.2017 Ground floor and 1st floor plaster completed.Outside building plaster running.Floor tiles work running.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Sep 13' 16 | Declaration of completion
7 | Gazaria S/S | BREB | Gazaria S/S Client - BREB | 7 | Gazaria | Shafiq Ahmed 01713147024 Site Engr Golam Morshed-01787687953 |  |  |  | - | - | Deed Agreement | Gazaria Project Manager Shafiq Ahmed 01713147024 Site Engr Golam Morshed-01787687953 | 23.10.2016 -Pre commissioning test report submitted to REB. 27.10.2016 -Waiting for Commissioning date by REB. 03.11.2016 10.11.2016 -No update. 17.11.2016 -Commissioning date will be 21 Nov,2016. 24.11.2016 -Commissioning done at 21 Nov,2016. 01.12.2016 to 09.02.2017 -No further update. 16.02.2017 -No further update. 23.02.2017 -No further update. 02.03.2017 -No further update. 09.03.2017 -02 Nos of DS replacing work has been done. 16.03.2017 -Kilowatt meter installed. -6 Nos feeder is running. 23.03.2017 to 27.04.2017 -No further update. 04.05.2017 -Close out has been completed. 11.05.2017 -No further update. 18.05.2017 -Graveling work is continuing. 25.05.2017 -Graveling work has been completed. 01.06.2017 Commissioning has been completed at 30 May,2017. 08.06.2017 to 13.07.2017 -No further update. | 20.07.2017 -No further update.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Aug 30' 16 | Declaration of completion
8 | Bay Extension at Jangalia | BREB | Bay Extension at Jangalia Client - BREB | 8 | Comilla (South) Jangalia | Shafiq Ahmed 01713147024 Site Eng. Belal- 01680850676 | Shafiq Ahmed |  | 1713147024 | - | - | Deed Agreement | Comilla (South) Jangalia Project Manager Shafiq Ahmed 01713147024 Site Eng. Belal- 01680850676 | 16.10.2016 -Ground floor & 1st floor brick work completed & 2nd floor brick works completed upto 50%. Cable trench completed near about 80%. 23.10.2016 -Brick work of control room completed. 27.10.2016 -Finishing work running. 03.11.2016 Inside plaster work completed. Equipment installation going on. 10.11.2016 -Building finishing work going on. 17.11.2016 -Civil works 80% done. -Installation work 60% done. 24.11.2016 -Civil works going on. -Installation work running. 01.12.2016 -Control room Grill fixing on the windows are complete.Gantry finishing work running.cable trench finishing work 60% complete -boundary wall complete but 1 column (& 1 section).soak well works running.tiles fittings going on .parapet 70% complete. 08.12.2016 -Boring work for earthing is going on.Indoor breaker materials arrived at site. 15.12.2016 -Plaster work is going on in Control building Out side wall.Soil digging has been done for foundation wall.LA has bee Installed. 22.12.2016 -Digging work is running for surface drain.Plaster & tiles work of control building is going on.Power cables reached at site. 29.12.2016 -Mesh earthing work has been continued. -Base casting has worked in Fancy boundary. -Control building out side plaster is going on. 05.01.2017 -CC work has been done for Surface drain, Soak coil / septic tank.Brick work for guard room wall has completed. 12.01.2017 -Trench work is running in 2nd floor of control building. -Bas bar setting ,fittings work has completed.01 Nos of VCB set ,33kv relay panel outgoing has shifted to Chittagong PBS by order of System operation (KE O) office,REB ,Dhaka. 19.01.2017 -Control room paint work has been done.Control cable works is going on.Surface Drain, fencing,guide wall, stair railing , & side dressing levelling works is going on. 26.01.2017 -Surface drain work is going on.Finishing work has been completed in Guard room. 02.02.2017 -Window Thai glass materials has arrived at site.-Facing bricks work is going on.Paint work is going on in boundary wall, control room. 09.02.2017 -Patent stone CC work has completed in control building roof top.Facing brick wall work is going on. 16.02.2017 -Facing brick wall work is going on.Main entrance road making work is going on. 23.02.2017 -False ceiling work has been done in control room.Brick soling work is going on. 02.03.2017 -30% road casting work has been done. 09.03.2017 -100% road casting work has been done.Paint work is going on (final part).Finishing works is going on for Tiles. 16.03.2017 -Switchyard soling finished. -Surface drain done,building paint & tile,plumbing, electrical work is going on. 23.03.2017 -Paint and fencing work has been finished. 30.03.2017 -Brick soling work is going on for S/Y.Electrical work is going on in control building. 06.04.2017 -Preparation work has been done for Commissioning,Approx. Commissioning date will be 10 april,2017. 04.05.2017 -All civil works has been completed.(Gravel work yet to be done). 13.04.2017 -Commissioning done at 10 april,2017. 20.04.2017 to 25.05.2017 -No further update. 01.06.2017 File submitted to Comilla REB office for close out at 01 June,2017. 08.06.2017 -Close out has been completed at 08 June,2017. 15.06.2017 -As built drawing work is going on. 22.06.2017 -No further update. 29.06.2017 -As built drawing Submitted at Comilla REB office at 23 june,2017. -No further update. 06.07.2017 -Remaining bill submitted at comilla BREB office. 13.07.2017 -Same as before. | 20.07.2017 -No further update.
[7 empty] | Site Eng. Belal- |  | 1680850676 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Jun 15' 16 | Declaration of completion
9 | Feni Switching station | BREB | Feni Switching station Client - BREB | 9 | Feni | Shafiq Ahmed 01713147024 | Shafiq Ahmed |  | 1713147024 | - | - | Deed Agreement | Feni Project Manager Shafiq Ahmed 01713147024 | 16.10.2016 -Control-protection wiring will be completed within next 2 days 23.10.2016 27.10.2016 -control protection wiring completed. 03.11.2016 -Pre commissioning test can be started within 2/3 days. 10.11.2016 -Pre-commissioning will be done by 15Nov,2016. 17.11.2016 -Pre commissioning date will be 22 Nov 2016. 24.11.2016 -Pre-Commissioning going on. 01.12.2016 -Pre-Commissioning done. 1 Incoming & 1 out-going internal connection incomplete,Bus-section DS not connected yet.Incoming overhead cable not installed yet. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 -No further update. 29.12.2016 -Requirements (3 Nos of pole with fittings) paper submitted to REB office,now file in PBS-2,Comilla. 05.01.2017 -Processing going on for Requirements (3 Nos of pole with fittings) paper submitted to REB office,now file in PBS-2,Comilla. 12.01.2017 -06 Nos of poles has been erected for bus to bus inter connection. 19.01.2017 -Preparation work done for 02 Nos Isolator installation. 26.01.2017 -2set new DS installation and 33kV bus change for interconnection, now bus to bus interconnection work is running. 02.02.2017 -33kV bus to bus inter connection work has been completed. 09.02.2017 -Pre parathion work has done for Shut down. 16.02.2017 -Jumpering work has been done for inter connection & LA , DS to LA & PI connection work done for underground feeder. 23.02.2017 -Apply for Commissioning at EX.EN, REB,Comilla. 02.03.2017 -Processing work is going on for Commissioning. 09.03.2017 -As same as before. 16.03.2017 -Processing work is going on for Commissioning. 23.03.2017 -Same as before. 30.03.2017 -Same as before. 06.04.2017 -Preparation work has been done for Commissioning, -Approx. Commissioning date will be 10 april,2017. ------------------ Commissioning done at 10 april,2017. 27.04.2017 to 18.05.2017 -No further update. 25.05.2017 -08 Nos Gas Cylinder has been installed.04 Nos halogen Light fitting work has done. 01-06.2017 Internal electrical connection work has been done between Breaker isolator-CT-PT. 08.06.2016 Panel test work has been completed. 15.06.2017 -No further update. 22.06.2017 -Pre commissioning work has been completed.Report has summited to REB office.Apply for get the Commissioning date. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 13.07.2017 -No further update. -No further update.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Dec 4' 16 | Declaration of completion
10 | 3 S/S (Shitalakhya, Kamrangirchor & Dhanmondi) | DPDC | 3 S/S (Shitalakhya, Kamrangirchor & Dhanmondi) Client - DPDC | 10.1 | Shitalakhya | Rabiul Alam , Mustafizur Rahman Mithu 01713147029 Site Engr --NAJMUL-01723598014 Kawser- 01676099541 | Rabiul Alam |  |  | - | - | Deed Agreement | Shitalakhya Project Manager Rabiul Alam , Mustafizur Rahman Mithu 01713147029 Site Engr --NAJMUL-01723598014 Kawser- 01676099541 | 23.10.2016 -Boundary wall & store room building 40% completed. -New control room 60% completed. 27.10.2016 -Building brick works going on. 03.11.2016 -Brick work completed. Cable trench & finishing work going on. 10.11.2016 -Building finishing work going on. 17.11.2016 -Civil works 70% done. 24.11.2016 -Civil works going on. 01.12.2016 -Building finishing work going on. 08.12.2016 -Building finishing work continuing. 15.12.2016 -Brick work is continuing. 22.12.2016 -Building finishing work is going on.Tiles work has been continued. 29.12.2016 -Building finishing work is going on. 05.01.2017 -Building finishing work is continuing. 12.01.2017 -Out door fencing brick work is running for control building. 19.01.2017 -Out door fencing brick work & others finishing work is running for control building. 26.01.2017 Fencing brick works continues.False ceiling work going on. 02.02.2017 -Already took shut down for materials shifting to other place like Breaker,XFR etc. 09.02.2017 -Store room building broken work has been completed. -False ceiling work has been done. 16.02.2017 -New road making work approx. 50 % has been done.Earth excavation work run for foundation of Circuit breaker. 23.02.2017 -New road making work approx. 70 % has been done.Earth excavation work run aprox.90% for foundation of Circuit breaker. 02.03.2017 -Cable trench work is going on. 09.03.2017 -Road works is going on. 16.03.2017 -Same as before. 23.03.2017 -Road construction and Electrical work is going on. 30.03.2017 -Electrical equipment errection work has been done for 33kV AIS. 06.04.2017 -Electrical work is going on. 13.04.2017 -Civil works has been completed. Control wiring work is going on. 27.04.2017 -Control protection wiring is going on. 04.05.2017 -Control protection wiring work has been completed .Earthing work also completed. 11.05.2017 -Preparation work for shutdown. 18.05.2017 to 13.07.2017 -No further update. | 20.07.2017 -No further update.
[7 empty] | Mustafizur Rahman Mithu |  | 1713147029 | - | - | Contract Date
[7 empty] | Site Engr --NAJMUL- |  | 1723598014 | - | - | Commencement Work
[7 empty] | Kawser- |  | 1676099541 | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Sep 30' 16 | Declaration of completion
10 | 3 S/S (Shitalakhya, Kamrangirchor & Dhanmondi) | DPDC | 3 S/S (Shitalakhya, Kamrangirchor & Dhanmondi) Client - DPDC | 10.2 | Kamran girchar | Rabiul Alam , Mustafizur Rahman Mithu 01713147029 Site Engr -NAJMUL-01723598014 | Rabiul Alam |  | 1713147029 | - | - | Deed Agreement | Kamran girchar Project Manager Rabiul Alam , Mustafizur Rahman Mithu 01713147029 Site Engr -NAJMUL-01723598014 | 23.10.2016 -No further update 30.10.2016 CT mounted on base, XFR to panel wiring done,132 kV DS measurement taken but not yet reached at site.Gantry tower installation done completely. 03.11.2016 Bus & wire hanging in tower(06pcs) is done. Old wall breaking for control panel board is going on. LA replacing to the other side, so making 03 new bases. 10.11.2016 DS setting on the structure. Cable wiring MK box to CT & circuit breaker is done. LA base reprocess(running) 17.11.2016 -LA structure,LA setting done.PI structure done. -Cable laying done from XFR MK box to main panel board. 24.11.2016 -132 kV control panel wiring. -Uper bus to DS wiring connection.Lower bus to DS wiring connection.Circuit breaker to upper bus wire connection.33kV LA & PI structure setting. 01.12.2016 -XFR breaker panel board installed. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 -Power cable is laying from XFR to panel board. -PI has been installed. -Earthing work is done for all panel. 29.12.2016 -Power cable, CT & Circuit breaker test has been completed. -Control panel board testing running. 05.01.2017 -XFR all types of test has completed.Relay test is going on. 12.01.2017 -All Relay test has done. 19.01.2017 -Paint work has been done for old Transformer.01.20 26.01.2017 -Paint work has been done for new XFR.180 m internal road has been make. 02.02.2017 -Drain work is going on beside the road. 09.02.2017 -Casting work is going on in XFR yard. 16.02.2017 -Base casting work has been done in switchyard. -02 Nos bus bar is running. -Drain work is going on the side of road. 23.02.2017 -No further update. 02.03.2017 -Gravel laid at switchyard. 09.03.2017 -No further update. 16.03.2017 -Gravel laid at switchyard. -XFR is Starting. 23.03.2017 -All work has been finished. 30.03.2017 -No further update. 06.04.2017 -GT is running. -Waiting for the Busbar protection work.(done by SIMENS). 50/75 MVA power XFR energized without bus bar protection work.(will be done by SIEMENS) 27.04.2017 to 06.07.2017 -No further update. | 20.07.2017 -No further update.
[7 empty] | Mustafizur Rahman Mithu |  | 1723598014 | - | - | Contract Date
[7 empty] | Site Engr -NAJMUL- |  |  | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Sep 30' 16 | Declaration of completion
10 | 3 S/S (Shitalakhya, Kamrangirchor & Dhanmondi) | DPDC | 3 S/S (Shitalakhya, Kamrangirchor & Dhanmondi) Client - DPDC | 10.3 | Dhanmondi | Rabiul Alam , Mustafizur Rahman Mithu 01713147029 Site Engr-NAJMUL-01723598014 Shohidul-01714674231 | Rabiul Alam |  |  | - | - | Deed Agreement | Dhanmondi Project Manager Rabiul Alam , Mustafizur Rahman Mithu 01713147029 Site Engr-NAJMUL-01723598014 Shohidul-01714674231 | 27.10.2016 -2 nos of towers & beams,CTs ,Breakers are installed with drive box. 03.11.2016 -C.T,Beaker, Transformer, Outdoor M.K box,132kV control panel wiring are completed .33 kV panels are installed (wiring not completed). 10.11.2016 -2 Set DS of Bus coupler are installed.33kV control panels are installed. Base for 7Nos of panel at first floor are completed. Cable trench for control cable at 1st floor completed. Ground floor mosaic.Gravel supporter grill are installed. 17.11.2016 -33kV Breakers are installed. -PI and LA structures are installed.Wiring running of 33kV Bus coupler breaker and control panel .Earth excavation for outdoor cable trench going on. 24.11.2016 -33kv breaker wearing are complete. -33kv controll panel wearing are complete (without AC distribution panel). -33kv LA are installed. 01.12.2016 -XFR ratio, winding resistance, insulation resistance,magnetic balance,HT-LT excitation, oil BDV, 33kV breaker meggar etc test completed. 08.12.2016 -132 kV CT testing has been done.33 kV CT & PT testing completed. 15.12.2016 -33kV control panel relay tasting completed.33kV PI are installed33kV power cable laying. 22.12.2016 -No further update. 29.12.2016 -No further update. 05.01.2017 -Short loop wiring has done from XFR to LA to CT to Breaker then DS. 12 Nos Power cable Termination has completed. 12.01.2017 -No up date. 19.01.2017 -Power cable termination completed.33 kV siid short loop installed. 26.01.2017 -No further update. 02.02.2017 -No further update. 09.02.2017 -No further update. 16.02.2017 -Pre-commissioning work is running.Final preparation going on for Shut down preparation. 23.02.2017 Pre-commissioning completed Upper bus feting completed. 02.03.2017 -02 Nos Isolator connector repaired. 09.03.2017 -No further update. 16.03.2017 -Gravel laid at XFR. - Shutdown preparing work is going on. 23.03.2017 -All work has finished. 30.03.2017 -No further update, 06.04.2017 -GT is running. -Waiting for the Busbar protection work.(done by SIMENS). 50/75 MVA power XFR energized without bus bar protection work.(will be done by SIEMENS) 27.04.2017 to 06.07.2017 -No further update. | 20.07.2017 -No further update.
[7 empty] | Mustafizur Rahman Mithu |  | 1713147029 | - | - | Contract Date
[7 empty] | Site Engr-NAJMUL- |  | 1723598014 | - | - | Commencement Work
[7 empty] | Shohidul- |  | 1714674231 | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Sep 30' 16 | Declaration of completion
11 | 33 kV Switching stn at ULON | DPDC | 33 kV Switching stn at ULON Client - DPDC | 11 | ULON | Rabiul Alam , Mustafizur Rahman Mithu 01713147029 Site Engr. Khorshed 01717434647 | Rabiul Alam |  |  | - | - | Deed Agreement | ULON Project Manager Rabiul Alam , Mustafizur Rahman Mithu 01713147029 Site Engr. Khorshed 01717434647 | 23.10.2016 -No further update. 30.10.2016 -Power XFR on base , yet to be erected. 03.11.2016 -No further update. 10.11.2016 -Regulator installation complete in power XFR. 17.11.2016 -GT (04) 50/75 MVA Transformer installation going on. 24.11.2016 -GT (04) 50/75 MVA Transformer installed. 01.12.2016 -New XFR (04) 50/75 MVA electrical wiring going on.GT-3 XFR AIS 33kV breaker with housing panel dismantling going on. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 -Cable wring is going on in GIS & CRP. 29.12.2016 -Electrical test work is going on for CRP. -132kV power Cable plug in work has done by Chinese engineer. 05.01.2017 -132kV power Cable termination work is going on by Chinese engineer. 12.01.2017 -No further update. 19.01.2017 XFR 50/75 MVA GT-04 electrical testing has been done.33 kV control relay panel setting work is going on. 26.01.2017 -Paint work has completed of new XFR 50/75 MVA GT-04. -33 kV control relay panel electrical wiring is going on. 02.02.2017 -33 kV control relay panel electrical wiring is going on. 09.02.2017 -No further update. 16.02.2017 -No further update. 23.02.2017 -33kv SAS panel electrical wiring work going on. 02.03.2017 to 30.03.2017 -No further update. 06.04.2017 -132kV Power cable High voltage test has been completed. Awaiting for commissioning. 27.04.2017 to 06.07.2017 -No further update. | 20.07.2017 -No further update.
[7 empty] | Mustafizur Rahman Mithu |  | 1713147029 | - | - | Contract Date
[7 empty] | Site Engr. Khorshed |  | 1717434647 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Sep 30' 16 | Declaration of completion
12 | 33 kV GIS installation at Dhanmondi Grid S/S | DPDC | 33 kV GIS installation at Dhanmondi Grid S/S | 12 | Dhanmondi | Mustafizur Rahman Mithu 01713147029 Site Engr. Shohidul-01714674231 | Mustafizur Rahman Mithu |  | 1713147029 | - | - | Deed Agreement | Dhanmondi Project Manager Mustafizur Rahman Mithu 01713147029 Site Engr. Shohidul-01714674231 | 23.10.2016 No further update. 30.10.2016 -Outdoor cable trench done 10%,CRP yet not placed.GT-2 XFR 33kV cable laying started. 03.11.2016 -Outdoor Earth work done 60%.GIS Chanel work running. 10.11.2016 -Channel installing in GIS panel.Base concrete 20 m done. 17.11.2016 -Cable trench 20m done. Panel work running in 1st floor.GIS panel not yet come. 24.11.2016 -Cable trench done 22 meter’s. 01.12.2016 -Cable trench done 25 meter’s.plumbing work going on. 08.12.2016 -GIS panel setting on base. -Control cable laying from GIS to control panel.Slab cover making done approx. 30 pcs. Casting work have been done for cable trench of approx. 20 ft. 15.12.2016 -GIS panel installation & Wiring for GIS has completed.Wiring for AC and DC supply is running. Cable trench for power cable is about to finish. Surface drain (out side the building) is running .Painting work is running Thai aluminum work for doors and windows is running. 22.12.2016 -Wiring for AC & DC supply is completed. -GIS wiring is running.ACDB & DCDB wiring is completed.-CRP & GIS earthing going on.-Battery solution processing running.-Cable hanger in cable trench is running.Cable trench for power cable is completed. -Surface drain (out side the building) is pending.Thai aluminum work for doors and windows is running. 29.12.2016 -GIS wiring is running. -Cable Port Fitting in GIS is completed.CRP & GIS earthing is completed. Battery solution processing is completed.Cable hanger in cable trench is completed. -Civil Work Surface drain (out side the building) is running.Thai aluminum work for doors and windows is completed. 05.01.2017 -GIS wiring has done.Approx. 17 Nos of earth joint has done by cad weld powder.SF6 gas refueling work has done in GIS.Surface drain work has done in out side of control building area.Power cable is laying for GT-1 XFR. 12.01.2017 -SAS Panel wiring is running. -Gas leakage in GIS(Incoming 2 & Bus 3) is located & repaired.Power Cable (3×3)=9 for XFR-2(GT-1) pulling is Completed.Power Cable (3×3)=9 for XFR-2(GT-3) pulling is completed. 19.01.2017 SAS Panel wiring is completed.Gas leakage in GIS (Incoming 2 & Bus 3) is Vacuumed .Testing of CRP panel is running.CT analyzing of GIS is running. 26.01.2017 -Gas filling in GIS is completed.Contact Resistance test is completed.CT analyzing of GIS is completed.Power Cable Connecting process of GT-1 is running. 02.02.2017 -GT -1 (XFR-1, 33kV GIS) has been completed & running properly. -Outgoing -3(H-05) Kakrail feeder cable join has completed.Outgoing -3(H-05) (Kakrail) has been completed & running properly.Earth excavation for XFR feeder has been completed.Wall dismantled for exhaust fan at seven place’s has been done. 09.02.2017 -GT-2 (XFR -1,33kV GIS) has completed & given clearance for energize. -TR-2 XFR cable laying is running.Chigger plate work of ist floor & ground floor is running.Earth excavation for XFR feeder has completed.Flower garden work at north & west side,Florecent 7 LED bulb work,Ceiling fan,Name plate setup at out side work has been completed. 16.02.2017 -Power cable laying work is going on.Out side new flower bed making has been done. 23.02.2017 -Preparation work is running for GT-3,Bashundhara outgoing feeder.Cable laying & connection to Auxiliary XFR is site building is running, 02.03.2017 -GT-3 is completed & running properly.Bashundhara outgoing feeder is completed & running properly.Both Auxiliary XFR is completed &running.Auxiliary connection to PGCB is completed.Gas filling id Taltala-1 (previously named Taltala-2)is completed which had leakage problem. -Land scraping, Apron work,Sand filling in outside cable trench is going on. 09.03.2017 -Outgoing feeder transfer to another spare outgoing feeder panel for Gas leakage solution. 25.05.2017 -No further update. -Security light (ip65) is installed on the building outside. -SAS panel wiring is running due to EEL new wiring diagram. -Flower bed guide wall plastering & finishing is complete. -Paint work is going on. -New gate make for auxiliary XFR. 16.03.2017 -Flower Bed at front side and right of GIS building is complete. -Switch Yard Brick flat soling and mortaring complete -Inside Paint work complete and Out side paint Work is running. -Water outlet pit for cable trans is complete. -Cable trans repairing work is about to finish.Excess soil removing from switch yard is under processing. 23.03.2017 -Repairing work for cementing. 30.03.2017 Maintenance work is running for GIS & SAS panel. 06.04.2017 -Same as before. Commissioning has been done at 28 February,2017 27.04.2017 to 06.07.2017 -No further update. | 20.07.2017 -No further update.
[7 empty] | Site Engr. Shohidul- |  | 1714674231 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Sep 30' 16 | Declaration of completion
13 | Supply,Installation,Testing & Commissioning of 33/11 kV, 1x20/28 MVA,Transformer,33 kV GIS,11 kV AIS with associated materials at Tejgaon | DPDC | Supply,Installation,Testing & Commissioning of 33/11 kV, 1x20/28 MVA,Transformer,33 kV GIS,11 kV AIS with associated materials at Tejgaon Client - DPDC | 13 | Mogbajar -Tejgaon | Mustafizur Rahman Mithu 01713147029 AE,Mehedi 01553504429 Sprvsr,lokman 01743604719 | Mustafizur Rahman Mithu |  | 1713147029 | - | - | Deed Agreement | Mogbajar -Tejgaon Project Manager Mustafizur Rahman Mithu 01713147029 AE,Mehedi 01553504429 Sprvsr,lokman 01743604719 | XFR LAY OUT WORK HAS BEEN DONE. WORK START AT 27,May,2017 21.06.2017 -50% work has been completed at XFR base foundation. -All documents approved by DPDC,(Civil wroks,33kV CRP,XFR GTP etc). 21.06.2017 -50% work has been completed at XFR base foundation.All documents approved by DPDC,(Civil wroks,33kV CRP,XFR GTP etc). 22.06.2017 -50% work has been completed at XFR base foundation.All documents approved by DPDC,(Civil wroks,33kV CRP,XFR GTP etc). 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -All equipment's shuttering work has been completed. 13.07.2017 -Casting of XFR foundation has been completed.Dismantle of column top for vertical extension of one floor all most complete.
[7 empty] | AE,Mehedi |  | 1553504429 | - | - | Contract Date
[7 empty] | Sprvsr,lokman |  | 1743604719 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Sep 30' 16 | Declaration of completion
14 | 4- S/S (Baridhara, Mirpur BIHS, Mohakhali, United Tower & Dhamalkot) | DESCO | 4- S/S (Baridhara, Mirpur BIHS, Mohakhali, United Tower & Dhamalkot) Client - DESCO | 14.1 | Mirpur BIHS |  |  |  |  | - | - | Deed Agreement | Mirpur BIHS Project Manager | 18.10.2016 -Already commissioned. 23.10.2016 to 10.11.2016 -No further update 17.11.2016 -Automation system not yet come in site. 24.11.2016 -Solar system implementation work going on. 01.12.2016 to 09.02.2017 -No further update. 16.02.2017 -SAS panel arrived in site. 23.02.2017 -Automation panel fitting work has been done. 02.03.2017 -Gravelling at site. 09.03.2017 -No further update. 16.03.2017 -Panels for SAS (PAS) are erected and will be commissioned soon. 23.03.2017 -Cabling going on in Pas panel. 30.03.2017 -Wiring work is going on from Panel to panel for Automation. 06.04.2017 -PAS panel and Box Panel wiring has been done. 13.04.2017 to 27.04.2017 -No further update. 04.05.2017 Panel wiring is going on for automation. 11.05.2017 18.05.2017 No further update. 25.05.2017 Mechanical work is going on. 01.06.2017 -06 Nos Fire extinguisher installation has been completed. 01.06.2017 06 Nos Fire extinguisher installation has been completed. 08.06.2017 -Repair works is going on. 15.06.2017 to 13.07.2017 -No further update. | 20.07.2017 -No further update.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Oct 31' 16 | Declaration of completion
14 | 4- S/S (Baridhara, Mirpur BIHS, Mohakhali, United Tower & Dhamalkot) | DESCO | 4- S/S (Baridhara, Mirpur BIHS, Mohakhali, United Tower & Dhamalkot) Client - DESCO | 14.2 | United Tower | Jane Alam Talukder 01777795201 | Jane Alam Talukder |  | 1777795201 | - | - | Deed Agreement | United Tower Project Manager Jane Alam Talukder 01777795201 | 18.10.2016 -Already commissioned. 23.10.2016 27.10.2016 03.11.2016 10.11.2016 -No further update 17.11.2016 -Automation system not yet come in site. 24.11.2016 -Solar system implementation work going on. 01.12.2016 -No further update. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 to 09.02.2017 -No further update. 16.02.2017 -SAS panel arrived in site. 23.02.2017 -Automation panel fitting work has been done. 02.03.2017 -Gravelling at site. 09.03.2017 -No further update. 16.03.2017 -Panels for SAS (PAS) are erected and will be commissioned soon. 23.03.2017 -Cabling going on in Pas panel. 30.03.2017 -Wiring work is going on from Panel to panel for Automation. 06.04.2017 -PAS panel and Box Panel wiring has been done. 13.04.2017 to 27.04.2017 -No further update. 04.05.2017 -Panel wiring is going on for automation. 11.05.2017 to 01.06.2017 -No further update. 08.06.2017 -Cleaning 11kV & 33kV panels.11kV PT testing work has ben done. 15.06.2017 Cleaning works has been completed for XFR’s, Battery room, AC/DC panels , charger. 22.06.2017 -No further update,Eid festival holidays, so No further update. 06.07.2017 13.06.2017 -No further update. | 20.07.2017 -No further update.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Oct 31' 16 | Declaration of completion
14 | 4- S/S (Baridhara, Mirpur BIHS, Mohakhali, United Tower & Dhamalkot) | DESCO | 4- S/S (Baridhara, Mirpur BIHS, Mohakhali, United Tower & Dhamalkot) Client - DESCO | 14.3 | Dhamalkot | Jane Alam Talukder 01777795201 | Jane Alam Talukder |  | 1777795201 | - | - | Deed Agreement | Dhamalkot Project Manager Jane Alam Talukder 01777795201 | 23.10.2016 -No further update. 27.10.2016 -Installation complete. -Testing work going on. 03.11.2016 -33kV Have no source. 10.11.2016 -Discharge of battery,DC high pot test, AC high pot test, Relay test,And Insulation resistance test done. 17.11.2016 IR Test of CT and PT of 11kV Panels, Relay test, Dressing of control cables done. 24.11.2016 -No update. 01.12.2016 -No further update. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 -No further update. 29.12.2016 -Re fueling in new XFR. 05.01.2017 -Test work done for relay. 12.01.2017 -No further update. 19.01.2017 -XFR oil centrifuging going on.XFR testing & wiring has been done. 26.01.2017 -No further update. 02.02.2017 Commissioning has been done. 23.02.2017 -Automation panel fitting work has been done. 02.03.2017 -Current injection work has done of outgoing feeders. 09.03.2017 to 30.03.2017 -No further update. 06.04.2017 -PAS panel fitting work has been done. 13.04.2017 -Panel to panel wiring is going on for automation. 20.04.2017 -Pas panel wiring is going on for automation. 27.04.2017 -Ethernet switch installation work is going on for automation. 04.05.2017 -Ethernet switch wiring is going on.Automation cable dressing work is continuing. 11.05.2017 -Earthing work is going on of box panels & PAS panels for automation.Cable dressing work also going on. 18.05.2017 -Substation cleaning and maintenance. 25.05.2017 -Excavation work is going on. 01.06.2017 XFR foundation CC cast work has been done.Soil excavation work is going on.Rod binding work has been completed. 08.06.2017 XFR foundation CC cast work has been done.Soil excavation work is going on.Rod binding work has been completed. 15.06.2017 Base CC casting has been completed for XFR foundation. Base CC casting work is going on for Fire wall foundation. 22.06.2017 -Base CC casting has been done for XFR.-02 lift CC casting work is going on for Fire wall foundation. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -Fire wall shuttering and casting work has been done. 13.07.2017 -Casting of fire wall, Excavation work of EM tower foundation.18.10.2016 Power cable wiring for 11kV completed.Power cable wiring for 33kV paused due to structure issue.CRP almost over
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Oct 31' 16
14 | 4- S/S (Baridhara, Mirpur BIHS, Mohakhali, United Tower & Dhamalkot) | DESCO | 4- S/S (Baridhara, Mirpur BIHS, Mohakhali, United Tower & Dhamalkot) Client - DESCO | 14.4 | Mohakhali | Jane Alam Talukder 01777795201 Site Engr. Hamid-01937109167 (UZZAL) | Jane Alam Talukder |  | 1777795201 | - | - | Deed Agreement | Mohakhali Project Manager Jane Alam Talukder 01777795201 Site Engr. Hamid-01937109167 (UZZAL) | 18.10.2016 -Equipments GTP & GA not submitted yet. -Civil and Electrical drawings submitted, but not approved yet. 23.10.2016 -No further update. 27.10.2016 -transformer not yet ready. 03.11.2016 -Didn’t get civil order. 10.11.2016 08.12.2016 -Transformer manufacturing under process. 15.12.2016 to 19.01.2017 -No further update. 26.01.2017 -XFR to be released from factory by 31.01.2017. 02.02.2017 -XFR reached in Mohakhali site. 09.02.2017 to 30.03.2017 -No further update. 06.04.2017 -Preparation work has been done for pile. 13.04.2017 -No further update. 20.04.2017 -Boring work for pile is going on. 27.04.2017 -Pile casting work is continuing. 04.05.2017 -No further update. (Total 04 Nos pile has been completed). 11.05.2017 -No further update. 18.05.2017 -Soil excavation for XFR foundation work. 25.05.2017 -Repairing work has been completed. 01.06.2017 to 13.07.2017 -No further update.
[7 empty] | Site Engr. Hamid- |  | 1937109167 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Oct 31' 16 | Declaration of completion
15 | Supply,Installation,Testing & Commissioning of 03 Nos 33/11 Kv Substation (Each 10/14 MVA, TURN-KEY) | PBS | Supply,Installation,Testing & Commissioning of 03 Nos 33/11 Kv Substation (Each 10/14 MVA, TURN-KEY) Client - PBS | 15.1 | TARONIBARI under Nilphamari PBS | TARONIBARI Jane Alam Talukder 01777795201 Excu.Sohelrana-01709650215 | TARONIBARI |  |  | - | - | Deed Agreement | TARONIBARI under Nilphamari PBS Project Manager TARONIBARI Jane Alam Talukder 01777795201 Excu.Sohelrana-01709650215 | project start or agreement date-06.02.2017 30.05.2017 SOIL FILLING COMPLETED 100%. 01.06.2017 -Soil Filling Has Been Competed. 08.06.2017 to 22.06.2017 -No further update. -Already get the Sub contractor, deed has been completed. -Land filling has completed. -Design, drawing has completed. 29.06.2017 13.07.2017 -No further update.
[7 empty] | Jane Alam Talukder |  | 1777795201 | - | - | Contract Date
[7 empty] | Excu.Sohelrana- |  | 1709650215 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - |  | Declaration of completion
15 | Supply,Installation,Testing & Commissioning of 03 Nos 33/11 Kv Substation (Each 10/14 MVA, TURN-KEY) | PBS | Supply,Installation,Testing & Commissioning of 03 Nos 33/11 Kv Substation (Each 10/14 MVA, TURN-KEY) Client - PBS | 15.2 | BODA under Thakurgaon PBS | Jane Alam Talukder 01777795201 Excu.Sohelrana-01709650215 | Jane Alam Talukder |  | 1777795201 | - | - | Deed Agreement | BODA under Thakurgaon PBS Project Manager Jane Alam Talukder 01777795201 Excu.Sohelrana-01709650215 | project start or agreement date-06.02.2017 30.05.2017 SOIL FILLING COMPLETED 100%. 01.06.2017 -Soil Filling Has Been Competed. 08.06.2017 to 22.06.2017 -No further update. -Already get the Sub contractor, deed has been completed. -Land filling has completed. -Design, drawing has completed. 29.06.2017 13.07.2017 -No further update.
[7 empty] | Excu.Sohelrana- |  | 1709650215 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - |  | Declaration of completion
15 | Supply,Installation,Testing & Commissioning of 03 Nos 33/11 Kv Substation (Each 10/14 MVA, TURN-KEY) | PBS | Supply,Installation,Testing & Commissioning of 03 Nos 33/11 Kv Substation (Each 10/14 MVA, TURN-KEY) Client - PBS | 15.3 | HORIPUR under Thakurgaon PBS | Jane Alam Talukder 01777795201 Excu.Sohelrana-01709650215 | Jane Alam Talukder |  | 1777795201 | - | - | Deed Agreement | HORIPUR under Thakurgaon PBS Project Manager Jane Alam Talukder 01777795201 Excu.Sohelrana-01709650215 | project start or agreement date-06.02.2017 30.05.2017 SOIL FILLING COMPLETED 100%. 01.06.2017 -Soil Filling Has Been Competed. 08.06.2017 to 22.06.2017 -No further update.Already get the Sub contractor, deed has been completed.Land filling has completed.Design, drawing has completed. 29.06.2017 13.07.2017 -No further update.
[7 empty] | Excu.Sohelrana- |  | 1709650215 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - |  | Declaration of completion
16 | Rahim Steel | Rahim Steel | Rahim Steel | 16.1 | Kachpur, N'Ganj | Abdul Hakim 01711955543 Site Engr Mr Rakib-01716275374 | Abdul Hakim |  | 1711955543 | - | - | Deed Agreement | Kachpur, N'Ganj Project Manager Abdul Hakim 01711955543 Site Engr Mr Rakib-01716275374 | 18.10.2016 -Piling cap broken. 23.10.2016 -No further update. 27.10.2016 -Civil works running. 03.11.2016 -Civil works 80% done. 10.11.2016 -Column & Base casting complete of ACR(automatic circuit reclozer) -Sand filling going on. -Site boundary wall work done. 17.11.2016 -Civil works 80% done. 24.11.2016 -Fancy boundary work going on.Civil works: Sand filling & guide wall done. 01.12.2016 -Fancy boundary work done. -XFR,CT,PT,DS, Isolator of 11 & 33 kV materials for Tower & beam arrived in site. 08.12.2016 -Beam and Tower making work have been done. 15.12.2016 -33 kV & 11kV CT,PT & LA erection has been done. 22.12.2016 -Casting work for road has been completed.Brick soling work has been completed. -XFR (5/7.0) assembling has done.Bus bar for 11 kV has installation has been done. 29.12.2016 -Internal connection, wiring, metering & jumpering work has been done for CT,PT. -HT & LT connection has been done for power transformer. 05.01.2017 -33kV source line hookup works has done. -33 kV ACR & Isolator jumpering work has done. 12.01.2017 -Site has been handed over to WZPDCL. 19.01.2017 -No further update. 26.01.2017 -No further update. Problem :-ACR,In 11kV metering system.Battery back up System fault. 02.02.2017 to 13.07.2017 -No further update.
[7 empty] | Site Engr Mr Rakib- |  | 1716275374 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
16 | City Group | - | City Group Client - - | 16.2 | City Group Gondhobpur Rupshi | Abdul Hakim 01711955543 Site Engr Mr Rakib-01716275376 | Abdul Hakim |  | 1711955543 | - | - | Deed Agreement | City Group Gondhobpur Rupshi Project Manager Abdul Hakim 01711955543 Site Engr Mr Rakib-01716275376 | 23.10.2016 Bashundhara Group already starts the civil work.After completion of the boundary wall we will start our other works. 27.10.2016 Basundhora Group already starts the civil work.After completion of the boundary wall we will start our other works. 02.11.2016 Bashundhora Group already starts the civil work.After completion of the boundary wall we will start our other works. 10.11.2016 Bashundhora Group already starts the civil work. After Completing the civil work we will start out work. 17.11.2016 -Bashundhora Group already starts the civil work. -After completion of the boundary wall we will start our other works. 24.11.2016 -Boundary wall work 100% done. 01.12.2016 -No further update. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 -No further update. 29.12.2016 Do as Previous Week. 05.01.2017 TO 02.03.2017 -No further update. 09.03.2017 -Equipment not yet arrived at site like Clamp connector etc. -Design,drawing work is processing going on for earthing ,panel arrangement. 16.03.2017 -Design, drawing works is going on. 23.03.2017 -No further date. 30.03.2017 -No further update. -Waiting for electrical equipment's. 06.04.2017 13.04.2017 -Same as before. 20.04.2017 -No further update. -Waiting for electrical equipment's. to 13.07.2017 -No further update.
[7 empty] | Site Engr Mr Rakib- |  | 1716275376 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
17 | Bashundhara Group | - | Bashundhara Group Client - - | 17 | Bashundara, N'Ganj | Bashundhara Group Project Manager Engr. Abul Kalam Azad- 01777781202 Site Eng Kabir 01711541491 | Engr. Abul Kalam Azad- | Bashundhara Group Project Manager | 1777781202 | - | - | Deed Agreement | Bashundara, N'Ganj Project Manager Bashundhara Group Project Manager Engr. Abul Kalam Azad- 01777781202 Site Eng Kabir 01711541491 | 23.10.2016 -Materials arrived at site. 27.10.2016 02.11.2016 -CSE yet Not delivered. After delivery of CSE we will start our erection work. 10.11.2016 -CSE yet not delivered. After delivery of CSE we will start our erection work. 17.11.2016 -CSE yet Not delivered at site. After delivery of CSE we will start our erection work. 24.11.2016 -CSE already arrived in Factory but Not yet delivered at site. 01.12.2016 -No further update. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 -Cable termination work is going on by Chinese Engineers. 29.12.2016 -132 kV Power cable termination and all electrical equipment's installation is completed.-Testing will be started very soon. 05.01.2017 -All necessary work has done for Power line run, without Gas refilling for Breaker. 12.01.2017 -No further update. 19.01.2017 -Equipment testing is going on. 26.01.2017 -Equipment testing is going on. 02.02.2017 -Sub Station is running now. 09.02.2017 -No further update. 16.02.2017 -No further update. 23.02.2017 -Preparation work is going on for 06 Nos of XFR parallel running for Rahim steel.(for 132kV 20/25MVA 02 Nos & 10/14 MVA 04 Nos). 02.03.2017 -75% work has been done for 06 Nos of XFR parallel running for Rahim steel. (for 132kV 20/25MVA 02 Nos & 10/14 MVA 04 Nos). 09.03.2017 -100% work has been done for 06 Nos of XFR parallel running for Rahim steel. (for 132kV 20/25MVA 02 Nos & 10/14 MVA 04 Nos). 16.03.2017 -Same as before. -Waiting for the operation. 23.03.2017 to 13.04.2017 -No further update. 20.04.2017 -All XFR is running in parallel operation. 27.04.2017 -Same as before. to 11.05.2017 -No further update. 18.05.2017 -Same as before. 25.05.2017 Panel placement drawing approval.Soil treatment instruction for earthing.DO ready for panel delivery. 01.06.2017 Panel delivery has been arrived at site.06 pc’s Breaker on the way to Bangladesh from India.PGCB control building’s floor cutting work is going on. 08.06.2017 -No further update. 15.06.2017 Panel placement drawing approval.Soil treatment instruction for earthing. Panel delivery at Site.33kv CT,PT delivery at site will be 21 june,17 22.06.2017 29.06.2017 -No further update. 06.07.2017 -Clamp & connector has been arrived at site at 03 july,2017 from India.PGCB end panel arrangement punching work has been handed over to Innovate company as a subcontractor.Punching work is going on then panel will be Erection. 13.07.2017 -No further update.
[7 empty] | Site Eng Kabir |  | 1711541491 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
18 | 132/33 kV S/S at Matarbari | Coal Power Co Ltd | 132/33 kV S/S at Matarbari Client - Coal Power Co Ltd | 18 | Matarbari Moheshkhali | Kh Belal Hossain 01730075384 Delwar Hosssain 01755633876 | Kh Belal Hossain |  | 1730075384 | - | - | Deed Agreement | Matarbari Moheshkhali Project Manager Kh Belal Hossain 01730075384 Delwar Hosssain 01755633876 | 27.10.2016 GA & GTP of 132 kV CB approved.GA & GTP of 33 kV CB resubmitted for approval.1st & grn floor plan submitted for approval.sand filling 65 %. 07.11.2016 GA & GTP of 132 kV CB and GA & GTP of Aux.TFR approved. GA & GTP of 33 kV CB and GA & GTP of 132 & 33 kV CT & IVT resubmitted for approval.1st & ground floor plan approved.sand filling 65% 11.11.2016 GA & GTP of 132 KV CB & GA and GTP of Aux.TFR and GA & GTP of 33 kV CB are approved.GA & GTP of 132 & 33 kV CT & IVT resubmitted for approval.Slope protection drawing approved.1st & gnd floor plan approved. Architectural drawing of control room submitted for approval.sand filling 70 % (~4600000cft) done. 17.11.2016 -GA & GTP of 132 kV CB, 33 kV CB, 132 & 33 kV CT & IVT , Aux. TFR approved.GA & GTP of Bus bar conductor submitted for approval.Slope protection drawing approved. Ist & gnd floor plan approved. -Architectural drawing of control room submitted for approval. -sand filliong 70 % (~4600000cft) done. 24.11.2016 -No update. 01.12.2016 -No further update 08.12.2016 -Sand filling work is going on. 15.12.2016 -One bulldozer added in site. -Sand slope making work going on. 22.12.2016 -Dam work is going on -Sloping work is continued -1 Nos Excavator and 1 Nos of Bulldozer is deployed for this work. 29.12.2016 -No further update. 05.01.2017 -No further update. 12.01.2017 -Slope and ambak/byke work is going on by 03 nos excavator and 02 nos Drager. 26.01.2017 -Slope and ambak/ byke work going by -03 nos excavator & 02 Nos Draggers are working.Earth protection work by using wooden bully is going on. 02.02.2017 -No further update. 09.02.2017 -Sand filling work has restart.Slope and ambak/ byke work has completed. 16.02.2017 -Same as before. 23.02.2017 -Sand filling work is going on. 02.03.2017 -Same as before. 09.03.2017 -Dragging work,Labor shed making work and Leveling work has been done. 16.03.2017 -Security guard room making. Sand filling is going on. 23.03.2017 -Sand filling work is going on. 30.03.2017 -Sand filling work has been stopped for billing issue. 06.04.2017 -Sand filling work is going on. 13.04.2017 -Sand filling work is going on.Dresser work is going on.Block (brick chip)arrived at site. 20.04.2017 -Sand filling has been completed.Block & brick chip has been arrived at site. 27.04.2017 -Shed making work is continue.Block setting, drecing,leveling & compaction work is going on.Block production work also going on. 04.05.2017 -Shed making work is completed for cement. Block setting, drecing,leveling & compaction work is going on.Block production work also going on. 11.05.2017 Block setting, drecing, leveling & compaction work is going on.Block production work also going on. 25.05.2017 -14 Nos pile work has done for boundary wall.06 Nos base earth excavation work has done at 33kV control building. Pile cap ballast & CC work has been completed. 01.06.2017 Block carrying, dressing, leveling & compaction work is going on. Block production work also going on. 08.06.2017 Slope protection work has been done.Block carrying, setting, mortaring & site dressing, leveling work is going on. 15.06.2017 Block carrying, motering, making.Water house making has ben completed.Site layout has been completed for pile work.Rig machine with accessories arrived at site. 22.06.2017 Block carrying, setting,motering, dressing, leveling work is going on.Site protection work has done in east side.Sand & stone arrived at site.Pilling work has been started. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 Block setting work has done site protection.Temporary house making work has been completed.18 Nos Pile has done.Soil excavation work is going on. 13.07.2017 -25 Nos pile cast has been done for control building.
[7 empty] | Delwar Hosssain |  | 1755633876 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | Oct 31' 16 | Declaration of completion
19 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram | PGCB | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram Client - PGCB | 19.1 | SHERPUR (BOGRA) Design Supply,Installation, Testing commissioning of 132/33kV S/S. | Md Imran Hossain 01713242198 | Md Imran Hossain |  | 1713242198 | - | - | Deed Agreement | SHERPUR (BOGRA) Design Supply,Installation, Testing commissioning of 132/33kV S/S. Project Manager Md Imran Hossain 01713242198 | 27.10.2016 GA & GTP of 132 kV CB approved.GA & GTP of 33 kV CB resubmitted for approval.1st & grn floor plan submitted for approval.sand filling 65 %. 07.11.2016 GA & GTP of 132 kV CB and GA & GTP of Aux.TFR approved. GA & GTP of 33 kV CB and GA & GTP of 132 & 33 kV CT & IVT resubmitted for approval.1st & ground floor plan approved.sand filling 65% 11.11.2016 GA & GTP of 132 KV CB & GA and GTP of Aux.TFR and GA & GTP of 33 kV CB are approved.GA & GTP of 132 & 33 kV CT & IVT resubmitted for approval.Slope protection drawing approved.1st & gnd floor plan approved. Architectural drawing of control room submitted for approval.sand filling 70 % (~4600000cft) done. 17.11.2016 -GA & GTP of 132 kV CB, 33 kV CB, 132 & 33 kV CT & IVT , Aux. TFR approved.GA & GTP of Bus bar conductor submitted for approval.Slope protection drawing approved. Ist & gnd floor plan approved. -Architectural drawing of control room submitted for approval. -sand filliong 70 % (~4600000cft) done. 24.11.2016 -No update. 01.12.2016 -No further update 08.12.2016 -Sand filling work is going on. 15.12.2016 -One bulldozer added in site. -Sand slope making work going on. 22.12.2016 -Dam work is going on -Sloping work is continued -1 Nos Excavator and 1 Nos of Bulldozer is deployed for this work. 29.12.2016 -No further update. 05.01.2017 -No further update. 12.01.2017 -Slope and ambak/byke work is going on by 03 nos excavator and 02 nos Drager. 26.01.2017 -Slope and ambak/ byke work going by -03 nos excavator & 02 Nos Draggers are working. -Earth protection work by using wooden bully is going on. 02.02.2017 -No further update. 09.02.2017 -Sand filling work has restart.Slope and ambak/ byke work has completed. 16.02.2017 -Same as before. 23.02.2017 -Sand filling work is going on. 02.03.2017 -Same as before. 09.03.2017 -Dragging work,Labor shed making work and Leveling work has been done. 16.03.2017 -Security guard room making. Sand filling is going on. 23.03.2017 -Sand filling work is going on. 30.03.2017 -Sand filling work has been stopped for billing issue. 06.04.2017 -Sand filling work is going on. 13.04.2017 -Sand filling work is going on.Dresser work is going on.Block (brick chip)arrived at site. 20.04.2017 -Sand filling has been completed.Block & brick chip has been arrived at site. 27.04.2017 -Shed making work is continue.Block setting, drecing,leveling & compaction work is going on.Block production work also going on. 04.05.2017 -Shed making work is completed for cement. Block setting, drecing,leveling & compaction work is going on.Block production work also going on. 11.05.2017 Block setting, drecing, leveling & compaction work is going on.Block production work also going on. 18.05.2017 -Block carrying, dressing, leveling & compaction work is going on.Block production work also going on.Labor shed work has been completed. Cement shed extension work has done. Site toilet making work is going on. 25.05.2017 08 Nos pile has been completed at switchyard.Centering work is going on for roof cast at Ansar barrack.05 Nos base casting has been completed at 33kV. 01.06.2017 11 Nos base casting has been completed at control building.Re-bar work is continuing.Pile head broken work 75% has been completed at 132 control building.15 Nos base casting has completed for boundary wall.76/112 Nos pile has been completed. 08.06.2017 33kv control building grade beam casting completed.06 out of 12 Nos pile has been complete for XFR.86 Nos out of 112 Nos pile work has ben completed. Boundary wall.20 Nos column casting has been completed at 132 kV switchyard. 15.06.2017 33kv control building column casting completed.84 Nos out of 112 Nos pile work has ben completed at 132 Kv S/Y.50 Nos Boundary wall column,base Gb casting has been completed. 22.06.2017 -33kv control building first floor slab casting completed.30 Nos Boundary wall column casting done. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 200m long Boundary wall has been completed. Ansar barrack roof casting has completed. 33kV control building ground floor roof casting has completed.33kV control building first floor roof casting will be completed at 15 july,2017 . 132kV control building ground floor roof casting will be completed at 30 jul,2017.Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site.15 Nos pudding has done at 132kV control building. 11Nos column has been completed at 33kV control building. | 13.07.2017 132kV Control room building 06nos RCC base casting complete. Boundary wall 30nos column base casting complete.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
19 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | PGCB | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S Client - PGCB | 19.2 | KURIGRAM Design Supply,Installation, Testing commissioning of 132/33kV | Md Imran Hossain 01713242198 | Md Imran Hossain |  | 1713242198 | - | - | Deed Agreement | KURIGRAM Design Supply,Installation, Testing commissioning of 132/33kV Project Manager Md Imran Hossain 01713242198 | 23-10-2016 - Sand Filling work is on progress. Approximately 225,000 cft Sand has been filled. 03.11.2016 -Sand Filling on Progress. 10.11.2016 -Sand Filling from a new point (Jorgacha) which is 11km from the site has started. 17.11.2016 -Approx. 250000 cft. Sand has been filled.GA & GTP of 132kV LA has been approved.GA & GTP of 33kV LA has been approved. 24.11.2016 -Sand Filling on Progress. -Overall Site Layout Approved. -Bore Hole Layout Approved. 01.12.2016 -Sand Filling work on progress. 08.12.2016 -Approx. 470,000 cft. Sand has been filled.Site mobilization work on progress.Site boundary & other site work on progress. 15.12.2016 -Sand has been filed aprox. 55000cft sand.new gate setting, electricity line connected.Soil test report approved. 22-12-2016 -Approx. 650000cft sand has been filled.Soil Test equipment's has been mobilized & ready for initiation.-GA & GTP of 132kV DS approved.-GA & GTP of 132kV IVT approved.-GA & GTP of 33kV IVT approved. 29.12.2016 -Approx. 700000cft sand has been filled.Soil Test On going.GTP of 132kV CB Submitted. 05-01-2017 -Approx. 780000cft sand has been filled. Soil Test On Going (29 boring out of 40 Completed ).GTP & GA of 33kV VCB Submitted.Control Room CRP Layout design submitted -HFL level approved by PGCB. 12-01-2017 Soil Test 40 nos completed -Control Room CRP Layout design approved. 26.01.2017 -132/33kV new grid S/S Road level sand filing complete and flood level reference sand filing continue. 02-02-2017 -Approx. 1100000 cft sand has been filled.PDB Pole Removal on progress.Soil Test Completed.GA & GTP of 33V DS Approved.CRP Panel of 132kV & 33kV Control room.Approved ..Pre pilling work on progress. 09.02.2017 ----- 16.02.2017 -Approx. 13 Lac cft sand has been filled. New REB & PDB Pole installed. Existing Poles will be removed very soon.GA & GTP of Thermal ACSR Approved. 23.02.2017 -Approx. 14lac cft sand has been filled.GA & GTP of 33kV VCB & 132kV CB has been Approved.Labor Shed, Cement Store & Toilet building on progress.RL Level has been confirmed.Pilling House completedPilling Rig has been mobilized. 02.03.2017 -Approx. 15lac cft sand has been filled.GA & GTP of 33kV VCB & 132kV CB has been Approved.Ground floor plan of 132 & 33 kV control building drawing has been approved. Labor Shed, Cement Store & Toilet building on progress.RL Level has been confirmed.Pilling House completed -04 Nos Pilling Rig has been mobilized. 09.03.2017 -39 Nos pile work has been done for 132 kV & 33kV control building. 16.03.2017 -31 Nos pile work has been done for 132 kV & 33kV control building.sand filling continuing. 23.03.2017 -All Pile work has been done for 132 kV & 33kV control building. Sand filling continuing.Pile work is going on for Boundary wall. 30.03.2017 -Pile and sand-filling is going on. 06.04.2017 -15/112 Nos pile has been done for switchyard.100/216 Nos pile has been done for boundary. 13.04.2017 -20/112 Nos pile has been done for switch yard.112/216 Nos pile has been done for boundary.04 Nos base foundation has been done for Ansar barrack. 20.04.2017 -60% pile work has been done for switch yard.80% pile has been done for boundary.30% base foundation has been done for Ansar barrack.GTP & GA of Power XFR has been approved. Drawing of 33kV CT has been approved. 27.04.2017 -35Nos pile has been done at switchyard.10 Nos putting base work has been completed at ansar brack.140 Nos pile has been done for boundary wall. 04.05.2017 -01 Nos pile has been done at Switchyard.Pile head broken work is continuing at 33kV & ansar barrack area. 11.05.2017 -Total 39 Nos out of 112 Nos pile has been completed at S/Y.Earth filling work in ansar barrack.11 Nos pile cap broken work has been done at 33kV control building. 18.05.2017 -07 Nos out of 112 Nos pile has been completed at S/Y.Earth filling work is going on at ansar barrack. All pile cap broken work has been done at 33kV control building. 25.05.2017 -14 Nos pile work has done for boundary wall.06 Nos base earth excavation work has done at 33kV control building. Pile cap ballast & CC work has been completed. 01.06.2017 32 Nos boundary wall pile has been completed.33kV control building:11Nos base earth excavation pile cap ballast & cement concrete 06 Nos complete. Ansar barrack :07 Nos earth excavation & 03 Nos cement concrete has been completed. 08.06.2017 33kV control building: 11Nos pile cap casting has completed.Ansar barrack :soil excavation & footing casting, short column casting work has been done.58 Nos boundary wall pile has been completed. 15.06.2017 22 Nos boundary wall pile,03 Nos TR pile & 33kV control building grade beam casting completed.Ansar barak grade beam casting,5 Nos pile cap earth excavation for 132kV,15 Nos pile ballast & 05 Nos pile cap casting has been done. 22.06.2017 52 Nos pile work done at boundary wall. 01 Nos TR pile work has dpne.11 Nos column casting has been done at 33kV control building.First slab casting has done at Ansar barak.5 Nos pile cap,05 Nos pile ballast work & 11 Nos casting and earth excavation work has been completed at 132kV. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 15m long Boundary wall has been completed.Ansar barrack roof casting has completed.33kV control building ground floor roof casting will be completed at 18jul,2017.132kV control building ground floor roof casting will be completed at 30jul,2017.Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 -XFR pad 02 Nos pile has been completed.132kV control building 11 Nos pile cap casting has done.Total 220m pile cap & grade beam has been casting at boundary wall.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
19 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | PGCB | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S Client - PGCB | 19.3 | THAKURGAON Capacity upgradation of existing132/33kV S/S | Imran Hossain 01713242198 | Md Imran Hossain |  | 1713242198 | - | - | Deed Agreement | THAKURGAON Capacity upgradation of existing132/33kV S/S Project Manager Imran Hossain 01713242198 | 23-10-2016 -Sand Filling work is going on. Sand being extracted from three points.Approximately 210,000 cft Sand has been filled. 27.10.2016 03.11.2016 -Sand Filling Work on Progress 10.11.2016 -Sand Filling work on going. 17.11.2016.Approx. 300000 cft. Sand has been filled .GA & GTP of 132kV LA has been approved .GA & GTP of 33kV LA has been approved. 17.11.2016 -Approx. 300000 cft. Sand has been filled .GA & GTP of 132kV LA has been approved.GA & GTP of 33kV LA has been approved. 24.11.2016 -Sand Filling on Progress. -Overall Site Layout Approved. -Bore Hole Layout Approved. 01.12.2016 -Sand Filling work on progress. 08.12.2016 -Approx. 700000 cft. Sand has been filled.Site Mobilization on progress. 15.12.2016 Soil test on going.barbed wire make boundary.New electricity connection get Container decoration on going. 22-12-2016 Soil Test Completed.Container Office work completed.Office toilet work in progress.Site was inaugurated by PGCB MD.Gate was successfully installed.Site area cordoned with bamboo & barbed wire.Electricity line connected.GA & GTP of 132kV Disconnector approved.GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -Sand Filling on going. -GA & GTP of 132kV CB Submitted. 05-01-2017 -Sand filling nearing completion -Soil Test report submitted by the sub contractor.GTP & GA of 33kV VCB Submitted.Control Room CRP Layout design submitted.HFL level approved by PGCB. 12-01-2017 -Sand filling is completed upto Public highway.Control Room CRP Layout design approved 26.01.2017 -No update yet. 02-02-2017 -Sand Filling on going.Soil Test Completed.GA & GTP of 33V DS Approved.CRP Panel of 132kV & 33kV Control room Approved.Pre pilling work on progress. 09.02.2017 ----- 16.02.2017 -Sand Filling nearing completion.Toilet, Labor Shed , Cement Shed, Pilling House Completed.Pilling will begun very soon -Pilling materials arrived.GA & GTP of Thermal ACSR Approved. 02.03.2017 -Sand filling nearing completion.GA & GTP of 33kV VCB & 132kV CB has been Approved.Pilling work already started.13nos pile has been completed.abour shed & store has been complete.RL Level has been confirmed. 09.03.2017 -17 Nos pile has been done for 132kV control building. 16.03.2017 -N o further update. 23.03.2017 -42 Nos piles have been completed in 132 KV control room building. 30.03.2017 -12 Nos piles have been completed in 132 KV control room building. 06.04.2017 -10Nos piles have been completed in 132 KV control room building.02 Nos piles have been completed in 33 KV control room building. 13.04.2017 -07 Nos piles have been complete in 33kV control room building.02 Nos piles have been complete in 132kV switchyard. 20.04.2017 -GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved.100% piles have been complete in 33kV control room building. 100% piles have been complete in 132kV switchyard. 27.04.2017 -16 Nos piles have been complete in 132kV S/Y.13 Nos piles have been complete in 33kV control building. 04.05.2017 -14 Nos piles have been complete in 132kV S/Y. 11.05.2017 -06 Nos piles have been completed in 132kV S/Y. 18.05.2017 -Labor shed making work has been done.Site leveling work s going on. 25.05.2017 to 29.06.2017 -No further update. 06.07.2017 -No further update. -Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 -No further update.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
19 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33 kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | PGCB | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33 kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S Client - PGCB | 19.4 | PALASHBARI Capacity upgradation of existing132/33kV S/S | Md Imran Hossain 01713242198 | Md Imran Hossain |  | 1713242198 | - | - | Deed Agreement | PALASHBARI Capacity upgradation of existing132/33kV S/S Project Manager Md Imran Hossain 01713242198 | 23-10-2016 Approved Drawings: SLD, Overall Layout, Electrical Layout, Section of Electrical Layout. 27.10.2016 to 10.11.2016 -No Update 17.11.2016 -GA & GTP of 132kV LA has been approved.GA & GTP of 33kV LA has been approved. 24.11.2016 -No Update. 01.12.2016 -No further update. 08.12.2016 -Equipment of GA GTP on progress. 15.12.2016 -No update. 22-12-2016 -GA & GTP of 132kV Disconnector approved.GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -GA & GTP of 132kV CB Submitted. 05-01-2017 -Sand filling nearing completion.Test report submitted by the sub contractor.GTP & GA of 33kV VCB Submitted.Control Room CRP Layout design submitted -HFL level approved by PGCB. 12.01.2017 CT Sizing calculation submitted. 26.01.2017 -No update yet. 02.02.2017 GA & GTP of 33kV DS Approved. 09.02.2017 ----- 16.0.2.2017 -GA & GTP of Thermal ACSR Approved. 23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 02.03.2017 to 13.04.2017 -No further update. 20.04.2017 -Final inspection work has been done for CRP layout & measurement.GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved. 27.04.2017 -No further update. to 29.06.2017 -No further update. 06.07.2017 -No further update. -Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 -No further update.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
19 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | PGCB | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S Client - PGCB | 19.5 | SHIRAJGANJ Capacity upgradation of existing132/33kV S/S | Md Imran Hossain 01713242198 | Md Imran Hossain |  | 1713242198 | - | - | Deed Agreement | SHIRAJGANJ Capacity upgradation of existing132/33kV S/S Project Manager Md Imran Hossain 01713242198 | 17-10-2016 Site Status:Preliminary & Secondary Inspection Completed,Drawing Status: Revised SLD submitted .Revised overall site layout submitted ,Revised section of outdoor equipment submitted,Revised control panel layout has been submitted. 23-10-2016 Approved Drawings: Single Line Diagram, Overall Layout, Electrical Layout, Section of Electrical Layout. 27.10.2016 to 10.11.2016 -No Update. 17.11.2016 -GA & GTP of 132kV LA has been approved.GA & GTP of 33kV LA has been approved. 24.11.2016 -No Update. 01.12.2016 -No further update. 08.12.2016 -Equipment of GA GTP on progress. 15.12.2016 No further update. 22-12-2016 GA & GTP of 132kV Disconnector approved. -GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -GA & GTP of 132kV CB Submitted. 05.01.2017 -GTP & GA of 33kV VCB Submitted -Control Room CRP Layout design submitted -HFL level approved by PGCB. 12.01.2017 CT Sizing calculation submitted. 26.01.2017 -No update yet. 02.02.2017 GA & GTP of 33kV DS Approved. 09.02.2017 ----- 16.02.2017 -GA & GTP of Thermal ACSR Approved. 23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 02.03.2017 to 13.04.2017 -No further update. 20.04.2017 -Final inspection work has been done for CRP layout & measurement.GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved. 27.04.2017 to 29.06.2017 -No further update. 06.07.2017 -No further update. -Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 -No further update.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
19 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | PGCB | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S Client - PGCB | 19.6 | NATORE Capacity upgradation of existing 132/33kV S/S | Md Imran Hossain 01713242198 | Md Imran Hossain |  | 1713242198 | - | - | Deed Agreement | NATORE Capacity upgradation of existing 132/33kV S/S Project Manager Md Imran Hossain 01713242198 | 23-10-2016 -Approved Drawings: Single Line Diagram, Overall Layout, Electrical Layout,Section of Electrical Layout. 27.10.2016 to 10.11.2016 No Update. 17.11.2016 -GA & GTP of 132kV LA has been approved GA & GTP of 33kV LA has been approved. 24.11.2016 -No Update. 01.12.2016 -2nd Site Visit Conducted along with PGCB Delegates (Design Dept.) 08.12.2016 -Final site visit completed. 15.12.2016 No further update. 22-12-2016 GA & GTP of 132kV Disconnector approved. -GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -GA & GTP of 132kV CB Submitted. 05.01.2017 -GTP & GA of 33kV VCB Submitted.Control Room CRP Layout design submitted -HFL level approved by PGCB. 12.01.2017 CT Sizing calculation submitted. 26.01.2017 -No update yet. 02.02.2017 GA & GTP of 33kV DS Approved. 09.02.2017 ----- 16.02.2017 -GA & GTP of Thermal ACSR Approved. 23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 02.03.2017 to 06.04.2017 to 13.04.2017 -No further update. 20.04.2017 -Final inspection work has been done for CRP layout & measurement.GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved. 27.04.2017 to 29.06.2017 -No further update. 06.07.2017 -No further update. -Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 -No further update.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
19 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | PGCB | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S Client - PGCB | 19.7 | CHAPAI NABABGANJ Capacity upgradation of existing132/33kV S/S | Md Imran Hossain 01713242198 | Md Imran Hossain |  | 1713242198 | - | - | Deed Agreement | CHAPAI NABABGANJ Capacity upgradation of existing132/33kV S/S Project Manager Md Imran Hossain 01713242198 | 17-10-2016 Site Status: Preliminary Inspection Complete Drawing Status: Ready for submission:SLD -Overall site layout.Section of outdoor equipment Control panel layout has been submitted. 23.10.2016 to 10.11.2016 -No update. 17.11.2016 -GA & GTP of 132kV LA has been approved.GA & GTP of 33kV LA has been approved. 24.11.2016 -No Update. 01.12.2016 -2nd Site Visit Conducted along with PGCB Delegates (Design Dept.) 08.12.2016 -Drawing / design approval after visit on process. 15.12.2016 No further update. 22-12-2016 GA & GTP of 132kV Disconnector approved. -GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -GA & GTP of 132kV CB Submitted.05.01.2017 -GTP & GA of 33kV VCB Submitted. 05.01.2017 -GTP & GA of 33kV VCB Submitted. 12.01.2017 26.01.2017 -No update yet. 02.02.2017 GA & GTP of 33kV DS Approved. 09.02.2017 ----- 16.02.2017 -GA & GTP of Thermal ACSR Approved. 23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 02.03.2017 to 13.04.2017 -No further update. 20.04.2017 -Final inspection work has been done for CRP layout & measurement.GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved. 27.04.2017 to 29.06.2017 -No further update. 06.07.2017 -No further update. -Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 -No further update.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
19 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | PGCB | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S Client - PGCB | 19.8 | RANGPUR 132kV bay extension | Md Imran Hossain 01713242198 | Md Imran Hossain |  | 1713242198 | - | - | Deed Agreement | RANGPUR 132kV bay extension Project Manager Md Imran Hossain 01713242198 | 17-10-2016 Site Status: Preliminary Inspection Completed.Drawing Status:-SLD submitted -Overall site layout submitted -Section of outdoor equipment submitted -Control panel layout has been submitted. 23.10.2016 to 10.11.2016 -No update. 17.11.2016 -GA & GTP of 132kV LA has been approved.GA & GTP of 33kV LA has been approved. 24.11.2016 -No Update. 01.12.2016 -2nd Site Visit Conducted along with PGCB Delegates (Design Dept.). 08.12.2016 -Drawing / design approval after visit on process. 15.12.2016 No update. 22-12-2016 GA & GTP of 132kV Disconnector approved. -GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -GA & GTP of 132kV CB Submitted. 05.01.2017 -GTP & GA of 33kV VCB Submitted.Control Room CRP Layout design submitted.HFL level approved by PGCB. 12.01.2017 CT Sizing calculation submitted. 26.01.2017 -No update yet. 09.02.2017 ----- 02.02.2017 GA & GTP of 33kV DS Approved. 16.02.2017 -GA & GTP of Thermal ACSR Approved.23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 02.03.2017 to 13.04.2017 -No further update. 20.04.2017 -Final inspection work has been done for CRP layout & measurement.GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved. 27.04.2017 to 22.06.2017 -No further update. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -No further update. -Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 -No further update.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
20 | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura | PGCB | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura Client - PGCB | 20.1 | NAWABGANJ Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S | Project Manager Md Enamul Haq 01708131702 Mr Farid Ahmed 01914454350 Sae. Aslam 01708131701 Rakib-01708453358 | Md Enamul Haq | Project Manager | 1708131702 | - | - | Deed Agreement | NAWABGANJ Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S Project Manager Project Manager Md Enamul Haq 01708131702 Mr Farid Ahmed 01914454350 Sae. Aslam 01708131701 Rakib-01708453358 | 23-10-2016 -Approved Drawings: Single Line Diagram, Overall Layout, Electrical Layout, -Section of Electrical Layout 27.10.2016 -Bore Hole Layout has been submitted for Approval. 03.11.2016 Bore Hole Layout has been Approved. Soil Testing will begin on 6-11-2016. 10.11.2016 Soil Test Completed. 17.11.2016 -GA & GTP of ACSR (Mallard) has been approved - GA & GTP of 132kV LA has been approved. 24.11.2016 -Soil Test work Completed. 01.12.2016 -No further update. 08.12.2016 -Equipment of GA GTP on progress. 15.12.2016 No update. 22-12-2016 GA & GTP of 132kV Disconnector approved. -GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -GA & GTP of 132kV CB Submitted. 05.01.2017 -GTP & GA of 33kV VCB Submitted -Control Room CRP Layout design submitted -HFL level approved by PGCB. 12.01.2017 -CT sizing calculation approved.Civil drawing of respective civil work is approved. 19.01.2017 -Sand filling going on approx. 28300 cft. 26.01.2017 -No update yet. 02.02.2017 -Pre pilling work on progress. 09.02.2017 ----- 16.02.2017 -Pilling House, Cement Shed Completed.Some Pilling materials already arrived.GA & GTP of Thermal ACSR Approved. 23.02.2017 -Pilling materials are being mobilized.GA & GTP of 132kV CB has been Approved. 02.03.2017 to 13.04.2017 -No further update. 20.04.2017 -Final inspection work has been done for CRP layout & measurement.GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved. 04.05.2017 48600 cft Sand filling work has been completed. 11.05.2017 111700 cft Sand filling work has been completed. 18.05.2017 Total 68 Nos out of 88 Nos Pile has been completed.13 Nos VCB arrived at site .132kV control building 19 out 32 pile cap casting has done33kV control building earth excavation has done.07Nos pile cap head broken work has done. 11.05.2017 -No further update. 18.05.2017 -No further update. 25.05.2017 -Total 76 Nos out of 88 Nos Pile has been completed.132kV control building 32 out of 32 pile cap casting has done.Total 20 Nos pile cap head broken work has been done.09 Nos pile cap cast at 33kv control building. 01.06.2017 Total 88 Nos out of 88 Nos Pile has been completed.Total 16 Nos pile cap head broken work has been done.12 Nos pile cap cast at 33kv control building. 08.06.2017 132kV control building floor,grade beam, column casting has been done.33 kV grade beam & column casting has been done. 15.06.2017 132kV CB:First floor beam shuttering on going, internal stair first landing, ground floor curing, external stair cast,132kV CB:GB casting, column trigger casting, dressing & leveling on going. 132kV S/Y:19Nos pile cap earth excavation, 10Nos pile head broken, 02 Nos pile cap cast.6200 cft Sand filling work has done, 110 Nos pile has been done at Boundary. 22.06.2017 132 kV & 33 kV CB:First floor beam & slab shuttering work is going on.132kV S/Y:All pile cap earth work has done,02 Nos cap casting has done.02 Nos CC casting work has done.12300 cft Sand filling work has done. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -Rod binding work has been done for 132 kV & 33 kV control building.Rod binding work has been done for column at 132kv gantry tower. | 13.07.2017 132kV CB:1st floor beam & slab casting done. 33kV CB:2nd floor column 2nd lift curing. 33kV SY :Earth works ongoing & 2nos base CC done.132kV SY :Column 16nos casting.Sand filling: 00nos.=00cft.XFR 2 base rod binding work done.XFR 1 earth excavation works & CC casting done. Pile cap rod binding work running.Boundary pile cap & column rod binding ( west side) running.
[7 empty] | Mr Farid Ahmed |  | 1914454350 | - | - | Contract Date
[7 empty] | Sae. Aslam |  | 1708131701 | - | - | Commencement Work
[7 empty] | Rakib |  | 1708453358 | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
20 | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura | PGCB | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura Client - PGCB | 20.2 | SRINAGAR Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S | Enamul Haq 01708131702 Farid Ahmed 01914454350 Ziaur-01708453369 | Enamul Haq |  | 1708131702 | - | - | Deed Agreement | SRINAGAR Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S Project Manager Enamul Haq 01708131702 Farid Ahmed 01914454350 Ziaur-01708453369 | 27.10.2016 90% Dyke construction complete.1500m dredging pipe setting complete. Dredger machine installation ongoing. Booster machine is not reached yet at site. 03.11.2016 3400ft (52% of total 6600 ft) pipe setting complete. 90% of dyke construction complete.Dredger machine installation complete.Booster machine is not reached yet at site. 10.11.2016 -No further update. 17.11.2016 -Pipe setting work running. (Dredger and Booster end). 24.11.2016 -Sand filling work started at site. 01.12.2016 -Approximate 70000 cft Sand filling done. 08.12.2016 -Approximate 10200 cft Sand filling has been done. 15.12.2016 -105000 cft of 300000 cft Sand filling completed. Sand filling will resume on 19th dec’16. 22.12.2016 -Sand filling work is going on. 29.12.2016 -Sand filling is continued. 05.01.2017 -Sand filling work is going on approx. 145700 cft. 12.01.2017 -Sand filling work is going on approx. 80000 cft. 19.01.2017 -Lay out & preparation work is going on for piling. 26.01.2017 -Weekly sand filling 167950 cft. 02.02.2017 -Sand filling going on approx.276392 cft. This week 09.02.2017 -Sand filling going on approx.377135cft. 16.02.2017 -Sand filling going on approx.259086 cft. 23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 02.03.2017 -Sand filling going on approx.92300 cft. 09.03.2017 -Sand filling going on approx.98100 cft. 16.03.2017 -Sand filling going on approx. 100700 cft. 23.03.2017 -Sand filling going on approx. 1,39,000 cft. 30.03.2017 -Sand filling going on approx.119700 cft. 06.04.2017 -Sand filling going on approx.100900 cft. 13.04.2017 -137700 cft Sand filling work has been completed. Lay out has been done at CB & Switchyard for 132k V & 33kV.Brick soling & hearing bond work has been completed.18Nos pile has been done. 20.04.2017 -216800 cft Sand filling work has been completed. 27.04.2017 -125000cft Sand filling work has been completed. 04.05.2017 -48600 cft Sand filling work has been completed. 11.05.2017 -111700 cft Sand filling work has been completed. 18.05.2017 Total 68 Nos out of 88 Nos Pile has been completed. 13 Nos VCB arrived at site .132kV control building 19 out 32 pile cap casting has done.33kV control building earth excavation has done.07 Nos pile cap head broken work has done. 25.05.2017 -132kV control building building:First floor slab shutter work is going on.33kV control building :Ground floor brick wall making done up to linten,Linten shutter work is running. Boundary wall:20 Nos column cast,40m gread beam and brick wall making has been done.33kV S/Y:7/22 gantry cast,03 Nos excavation & 03 Nos gantry base macadam and CC casting has been done.XFR foundation:2nd XFR over all base rod binding & shuttering complete. 01.06.2017 -132kV control building building :First floor slab shutter work has completed. Rod binding work is continuing. Ground floor slab plaster has done.Linten,brick wall & plaster work 50% has done.33kV control building:Ground floor Linten,Brick wall completed up to linten.Ground floor slab plaster completed & Brick wall 70% plaster completed. Boundary wall:07 Nos column casting done.25m grade beam 7 Brick wall making has done.132kV S/Y:Total 56/88 Nos pedestal column casting has done.33kV S/Y:16/22 gantry cast,10 Nos excavation & 10 Nos gantry base macadam &02 Nos VCB foundation base casting,03 Nos soil excavation has done.XFR foundation:2nd XFR over all base casting done 08.06.2017 132kV control building building:2nd floor slab casting,Linten,brick wall & plaster work 100%,Brick wall plaster 70% completed.33kV control building : Ground floor brick wall 100% completed with plaster work.Boundary wall:01 No column casting done, total column,pile cap,gread beam brick wall completed.132kV S/Y: 72/88 Nos pedestal column casting has been done.33kV S/Y :22/22 gantry cast 10 Nos excavation,10 Nos VCB foundation base casting, 03 Nos soil excavation has done.XFR foundation:02 Nos XFR pit wall & beam rod binding completed, 15.06.2017 132kV control building building:Brick wall plaster 100% completed at internal side.33kV control building: 04 Nos windows sun shed & drop wall casting done.Boundary wall: 50m coping casting has been done.132kV S/Y:32 Nos pedestal column casting has been done.33kV S/Y:06 Nos base & gantry casting done.12 Nos VCB foundation base casting, 07 Nos VCB bay/beam cast has been completed.50% cable trench soil excavation has done.XFR foundation:01 No XFR rail fitting work has done. 22.06.2017 132kV control building building: Window Drop wall has -Boundary wall: 40m plaster work has done.132kV S/Y:15 Nos base has done for equipment.33kV S/Y:100% cable trench soil excavation has done.XFR foundation:Beam cast has done for XFR. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 132kV control building building: First floor shuttering open work & Ground floor column plastering work has done.33kV CB building:Brick wall making done up to linten.Boundary wall: 25m plaster work & 25m coping casting has done.132kV S/Y:12 Nos equipment soil excavation done,09 Nos equipment base & column casting done.33kV S/Y:60m CC & base casting done for A type cable trench.XFR foundation: Pit wall casting done. | 13.07.2017 -No further update.
[7 empty] | Farid Ahmed |  | 1914454350 | - | - | Contract Date
[7 empty] | Ziaur |  | 1708453369 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
20 | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura | PGCB | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura Client - PGCB | 20.3 | NARAIL Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S | Enamul Haq 01708131702 Farid Ahmed 01914454350 Site Engr. Ruhulamin 01708453368 | Enamul Haq |  | 1708131702 | - | - | Deed Agreement | NARAIL Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S Project Manager Enamul Haq 01708131702 Farid Ahmed 01914454350 Site Engr. Ruhulamin 01708453368 | 27.10.2016 -Sand filling on going, 34,00,000 cft complete. 03.11.2016 Approximately 30 lacs cft (asper boat,count,without wastage calculation) sand filling complete,another 10 to 12 lacs cft of sand filling required.Water level is decreasing rapidly in canel,sand dredging can be continued for next 5 to 7 days,then we have to go for truck. 10.11.2016 -31400 cft Sand filling done.Leveling work going on. 17.11.2016 -leveling work running. 24.11.2016 -6 inch Dredging pipe installation going on.Land Leveling work complete of sub station area. 01.12.2016 -Finishing work going on in sand filling area. 08.12.2016 -Sand filling work 70% done. -Slope work is going on in west side area. 15.12.2016 -Sand filling at north end going on.Levelling and slope dressing is going on. 22.12.2016 -Sand filling work is going on. 29.12.2016 -Labor & Materials shed is making.Power connection has done at site .Installation work is going on for Submersible pump. 05.01.2017 -Materials shed,guard room,labor tin shed,wood fitting,soling & plasterworks, Water house (for pile) has completed. Generator room tin fitting works 90%,toilet tin & wood fitting and Boundary fencing briars,all room & out side electric cable wiring & light fittings 75%, Soil test work 80% has been completed. 12.01.2017 -Sand filling work is going on approx. 80000 cft. 19.01.2017 -46 Nos of pile casting work done for boundary.10 Nos footing & short column casting.in Ansar barrack.11 Nos CC ,Pile cap casting,GB casting in 33 Kv control building.09 Nos CC & pile cap casting for 132kV switch yard. -GB & 15 Nos short column work done for 132kV control building. 26.01.2017 -40nos pile work done. -2nos pile house for 132/33kV switch yard.33kV control building for 1 pile house. 33kv layout pile point costing. 1No labor water reserve house completed. 1nos cube querying work done.Road construction 12Nos for material carry done. 02.02.2017 -50 Nos pile casting work has done.80% brick wall has been done at office building. 09.02.2017 -Office building civil works has completed.83 Nos pile casting work has done. Labor shed,kitchen has make. 16.02.2017 -Pile work is going on for switchyard.Wall making work is running in Temporary office house.10 Nos CC work & 5 Nos column work has been done in 132kV control building.Rod binding & pile head broken work is going on. 23.02.2017 -36 Nos pile has done in 132kV Switchyard.28 Nos pile cap work done in 132kV control building.82 Nos pile head broken work has been done. 02.03.2017 -28/32 Nos pile cap casting at 132 kV switchyard.8/11 Nos pile cap casted load test complete at 132 kV switch yard.Grad beam casting completed at 132kV switch yard. 09.03.2017 -132kv control building : 30/32 now pile cap casting.Grade beam casting with out load test portion.30/32 now short column casting.4nos full column and 10nos first lift casting.Stair footing soil excavation and CC casting.Load test complete.33 kV building :11/11 numbers pile cap casting , grade beam casting without west side 3 pile 8/11 column casting . Stair column footing casting.132kV switch yard :22nos pile cap soil excavation, 18nos CC casting complete,12 Nos pile head backing complete -Load test complete . Boundary wall 73/104nos pile casting. 16.03.2017 -No update yet. 23.03.2017 -16 no column casting and Ground floor RCC casting work has been done.132/33 KV stairs first step 30.03.2017 -Boundary wall:50M grade beam & 20 Nos pile and 10 boundary column casting done.132 kV S/Y:13 Nos pile cap casting done. 132kV control building:2 Nos stair first lift casting done,beam shuttering done,slab shuttering running.33kV control building:stair first lift casting done,shuttering done. 06.04.2017 -Boundary wall:60M grade beam & 20 Nos boundary casting,200 sft brick wall work is making done.132 kV S/Y:19 Nos pile cap casting done.132kV control building:2 Nos stair first lift casting done,beam shuttering done,first floor slab shuttering,rod binding work has been done.33kV control building:stair first lift casting done,shuttering,rod binding has done. 13.04.2017 -132kV control building:Casting work is going on in first floor. 33kV control building: Casting work is going on in first floor.earth excavation work is going on.Boundary wall brick work,grade beam & pile cap work has been done. 20.04.2017 Boundary wall: 30Nos column,pile cap casting done. 40m brick wall work is making done.132 kV S/Y:16Nos pedestal column shuttering 7 ring ,tie binding work has been done.-33kV S/Y: Soil excavation work is going on.132kV control building:2No s stair first lift casting done,beam shuttering done,first floor slab shuttering ,rod binding work has been done. 33kV control building :stair first lift casting done,shuttering, rod binding has done. 27.04.2017 Boundary wall:18 Nos column,pile cap casting done. 45m grad beam & 50m brick wall work is making done.132 kV S/Y 12/88 Nos pedestal column shuttering work has been done.33kV S/Y: layout & 03 Nos base soil excavation done.132kV control building:25 No column first lift casting done, beam shuttering opening work has been done.33kV control building:11 Nos column casting & Ist floor out side beam shuttering open. 04.05.2017 Boundary wall:18 Nos column,pile cap casting done.45m grad beam & 50m brick wall work is making done.132 kV S/Y 12/88 Nos pedestal column shuttering work has been done.33kV S/Y: layout & 03 Nos base soil excavation done.132kV control building:25 No column first lift casting done,beam shuttering opening work has been done.33kV control building:11 Nos column casting & Ist floor out side beam shuttering open. 11.05.2017 Boundary wall:01 No column done.10m brick wall work is making done.132 kV S/Y:16/88 Nos pedestal column shuttering work has been done.33kV S/Y: 02 Nos base & 04 Nos gantry column casting done.132kV control building:27 No column 2nd lift casting done,internal Stair third lift casting done,33kV control building:External stair slab casting done. 18.05.2017 -132kV control building:11 Nos column 2nd lift casting done, total 27/27.ground floor slab shutter opening work completed,external stair slab cast & first floor slab cast work has done. 33kV control building: First floor slab casting,stair slab shuttering & rod binding and casting as been completed.XFR foundation:1st XFR 3 nos pile cap & overall base casting and 2nd XFR soil excavation has done.132 kV S/Y:12Nos pedestal column shuttering done.33kV S/Y:Layout &03 Nos base & gantry cast,01No gantry base macadam & CC casting has done. 25.05.2017 -XFR foundation work is continuing.Cable trench casting work is going on for 132kV & 33kV switchyard.Brick work & plaster work is continuing at 132kV & 33kV Control building first floor.Electrical & sanitary work is going on at Ansar barrack. 01.06.2017 02 Nos base slab casting in XFR foundation.Base & guide wall cast has been done at 33kV cable trench.CC & base cast has done at 132 kV switchyard.Brick work 7 plaster work has been done at 132kV & 33kV. Finishing work is going on at Ansar Barack. 08.06.2017 XFR foundation rail beam casting work is going on.132kV switchyard guide wall casting work is continuing.132kV & 33kV control building first floor in side wall plaster work is going on. 15.06.2017 132kV S/Y:cable trench base slab & guide wall casting.33 kV SY:earth back filling.132 & 33 kV CB:1st floor brickwork, plaster,drop wall casting. Ansar barrack floor curing &door fitting.Transformer rail beam & oil pit wall casting.Blast wall pile head break & cc casting. 22.06.2017 -Earth excavation work is going on at 33kV switchyard. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -Switchyard sand back filling & leveling work is going on at 33kv & 132 kv area.Rail beam (shuttering,rod binding) work has done for XFR foundation.Ballast wall shuttering work is going on. | 13.07.2017 -No further update.
[7 empty] | Farid Ahmed |  | 1914454350 | - | - | Contract Date
[7 empty] | Site Engr. Ruhulamin |  | 1708453368 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
20 | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura | PGCB | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura Client - PGCB | 20.4 | JHENAIDAHA Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S | Enamul Haq 01708131703 Farid Ahmed 01914454350 | Enamul Haq |  | 1708131703 | - | - | Deed Agreement | JHENAIDAHA Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S Project Manager Enamul Haq 01708131703 Farid Ahmed 01914454350 | 22.10.2016 Post work measurement done. lay out of 132 kV control room building done.lay out of 33kV control room building done. 132kV switchyard layout done. 33kV switchyard layout done. Soil test work done. 27.10.2016 Post work measurement of earth development work taken on 19th Oct'16.Substation layout given by total station on 20th Oct'16,Compection test of earth work done. 03.11.2016 -PGCB stopped all types of activities by mail as per world bank guide line, but we continue for labor and material shade construction. 10.11.2016 -Labor shed,metarials shed & main gate make. 17.11.2016 -Labor shed,Security room,Metarials shed are built. -Temporary Boundary wall built. 24.11.2016 -Pile work started at site. 01.12.2016 -21 Nos of pile completed in control building.Boundary wall work going on in office building area. 08.12.2016 -All (64 Nos) of the pile completed in control building. -08 Nos pile out of 48 Nos are completed in switchyard. 15.12.2016 -36 Nos pile out of 48 Nos of 32 Kv gantry complete.Earth Excavation for pile cap of 132 kV control building started. 22.12.2016 -Pile work is continuning for 33kV switchyard building. -Soil digging & civil work has been running.Office building tiles work is continued. 29.12.2016 -Soil digging work is running for pile cap in 132 kV control building.29 Nos out of 64 Nos pile head has broken. 05.01.2017 -Pile work has done in 132 kV & 33 kV switchyard. -13 Nos CC work has done of 132 kV control building. -15 Nos of pile cap casting work has done in control building. 12.01.2017 -Main gate has fixed at site. -Brick soling road is making from main road to site. 19.01.2017 -46 Nos of pile casting work done for boundary.10 Nos footing & short column casting.in Ansar barrack.11 Nos CC ,Pile cap casting,GB casting in 33 Kv control building.09 Nos CC & pile cap casting for 132kV switch yard. -GB & 15 Nos short column work done for 132kV control building 26.01.2016 132 kV control building : 14nos column casting done.132kV switch yard : 02nos CC + Pile cap casting.33kV control building : 05nos column casting done.Ansar barrack: 10nos column casting done. Boundary pile: 60nos pile casting. 02.02.2017 -Pile load has been tested in 132 kV control building & switch yard.60nos pile cap casting for boundary wall. 09.02.2017 -01 No pile cap gb & column casting done in 132kV control building.60 Nos pile cap & 40m GB and 40 Nos column casting work has done. 16.02.2017 -01 No stair & ground floor casting & first floor beam shuttering work has been done in 132 kV control building.95 Nos pile cap casting,340 meter’s grade beam casting & 70 Nos column casting,300 meter’s brick work has been done. 23..02.2017 -stair 2nd lift shuttering & first floor beam & slab shuttering work has been done in 33 kV control building.Boundary wall 62 Nos pile cap casting,48 m grade beam casting & 40 Nos column casting,70 m brick work has been done. 02.03.2017 -33 kV control building:Stair 2nd lift casting & first floor beam & slab rod binding,Ansar barrack roof slab rod binding has been done.Boundary wall:total brick work done,03 Side plaster work has been done.132 kV control building :External stair final flight casting work,Ist floor shuttering & slab rod binding work has been done. 09.03.2017 -132 kV control building:Ist floor slab casting done. -33 kV control building-:Ist floor slab casting done.Column Ist & 2nd lift casting done for roof floor.-Ansar barrack:Roof slab casting work has done. 16.03.2017 -All column casting done for 2nd floor,Stair roof slab shuttering & rod binding done,boundary wall north side plaster done,33kV S/Y layout, excavation & CC work done. 23.03.2017 -132 kV control building:-External stair roof slab & internal stair third flight casting done,33 KV control building;- Stair roof slab casting done,33 kV Switch yard:-18 Nos gantry tower base casting done, 30.03.2017 -132 kV control building:-Shuttering work is going on for roof slab.33 KV control building;- Shuttering work is going on.Ansar barrack :Brick work & plaster work is going on. 06.04.2017 -132 kV control building:-Brick work,silling work,Shuttering work is going on for roof slab.Lenten casting done.33 KV control building;-Rod binding & Shuttering work is going on.Ansar barrack :Brick work & linten work is going on. 13.04.2017 -132 kV Control Building:-Roof slab casting has been done.33 KV Control Building;Roof slab casting has been done.Ansar barrack: Brick work is going on.33kV Switch yard: Gantry foundation casting has been completed. 20.04.2017 -132 kV Control Building:-Curing on going.33 KV Control Building: Curing on going.Ansar barrack : Plaster work is going on. 132kV/33kV Switch yard: Equipment foundation casting on going. 27.04.2017 -132 kV Control Building:-Second floor Roof slab Curing on going.33 KV Control Building: Second floor Roof slab Curing on going.Ansar barrack : Plaster work is continuing.132kV/33kV Switch yard: Equipment foundation casting on going.Blast wall & XFR pile work has been done. 04.05.2017 -132 kV & 33 KV Control Building: Roof slab Curing is continuing.132kV/33kV S/Y: Equipment foundation casting work is going on.Blast wall & XFR foundation pile work is continuing. 11.05.2017 -Equipment foundation work has been done for 32kV switchyard. 18.05.2017 XFR foundation work on going.Cable trench work is going on for 132kV & 33kV switchyard. Brick work is continuing at 132kV & 33kV Control building. 25.05.2017 to 08.06.2017 -No further update. 15.06.2017 Magura-2 bay gravel & brick soling removing has been completed.10 Nos foundation base earth excavation done. 06 Nos foundation base casting has been done. completed.Earth excavation work is going on. 22.06.2017 -Earth excavation work is going on. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -Cable trench base,guide,cover slab work is going on. | 13.07.2017 -Cable trench base, guide, cover slab work has been completed.
[7 empty] | Farid Ahmed |  | 1914454350 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
20 | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura | PGCB | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura Client - PGCB | 20.5 | MAGURA Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S | Enamul Haq 01708131704 Farid Ahmed 01914454350 SAE alamin-01799997296 | Enamul Haq |  | 1708131704 | - | - | Deed Agreement | MAGURA Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S Project Manager Enamul Haq 01708131704 Farid Ahmed 01914454350 SAE alamin-01799997296 | 22.10.2016 -Approved of GA & GTP Continued (40% done) 27.10.2016 to 16.03.2017 23.03.2017 -Soil excavation work is going on. -Wait for Anchor bolt for work. 30.03.2017 Soil excavation work is going on. 06.04.2017 Soil excavation work is going on.CC work is going on for LA,IVT,CT. 13.04.2017 JENAIDHA-1 BAY:Bay casting & column casting is continuing.JENAIDHA-2 BAY:Brick soling remove work has been done. NORAIL-2 BAY: Earth excavation work is going on 20.04.2017 -JENAIDHA-1 BAY:Bay casting & column casting has been finished. JENAIDHA-2 BAY:Cc casting & earth excavation work is going on.NORAIL-2 BAY:Base casting work has been completed, Column casting work is going on. 27.04.2017 -NORAIL-2 BAY:Base casting work has been completed, Column casting work has been completed.JENAIDHA-2 BAY:Cc casting & earth excavation work has been completed. 04.05.2017 -JENAIDHA-2 BAY: All Column casting work has been completed. 11.05.2017 -Earth excavation work has been done for Cable trench at JENAIDHA-1 BAY & JENAIDHA-2 BAY.CC work has been done at JENAIDHA -2 BAY.Rod binding & shuttering work at JENAIDHA -2 BAY site. Cable trench bas casting at JENAIDHA-2 BAY site. 18.05.2017 Base casting has been completed at JENAIDHA-1 bay area.Earth excavation & CC casting work has been done at Norail-2 Bay site. 25.05.2017 -Shuttering & Rod binding work has been completed at Norail-2 Bay site.Cable trench one side shuttering work has been done at JENAIDHA-1 bay area. 01.06.2017 -Base casting & shuttering work has been completed at Norail-2 Bay. 08.06.2017 -Guide wall casting work & back filling work has been completed at Norail-2 Bay. 15.06.2017 06.07.2017 -No further update. | 13.07.2017 -No further update.
[7 empty] | Farid Ahmed |  | 1914454350 | - | - | Contract Date
[7 empty] | SAE alamin- |  | 1799997296 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
21 | JICA PKG 3 Plant Design Supply, Installation of JICA Pakage 3 132/33kV S/S at BHALUKA , Mymensiing , Baroirhat and Ramganj on Turnkey Basis | PGCB | JICA PKG 3 Plant Design Supply, Installation of JICA Pakage 3 132/33kV S/S at BHALUKA , Mymensiing , Baroirhat and Ramganj on Turnkey Basis Client - PGCB | 21.1 | BHALUKA 132 / 33KV Substation | Kh Belal Hossain 01730075384 Mr Pratik Roy 01717338637 | Kh Belal Hossain |  | 1730075384 | - | - | Deed Agreement | BHALUKA 132 / 33KV Substation Project Manager Kh Belal Hossain 01730075384 Mr Pratik Roy 01717338637 | Panel layout, SLD, GA, GTP, Bore-Hole design and DS of 132 & 33kV approved. CT-33kV approved Land sloping of 3 sides from 4 of the sides has been done. Sectional drawing approved,civil design is ready. -subsoil investigation done. 18.10.2016 -No further upgrade 22.10.2016 -Approval of GT & GTP CONTINUED (40%) DONE. 27.10.2016 TO 16.03.2017 -No further update. 23.03.2017 -Soil excavation work is going on.Wait for Anchor bolt for work. 30.03.2017 Soil excavation work is going on. 06.04.2017 Soil excavation work is going on.CC work is going on for LA,IVT,CT. 13.04.2017 JENAIDHA-1 BAY:Bay casting & column casting is continuing.JENAIDHA-2 BAY:Brick soling remove work has been done. NORAIL-1 BAY:Earth excavation work is going on. 20.04.2017 -JENAIDHA-1 BAY:Bay casting & column casting has been finished. JENAIDHA-2 BAY:Cc casting & earth excavation work is going on.NORAIL-2 BAY:Base casting work has been completed,Column casting work is going on. 27.04.2017 -NORAIL-2 BAY:Base casting work has been completed, Column casting work has been completed. JENAIDHA-2 BAY:Cc casting & earth excavation work has been completed. 04.05.2017 -JENAIDHA-2 BAY:All Column casting work has been completed. 11.05.2017 -Earth excavation work has been done for Cable trench at JENAIDHA-1 BAY & JENAIDHA-2 BAY.CC work has been done at JENAIDHA-2 BAY.Rod binding & shuttering work at JENAIDHA-2 BAY site.Cable trench bas casting at JENAIDHA-2 BAY site. 18.05.2017 Base casting has been completed at JENAIDHA-1 bay area.Earth excavation & CC casting work has been done at Norail-2 Bay site. 25.05.2017 -Earth cutting for Pile CC work is going on.5 nos. of Pile CC has been completed. 01.06.2017 -Soil excavation work is continuing for Pile.Back filling work is going on at pond area. 08.06.2017 10 Nos pile has been done for 32kv gantry tower.House making work & sand filling work is continuing at control building area. 15.06.2017 20 nos. of pile casting work has been completed for 132kV Gantry Tower.90% Earth filling has been completed & Compaction work is continuing. 22.06.2017 -30 Nos of pile casting work has been completed for 132kV Gantry Tower. -90% Earth filling has been completed and Compaction work is continuing. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -04 Nos Rig is running for pile work. | 13.07.2017 -Pile work is going on.
[7 empty] | Mr Pratik Roy |  | 1717338637 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
21 | JICA PKG 3 Plant Design Supply, Installation of JICA Pakage 3 132/33kV S/S at BHALUKA , Mymensing , Baroirhat and Ramganj on Turnkey Basis | PGCB | JICA PKG 3 Plant Design Supply, Installation of JICA Pakage 3 132/33kV S/S at BHALUKA , Mymensing , Baroirhat and Ramganj on Turnkey Basis Client - PGCB | 21.2 | MYMENSINGH 132 / 33KV Substation | Kh Belal Hossain 01730075384 Mr Pratik Roy 01717338637 | Kh Belal Hossain |  | 1730075384 | - | - | Deed Agreement | MYMENSINGH 132 / 33KV Substation Project Manager Kh Belal Hossain 01730075384 Mr Pratik Roy 01717338637 | Sand filling done approximately 3500000 cft. 27.102016 -Land not yet handover. 03.11.2016 -Land Handover is not done yet. 10.11.2016 -Site hand over done. 17.11.2016 -Land Handover not done yet properly. 24.11.2016 -No update. 01.12.2016 -Officially been handed over -Tree cutting and cleaning is going on.Soil test and pre-section within a week. 08.12.2016 -Preparation work is going on for pre-section. 15.12.2016 -Pre Sectional work is over. 22.12.2016 -Lay out work is going on. 29.12.2016 -Land dispute is going on, so work is stopped. 05.01.2017 -Land dispute is going on, Created by landowner. -Sand fill contract goes to two(02)Nos of contractor. (05 janu,17). 12.01.2017 -Work has stopped still now. 19.01.2017 -Land disputes are going on. 26.01.2017 Earth filling has been started. 3% (1lakh. Cft.) soil filling has been done. 02.02.2017 -Sand filling works has been done approx. 6%. 09.02.2017 -Sand filling works has been done approx. 7%. 16.02.2017 -Sand filling works has been done approx. 10%. 23.02.2017 -Sand filling works has been done approx. 18%. 02.03.2017 -Sand filling works has been done approx. 21%. 09.03.2017 -Earth excavation work is going on. 16.03.2017 -50 % Earth excavation work has been done. 23.03.2017 -90319 cft Earth excavation work has been done by Arosh Enterprise.274949 cft Earth excavation work has been done by Ms Khan Enterprise. 30.03.2017 -13,96,879 cft Earth excavation work has been done by Arosh Enterprise. -8,81,022 cft Earth excavation work has been done by Ms Khan Enterprise. 06.04.2017 -No further update. 13.04.2017 -Soil compact work has been done. 20.04.2017 Earth filling has been Completed.Soil test or Borehole soil compaction test will going on from 21 April,17 27.04.2017 -Earth filling has been completed and Compaction work is going on. 04.05.2017 -Compaction & rolling work is going on. 11.05.2017 -Compaction & rolling work is continuing. 18.05.2017 -Earth filling has been completed and Compaction work is continuing. Materials for the fencing work are supplying to the site. 25.05.2017 Earth filling has been completed and Compaction work is continuing.Layout of the 132 kV gantry tower and 33 kV gantry tower has been completed.3 Nos of Rigs for piling works are supplied by M. A. Hashem Enterprise and preparation of piling work is going on. 01.06.2017 -06 Nos Base casting has been completed.06 Nos equipment earth excavation has been done. 08.06.2017 14 Nos Base casting has been completed for equipment. 15.06.2017 18 nos. of base casting has been completed for the 132 kV gantry tower.4 nos. of Column casting with anchor bolt fittings has been completed. 22.06.2017 -18 Nos of base casting has been completed for the 132 kV gantry tower. 15 Nos of Column casting with anchor bolt fittings has been completed.Tower structure has been mobilized at site. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -22 Nos column with base has been completed. | 13.07.2017 -04 Nos column with base has been completed.
[7 empty] | Mr Pratik Roy |  | 1717338637 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
21 | JICA PKG 3 Plant Design Supply, Installation of JICA Pakage 3 132/33kV S/S at BHALUKA , Mymensing , Baroirhat and Ramganj on Turnkey Basis | PGCB | JICA PKG 3 Plant Design Supply, Installation of JICA Pakage 3 132/33kV S/S at BHALUKA , Mymensing , Baroirhat and Ramganj on Turnkey Basis | 21.3 | BAROIRHAT 132 / 33KV Substation | Kh Belal Hossain 01730075384 Mr Pratik Roy 01717338637 | Kh Belal Hossain |  | 1730075384 | - | - | Deed Agreement | BAROIRHAT 132 / 33KV Substation Project Manager Kh Belal Hossain 01730075384 Mr Pratik Roy 01717338637 | Civil works completed 55%.pile head broken is stopped.PLI on foundation bolt is pending. 27.10.2016 Soil resistivity measurement done, Anchor bolt PLI.Civil works will be start at 31 oct,2016. 03.11.2016 -Anchor bolt PLI has been completed.sand,stone, rod is supplying to site. 10.11.2016 -Tower's Base & Column casting work going on. 17.11.2016 -Tower's Base & Column casting work 80% done. 24.11.2016 -Tower's Base & Column casting work 100% done. 01.12.2016 -Substation cleaning and soil cutting is going on (excess soil removal). 08.12.2016 -Soil excavation for equipment foundation is going on. 15.12.2016 22.12.2016 -No further update. 29.12.2016 -Soil excavation work has hold by PGCB GRID people. 05.01.2017 -Land excavation has been stop till now. 12.01.2017 -No further update. 19.01.2017 -Earth excavation is going on.Land disputes are going on. 26.01.2017 -Earth excavation is going on.Land dispute is going on. 02.02.2017 09.02.2017 -No further update. 16.02.2017 -No further update. 23.02.2017 -No further update. 02.03.2017 -No further update. 09.03.2017 -Soil excavation work is going on. 16.03.2017 -Equipment foundation construction preparation work is going on. 23.03.2017 to 06.04.2017 -No further update. 13.04.2017 -Temporary shed repairing work has been done. 20.04.2017 27.04.2017 -No further update. 04.05.2017 -350 bag’s cement arrive at site.Tower base layout drawing has been prepared. 11.05.2017 -Material supply work is going on.Tower base layout drawing work is going on for approval. 18.05.2017 -Work will be start very soon. 25.05.2017 -For control building, 50% Grade beam casting work has been completed and else is going on.For 132 kV Gantry Tower, All (29 nos.) column casting with anchor bolt fittings has been completed.21 nos of equipment foundation has been completed and else is going on for 132kV gantry. XFR foundation Pile Cap (Base) work has been completed. 01.06.2017 20 Nos base cast has been done for equipment foundation.Total grade beam work has been completed at control building. 08.06.2017 Rod binding for column at control building.Wall casting work has been done at XFR.Equipment foundation casting work has been completed. Short & long column casting work has been done at control building. 15.06.2017 For control building, 1st Floor Slab casting will be held on 22,june,2017. 36 nos. of equipment foundation base has been completed and else is going on for 132kV gantry Tower.Transformer foundation Pile Cap and base work has been completed. 22.06.2017 For control building, preparation for 1st Floor Slab casting is going on.36 nos. of equipment foundation base has been completed and else is going on for 132kV gantry Tower.Transformer foundation Pile Cap and base work has been completed. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -No further update, | 13.07.2017 -Base & column cast work has been completed at switchyard.33kv Base foundation has done. Column/rebar work is going on at control building.
[7 empty] | Mr Pratik Roy |  | 1717338637 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
21 | JICA PKG 3 Plant Design Supply, Installation of JICA Pakage 3 132/33kV S/S at BHALUKA , Mymensing , Baroirhat and Ramganj on Turnkey Basis | PGCB | JICA PKG 3 Plant Design Supply, Installation of JICA Pakage 3 132/33kV S/S at BHALUKA , Mymensing , Baroirhat and Ramganj on Turnkey Basis Client - PGCB | 21.4 | RAMGANJ 132 / 33KV Substation | Kh Belal Hossain 01730075384 Mr Pratik Roy 01717338637 | Kh Belal Hossain |  | 1730075384 | - | - | Deed Agreement | RAMGANJ 132 / 33KV Substation Project Manager Kh Belal Hossain 01730075384 Mr Pratik Roy 01717338637 | ………………. -Sand filling done approximately 350000 cft. -pump sinking. 27.10.2016 Site mobilization start.Pump motor (2hp) installed now work stop for local Mayor. 03.11.2016 -Due to land disputes, Stoppage of work is going on. 10.11.2016 -Land dispute is going on with MAYOR. 17.11.2016 01.12.2016 -No further update. 08.12.2016 -Dismantling work done for existing building. 15.12.2016 -One existing building had broken already. 22.12.2016 -preparation work is running for pile. 29.12.2016 -Pile construction work has been started. 05.01.2017 -08 Nos pile work has been done for tower foundation. 12.01.2017 -22 Nos pile work has been done for tower foundation. 19.01.2017 -52 Nos pile work has been done for tower foundation. 26.01.2017 -92nos pile out of 116 have been done for tower foundation. 02.02.2017 -114 Nos pile out of 114 have been done for tower foundation.04 Nos pile out of 64 Nos have been done for control building. 09.02.2017 -39 Nos pile out of 64 Nos have been done for control building. 16.02.2017 -64 Nos pile out of 64 Nos have been done for control building. 23.02.2017 -16 Nos pile out of 16 Nos have been done for XFR. 02.03.2017 -Blast wall pile done 5 out of 5. 09.03.2017 -Pile load test preparation work has been done. -Gantry tower,base foundation ,pile head broken work has been done. 16.03.2017 -Pile load test has been done. 23.03.2017 -Pile cap work is going on for gantry tower.20 Nos CC work done at control building.Soil excavation work done for XFR. 30.03.2017 -CC work done in control building.Creeker done for column. 06.04.2017 -CC work done in 2Nos XFR.Creeker work is going on for gantry tower. 13.04.2017 -Base foundation/pile cap work has been done at 01 no XFR.02 Nos gantry tower has been completed. 20.04.2017 -2 Nos.of pile cap work has been completed for control building.All base foundation/pile cap has been completed and 07 Nos.of column has been completed. .XFR foundation Pile CC work is also going on and 01 no of pile CC is completed. 27.04.2017 13 Nos of Pile Cap work has been completed for control building.11 Nos of column and Anchor bolt fittings has been completed and else going on for Gantry Tower.XFR foundation Pile CC work has been done & preparing for Pile Cap. 04.05.2017 -09 Nos of Pile Cap work has been completed for control building.03 Nos of column and Anchor bolt fittings has been completed and else going on for Gantry Tower.XFR1 rod binding work has been done. 11.05.2017 -Pile cap work has been completed for control building.19 Nos column and anchor bolt fittings has been completed for gantry tower. Transformer base has been completed. 18.05.2017 For control building, Grade beam shuttering and casting work is going on.For Gantry Tower,27 Nos.of column casting with anchor bolt fittings has been completed and else going on. Transformer foundation Pile Cap(Base) work has been completed. 25.05.2017 -In the Control Building, All (32 nos.) Column has been completed and stair casting work preparation is going on. In the 132kV Gantry Tower, 10 nos. of Tower column has been completed with Anchor Bolt fittings.33kV gantry Tower, 6 nos. of tower has been completed. 01.06.2017 -10 Nos gantry tower’s all civil works has been finished at 33kV site.24 Nos gantry tower’s all civil works has been finished at 132kV site. 08.06.2017 Equipment soil excavation & CC casting work is continuing.33 kV gantry tower civil works has been completed.XFR pile head broken work has started. 15.06.2017 In the Control Building, 1st Floor slab casting will be held on 19.06.2017.In the 132kV Gantry Tower, 69 nos. of equipment foundation CC works has been completed. Transformer and Blast wall earth excavation and pile CC work is going on. 22.06.2017 -In the Control Building, 1st Floor slab casting has been done on In the 132kV Gantry Tower, -All equipment foundation CC works has been completed. -Transformer and Blast wall earth excavation and pile head break has been done. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -15 Nos Base casting has done for equipment.18 Nos column has done for control building at first floor. | 13.07.2017 -All column work has been completed at control building.26 Nos base cast work has been done 132kV equipment site.02 XFR CC work has been done.
[7 empty] | Mr Pratik Roy |  | 1717338637 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
22 | JICA PKG 4 EPC for Jaldhaka & Mohastangor; Bay extension at Saiedpur & Barisal | PGCB | JICA PKG 4 EPC for Jaldhaka & Mohastangor; Bay extension at Saiedpur & Barisal Client - PGCB | 22.1 | Jaldhaka | Jaldhaka Project Co-ordinator Md Abdul Khaleque 01712204871 Dilip,Sae- 01708131729 | Md Abdul Khaleque | Jaldhaka Project Co-ordinator | 1712204871 | - | - | Deed Agreement | Jaldhaka Project Manager Jaldhaka Project Co-ordinator Md Abdul Khaleque 01712204871 Dilip,Sae- 01708131729 | ……………… -Sand filling done 49%. 27.10.2016 -from 14.10 to till date work stop, tomorrow will be meeting then work will be start. 03.112016 filling has been started from 31.10.2016, 54% filling has been completed. 10.11.2016 -Sand filling 60% done. 17.11.2016 -Sand filling 70% done. 24.11.2016 -Sand filling 70% done. -Soil test has been completed. 01.12.2016 -Soil test and pre-section measurement done. 08.12.2016 -90% sand filling work done. -Site office installation preparation work is going on. 15.12.2016 93% sand filling work done.Site Office construction is going on. 22.12.2016 -Lay out work is going on. -Site office, labor shed, sanitation work is going on. 29.12.2016 -93% sand filling work has been done.Materials shed & Labor shed making is going on. 05.01.2017 -Submersible pump has installed.Materials shed & Labor shed making is going on.Mobilization work has started for pile instrument. -95% sand filling work has been done. 12.01.2017 -96% filling work has done. -Materials shed & Labor shed making has finished. 19.01.2017 -99% filling work has done. 26.01.2017 -100% filling work has been done.Control building pile-30Nos done. 02.02.2017 -30Nos pile has done at Control building. 09.02.2017 -64 Nos pile has done at Control building.30 Nos out of 116 Nos pile has been completed at Gantry tower. 16.02.2017 -58 Nos out of 116 Nos pile has been completed at Gantry tower. 23.02.2017 -80 Nos out of 116 Nos pile has been completed at Gantry tower. 02.03.2017 -95 Nos out of 120 Nos pile has been completed at Gantry tower. 09.03.2017 -Pile work has done for gantry tower and transformer. 16.03.2017 -112 Nos out of 120 Nos pile has been completed at Gantry tower.9 Nos out of 21Nos pile has been completed at XFR. 23.03.2017 -120 Nos out of 120 Nos pile has been completed at Gantry tower.21 Nos out of 21Nos pile has been completed at XFR.All pile head cap broken at control building. 30.03.2017 -10 Nos rod binding has done for base.CC complete for control building.10 Nos CC has been completed for gantry tower. 06.04.2017 -Rod binding work is going on for gantry & Control building.16 Nos pile work has been complete for control building.27/30 Nos head broken work has been completed for gantry tower. 13.04.2017 -08 Nos pile work has been complete for control building.10 Nos base foundation/pile cap has been completed. 20.04.2017 32 Nos. (All) of Pile Cap work has been complete for Control building and Grade Beam Rod binding work is going On.17 Nos base foundation/pile cap has been completed.33kV gantry Tower earth excavation work is also going on. 27.04.2017 -50% Grade Beam casting work has been completed and going on the else for the Control Building.All (30 nos.) base foundation/pile cap work has been completed and preparing for the Anchor Bolt fittings.2 nos. of 33kV gantry Tower Pile CC work has been completed and else going on. 04.05.2017 -44082 ft Grade Beam casting work has been completed.18 Nos of 33kV gantry Tower Pile CC work has been completed. 11.05.2017 -Column casting work is going on for the control building.33kV gantry tower base has been completed. 132kV gantry tower column and anchor bolt fittings work is going on. 18.05.2017 In the Control Building, 19 nos. of Column has been completed and else Column casting work is going on.In the 132kV Gantry Tower,16 nos of Column has been completed with Anchor Bolt fittings.33kV gantry Tower base foundation has been completed and shuttering for column and template fittings work is going on. 25.05.2017 50 m long grade beam work has done.08 Nos column has been completed for Gantry tower base.Rebar work for Column in Control building.06 Nos shuttering work has done for roof column at first floor in control building.18 Nos cracker work for column at control building.20 Nos pile cap has been cast. 01.06.2017 First floor column casting going on.Boundary wall pile cap casting 120 nos.completed out of 220 & grade beam casting going on (125 meter completed)Gantry Tower pile cap casting 17 nos. completed out of 30 Nos.& Gantry Tower short column casting going on. 08.06.2017 70m grade beam,Gantry tower column 04 Nos.10 Nos boundary bass.Star casting & roof saturating processing work is continuing. 15.06.2017 10m long grade beam cast work has been done.20 Nos base casting done for boundary.01 No bass cast has done for gantry. Rod placing work is going on for beam. 22.06.2017 -10m grade beam cast has done. -Rod binding work has done for Roof. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -12 Nos pile cap casting has done for boundary wall.10m long Grade beam casting has done. | 13.07.2017 -02 Nos pile cap casting has done for boundary wall.20m long Grade beam casting has done. 10 Nos column casting has done for boundary wall.08 Nos gantry base column work has been completed.
[7 empty] | Dilip,Sae- |  | 1708131729 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
22 | JICA PKG 4 EPC for Jaldhaka & Mohastangor; Bay extension at Saiedpur & Barisal | PGCB | JICA PKG 4 EPC for Jaldhaka & Mohastangor; Bay extension at Saiedpur & Barisal Client - PGCB | 22.2 | Mohasthangor | Mohastangor Project Coordinator Md Abdul Khaleque 01712204871 Fulon- 01713608774 |  |  |  | - | - | Deed Agreement | Mohasthangor Project Manager Mohastangor Project Coordinator Md Abdul Khaleque 01712204871 Fulon- 01713608774 | 27.10.2016 -Civil Design & Drawing is going on.Sand filling is going on & 92% Completed.Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned person.Waiting to receive GTP & Drawing.Soil Test is going on. 03.11.2016 Soil Test has been done.Sand filling is going on & 97% Completed.Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned person.Waiting to receive GTP & Drawing.Civil Design & Drawing is going on. 10.11.2016 -Earth filling completed. -Transformer & DS drawing received. 17.11.2016 -Soil Test Completed. -site office is under construction. -Site Construction material rate is under negotiation. 24.11.2016 -No update. 01.12.2016 -Site Office & Labor shade work is going on. 08.12.2016 -GTP & Drawing of DS ES, Search Eristor and Circuit breaker’s submitted to PGCB for approval. -Site Office making work is going on. -Labor shade work completed. 15.12.2016 -GTP & Drawing of DS ES, Search Eristor and Circuit breaker’s submitted to PGCB for approval it’s processing going on.Site Office construction is going on.Piling has started for control building. 22.12.2016 -Pile has been done 22 Nos out of 152 Nos. 29.12.2016 -93% sand filling work has been done.Materials shed & Labor shed making is going on. 05.01.2017 -Piling is going on and 63 nos. Completed out of 152 nos. 12.01.2017 -Design submitted for approval to PGCB for CB & LA.Piling is going on and 90 Nos. Completed out of 152 Nos. 19.01.2017 -Got Approval GTP & GA of LA & 132 KV CB.GTP & GA of DS/ES submitted for approval to PGCB.Piling is going on and 112 Nos. completed out of 152 Nos. 26.01.2017 -GTP & GA of Conductor submitted for approval to PGCB.Control building piling has been completed.Gantry Tower piling is going on & 61 nos. completed out of 88 nos. 02.02.2017 -Got approval GTP & GA of 132 KVA DS/ES.GTP & GA of CT, IVT & 33 KV.GCB submitted for approval to PGCB.Control building piling is completed. Gantry Tower piling is going on & 76 nos. completed out of 88 nos. 09.02.2017 -Gantry Tower piling is going on & 82 nos. completed out of 88 nos. 16.02.2017 -Got approval GTP & GA of Auxiliary Transformer from PGCB.Control building piling is completed. Gantry Tower piling is going on & 86 nos. completed out of 88 nos. 23.02.2017 Pile load test for Control Building has been done.All Pile head broken. 02.03.2017 -Control building pile cap casting going on (15 Nos completed out of 32 Nos). 09.03.2017 -Control building pile cap casting completed & Grade beam casting going on. -Boundary wall Piling going on. 16.03.2017 -Boundary Pile 47 Nos out of 217 are complete. 23.03.2017 -98 Nos pile of boundary wall. 30.03.2017 -117 Nos pile has been done of boundary wall.14Nos grade beam casting has been done of control building. 06.04.2017 -115/220 Nos pile has been done of boundary wall.All Grade beam casting has been done of control building. 13.04.2017 -220/220 Nos pile has been done of boundary wall.50 Nos pile head broken work has been done for boundary wall.10 Nos CC casting has been completed for Gantry tower.12 Nos pile broken done for Gantry tower. 20.04.2017 -20 Nos pile base done for boundary.04 Nos Gantry base done.20 Nos pile work has been done for XFR.Shuttering work has been done in 1st floor roof &stair.150 Nos pile head broken work has been done.All column works has been done in Control building. 27.04.2017 -04 Nos Gantry tower base has done.30 Nos Pile cap casting work has been done for boundary wall.06 Nos pile casting work has been done for XFR.90% Shuttering work has been done in 1st floor roof. 04.05.2017 -03 Nos Gantry tower base has done.30 Nos Pile cap casting work has been done for boundary wall.03 Nos pile casting work has been done for gantry tower.100% Shuttering work has been done in 1st floor roof. 11.05.2017 -Rod binding work has been completed for pile cap.02 Nos stairs casting work has been completed. 18.05.2017 -First roof casting work has been completed.15 Nos pile cap casting has been done. 25.05.2017 -XFR & blast wall pile 16 Nos has been completed out of 16 Nos.Control room pile cap 08 Nos has been completed out of 32 No. 01.06.2017 -Control building pile cap casting going on. (14 nos. completed out of 32 nos.)Boundary wall pile head breaking going on.Gantry tower pile head breaking going on. 08.06.2017 32 Nos out of 32 Nos pile cap has been completed at control building. Grade beam reinforcement banding work is continuing.05 Nos out of 206 Nos pile cap has been completed at control building. 15.06.2017 Control building grade beam casting 25% done.10 Nos Boundary wall pile cap casting done with 22 Nos reinforcement banding continue out of 206 Nos. 22.06.2017 -Control building grade beam casting 100% done.56 Nos out of 206 Nos pile cap with beam casting has been completed. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -07 Nos boundary column casting has done.13 Nos pile cap casting has done up to beam. | 13.07.2017 Control building short column-32 nos. Long Column -06 nos. Boundary wall- pile cap-187nos out of 206nos . Grade beam 151nos. Column 90nos. Brick work-40gap.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
22 | JICA PKG 4 EPC for Jaldhaka & Mohastangor; Bay extension at Saiedpur & Barisal | PGCB | JICA PKG 4 EPC for Jaldhaka & Mohastangor; Bay extension at Saiedpur & Barisal Client - PGCB | 22.3 | Saidpur | Saidpur Project Coordinator Md Abdul Khaleque 01712204871 Dilip,SAE-01708131729 | Md Abdul Khaleque | Saidpur Project Coordinator | 1712204871 | - | - | Deed Agreement | Saidpur Project Manager Saidpur Project Coordinator Md Abdul Khaleque 01712204871 Dilip,SAE-01708131729 | 30.10.2016 Civil Design & Drawing is going on.Sand filling is going on & 45% Completed (Apx.).Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned person.Waiting to receive GTP & Drawing. 03.11.2016 Civil Design & Drawing is going on.Sand filling is going on & 48% Completed (Apx.),Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned person.Waiting to receive GTP & Drawing. 10.11.2016 -Earth filling complete 50%. -Transformer & DS drawing received. 17.11.2016 -Earth Filling Progress is 52%. 24.11.2016 -Earth Filling Progress is 57%. 01.12.2016 -Earth Filling Progress is 62%. 08.12.2016 -GTP & Drawing of DS ES, Surge arrester and Circuit breaker’s submitted to PGCB for approval.Earth Filling Progress is 67%. 15.12.2016 -Earth Filling Progress is 70%. 22.12.2016 -Earth Filling Progress is 72%. 29.12.2016 -Pile has been done 40 Nos out of 152 Nos. 05.01.2017 -Earth Filling is going on and 75% Completed. 12.01.2017 -Design submitted for approval to PGCB for CB & LA.Earth Filling is going on and 77% Completed. 19.01.2017 -Got Approval GTP & GA of LA & 132 KV CB.GTP & GA of DS/ES submitted for approval to PGCB.Earth Filling is going on. 26.01.2017 -GTP & GA of Conductor submitted for approval to PGCB.Sand Filling is going on. 02.02.2017 -Got approval GTP & GA of 132 KVA DS/ES.GTP & GA of CT, IVT & 33 KV GCB submitted for approval to PGCB.Sand Filling is going on & 83% Completed (Apx.) 09.02.2017 -As same as before. 16.02.2017 -Got approval GTP & GA of Auxiliary Transformer from PGCB.Soil Compaction Test Completed.Soil Test going on. 23.02.2017 -Soil test & soil compaction test has been done. 02.03.2017 -Labor Shade and Site Office Construction is going on. 09.03.2017 -Labor Shade and Site Office Construction is going on. 16.03.2017 -Labor shed & house are complete. 23.03.2017 -Pile 19 Nos out of 64 are complete.Gantry tower Pile 06 Nos out of 120 are complete. 30.03.2017 -Pile 37 Nos out of 64 are complete.Gantry tower Pile 15 Nos out of 120 are complete. 06.04.2017 -Pile 54 Nos out of 64 are complete.Gantry tower Pile 29 Nos out of 120 are complete.12/205 Nos pile has been done of boundary wall. 13.04.2017 -Pile 64 Nos out of 64 are complete in control building. Gantry tower Pile 39 Nos out of 120 are complete.39/205 Nos pile has been done of boundary wall. 20.04.2017 -39 Nos out of 120 Pile has been complete in Gantry tower.71/206 Nos pile has been done of boundary wall. 27.04.2017 -78 Nos out of 120 Pile has been complete in Gantry tower.103/206 Nos pile has been done of boundary wall. 04.05.2017 -98 Nos out of 120 Pile has been complete in Gantry tower.138/206 Nos pile has been done of boundary wall. 11.05.2017 -18 Nos Pile has been complete in Gantry tower.60 Nos pile has been done of boundary wall. 18.05.2017 -04 Nos Pile has been complete in Gantry tower. 08 Nos pile has been done of boundary wall.05 Nos out of 16 Nos pile has been done at XFR.03 Nos pile cap has completed at control building. 25.05.2017 -Same as before. 01.06.2017 -Gantry tower pile head breaking going on. 08.06.2017 Earth excavation and Pile head broken work has been done.Pre parathion work is going on for CC casting. 15.06.2017 04 Nos gantry tower base CC work has been done.Preparation work has been completed for gantry base,Rod binding & cutting.20m long grade beam & 10 Nos boundary bass casting work has been completed.3rd steps stair shuttering & cast done.Stair column & stair four slab casting done.2nd roof shuttering done. 22.06.2017 -04 Nos gantry base casting has been completed. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -04 Nos column casting has done at gantry tower base. | 13.07.2017 -02 Nos gantry base column casting has done.
[7 empty] | Dilip,SAE- |  | 1708131729 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
22 | JICA PKG 4 EPC for Jaldhaka & Mohastangor; Bay extension at Saiedpur & Barisal | PGCB | JICA PKG 4 EPC for Jaldhaka & Mohastangor; Bay extension at Saiedpur & Barisal Client - PGCB | 22.4 | Barisal | Barisal Project Coordinator Md Abdul Khaleque 01712204871 Hasnat-01708131709 | Md Abdul Khaleque | Barisal Project Coordinator | 1712204871 | - | - | Deed Agreement | Barisal Project Manager Barisal Project Coordinator Md Abdul Khaleque 01712204871 Hasnat-01708131709 | 20.10.2016 30.10.2016 -Civil Drawing Submitted to PGCB for Approval.Soil Test Completed.Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned person.Waiting to receive GTP & Drawing. 03.11.2016 Civil Drawing has been Approved.Soil Test Completed.Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned. person.Waiting to receive GTP & Drawing. 10.11.2016 Preparation for pilling in site office area. 17.11.2016 -S/S-Yard Construction area is cleaned. All tree and grass removed.Labor shed and site office is ready. Water pump is installed. Preparing to start Pilling work. 24.11.2016 -Pilling work is started. 01.12.2016 -Pilling work is going on. 08.12.2016 -GTP & Drawing of DS ES, Surge arrester and Circuit breaker’s submitted to PGCB for approval.13 Nos out of 16 Nos Pilling work has been done. 15.12.2016 -Piling work has completed. 22.12.2016 -No further update. 29.12.2016 -Earth Filling Progress is 74%. 05.01.2017 -Mixture Machine, Rod cutter & Vibrator Machine reached in site. 12.01.2017 -Design submitted for approval to PGCB for CB & LA. 19.01.2017 -Got Approval GTP & GA of LA & 132 KV CB.GTP & GA of DS/ES submitted for approval to PGCB.Earth Filling is going on. 26.01.2017 -GTP & GA of Conductor submitted for approval to PGCB. 02.02.2017 -Got approval GTP & GA of 132 KVA DS/ES. GTP & GA of CT, IVT & 33 KV GCB submitted for approval to PGCB. 09.02.2017 -As same as before. 16.02.2017 -As same as before. to 06.04.2017 -Same as before. 13.04.2017 -Same as before. 20.04.2017 -Same as before.16 Nos pile work has been done,but pile head broken work not yet start.. 27.04.2017 to 25.05.2017 -No further date. 01.06.2017 -Gantry tower piling going on & 05 Nos completed out of 40 Nos. 08.06.2017 Gantry tower piling going on & 12 Nos completed out of 40 Nos. 15.06.2017 08 Nos completed out of 40 Nos for gantry tower. 22.06.2017 -32 Nos completed out of 40 Nos pile work has done for gantry tower. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -No further update. | 13.07.2017 -No further update.
[7 empty] | Hasnat- |  | 1708131709 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
23 | Design, Supply, Erection, Testing & Commissioning of New 132/33kV AIS S/S at Ruppur and Extension of 132kV bays at existing Ishurdi 230/132kV S/S on Turnkey basis | PGCB | Design, Supply, Erection, Testing & Commissioning of New 132/33kV AIS S/S at Ruppur and Extension of 132kV bays at existing Ishurdi 230/132kV S/S on Turnkey basis Client - PGCB | 23.1 | RUPPUR | Project Manager Eng Moazzem 01714217922 Engr Rashad 01755633886 Sae-Romijul, 01787690462, | Eng Moazzem- | Project Manager | 1714217922 | - | - | Deed Agreement | RUPPUR Project Manager Project Manager Eng Moazzem 01714217922 Engr Rashad 01755633886 Sae-Romijul, 01787690462, | 30.10.2016 -Civil Design & Drawing is going on.Soil Test Completed.Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned person.Waiting to receive GTP & Drawing. 03.11.2016 10.11.2016 -No further update. 10.11.2016 26 Nos out of 88 Nos pile are completed. 17.11.2016 -Searching for Contractor. 24.11.2016 -No update. 01.12.2016 -Searching Contractor for pilling work. 08.12.2016 -GTP & Drawing of DS ES, Search Eristor and Circuit breaker’s submitted to PGCB for approval.Till now Searching Contractor for piling work. 15.12.2016 22.12.2016 -No further update. 29.12.2016 -Requisition submitted to purchase section for Mixer machine & Shuttering materials. 05.01.2017 -Got Approval Piling Drawing from PGCB. 12.01.2017 -Design submitted for approval to PGCB for CB & LA. 19.01.2017 -Got Approval GTP & GA of LA & 132 KV CB.GTP & GA of DS/ES submitted for approval to PGCB. 26.01.2017 -GTP & GA of Conductor submitted for approval to PGCB. 02.02.2017 -Got approval GTP & GA of 132 KVA DS/ES. GTP & GA of CT, IVT & 33 KV GCB submitted for approval to PGCB. 09.02.2017 -Same as before. 16.02.2017 -Got approval GTP & GA of Auxiliary Transformer from PGCB. 23.02.2017 -As same as before. to 30.03.2017 -No further update, 06.04.2017 -Labor shed & side office construction work is going on. 13.04.2017 -Labor shed & side office’s construction work is continuing. 20.04.2017 -Labor shed & side office’s construction work has been finished. 27.04.2017 -No further update. 04.05.2017 -Water house making work has been completed for pile work. 04.05.2017 -Water house making work has been completed for pile work. 11.05.2017 -Pile lay out work has been completed. 18.05.2017 -No further update. 25.05.2017 -50% floor casting work has been done at ground floor in control building.Brick soling work has been done in switchyard.Cable trench excavation work done.07Nos base 7 column work has completed for boundary wall.08 Nos gantry tower casing completed. 01.06.2017 100% floor casting work at ground floor in control building.70% plaster work & Tiles work has been completed at control building.All Air conditioner has been installed. Electrical wiring & False ceiling work has been completed at control building. 08.06.2017 40m base cast has done for cable trench.06 Nos pit has been completed for WCP.07 Nos COLUMN & 15m brick work has been done.55m road soling, herring bond has done.Facing bricks work has done at south side.West side drop wall has been completed. 15.06.2017 20m base cast has done for cable trench.10 Nos pit has been completed for WCP with PVC pipe setting.Safety tank brick work has done.5*20 m road soling with herring bond has done. 1.5m wide,55m long RCC road casting has been completed 40m*10m soling mortar has done. 22.06.2017 150m coping /RCC casting work has done.04 Nos pit has been completed for WCP with PVC pipe setting.1.5m wide,10m long RCC road casting has been completed.5m wide,22m long RCC road casting has been done.Control building west side facing brick work has completed.Sanitary work 60% has done. -20m Coper slab work has done at cable trench. 29.06.2017 Cable trench work has been done. (Type A 20m,Type B 58m,Type C 05m,) 06.07.2017 -Road brick soling work has done.58 m long brick work has done at switchyard. West side of CB brick soiling work has been completed.Plaster work for boundary wall has done. | 13.07.2017 150m long plaster work for boundary wall.(in & out side) 20 Nos Water cast meant pit (W C P) has been completed for Bay-2 & Bay-3.levling,soling, motering work has been completed at Bay-2 & Bay-3.90m long Surface drain has been completed.
[7 empty] | Engr Rashad |  | 1755633886 | - | - | Contract Date
[7 empty] | Sae-Romijul |  | 1787690462 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
23 | Design, Supply, Erection, Testing & Commissioning of New 132/33kV AIS S/S at Ruppur and Extension of 132kV bays at existing Ishurdi 230/132kV S/S on Turnkey basis | PGCB | Design, Supply, Erection, Testing & Commissioning of New 132/33kV AIS S/S at Ruppur and Extension of 132kV bays at existing Ishurdi 230/132kV S/S on Turnkey basis Client - PGCB | 23.2 | ISHURDI | Project Manager Eng Moazzem-1714217922 Engr Rashad 01755633887 SE,nurhasan 01708453300 | Eng Moazzem- | Project Manager | 1714217922 | - | - | Deed Agreement | ISHURDI Project Manager Project Manager Eng Moazzem-1714217922 Engr Rashad 01755633887 SE,nurhasan 01708453300 | 23.10.2016 94% Sand Filling Completed,Civil Drawings will be submitted within 31-10-2016. 27.10.2016 Sand Filling work is complited. Leveling & dressing works are going on. 15,000-20,000 cft additional sand filling may be required after leveling the area.Approval of drawings are halted due to training of PGCB's Engineers (PD: S.M Shafiqul Islam, X-Eng: Bellayet & A.E: Mizan). From next Sunday (30-10-2016) PGCB's engineers will be available to check & approve the submitted drawings. 03.11.2016 -Piling work will be started on 05Nov,2016. Control Room Building: Total pile 88 nos as per our work schedule all 88 piles should be completed within 16/11/2016. Pile work will be addressed by PGCB's MD sir & EEL's CEO sir on 6/11/2016. 10.11.2016 -26 Nos out of 88 Nos pile are completed. 17.11.2016 -Total pile work (88 nos) completed.Site office,site bathroom work 80% completed. -Excavation for 24 nos of piles started. 24.11.2016 CRB: 18 Nos pile excavation completed and pile cap works going on Gantry Tower: 16 Nos out of 88 Nos pile completed Site Office: Completed. 01.12.2016 -A/y:66 Nos out of 88 Nos pile completed.CRB:24 Nos out of 44Nos PCC works completed. 8 Nos out of 44 Nos Column rebar works completed. 08.12.2016 S/Y: 82 Nos out of 88 Nos Pile have been completed -CRB: 36 Nos out of 44 Nos PCC works completed. -12 Nos out of 44 Nos Column Rebar binding works completed. 15.12.2016 -88 Nos Gantry pile completed -8 Nos transformer piles completed 21 Nos out of 44 Nos pile cap of control room building completed. 22.12.2016 -42 Nos out of 44 Nos pile cap completed.8 Nos column casting completed.pile of boundary work started. 29.12.2016 -02 Nos out of 24 Nos Tower Foundation PCC Completed.185 RM Grade Beam Rebar Work completed. 05.01.2017 -Grade beam and 06 Nos Gantry tower pile cap work has been completed. 12.01.2017 -Out of 44,5 Nos short column is casting remain. shuttering work of slab beam started,03 Nos gantry tower foundations work has completed, 19.01.2017 Slab beam shuttering work & 04 Nos gantry tower foundation work has been completed.Roof slab shuttering & 01 Nos XFR foundation work is going on. 26.01.2017 1st floor slab casting has been completed.One no XFR base casting has been completed.12 Nos out of 44 Nos gantry tower casting has been completed. 02.02.2017 -10 Nos of column has completed at Ist floor of control building.26 Nos gantry tower foundation has done.1 No XFR base foundation has been completed. 09.02.2017 -32 Nos column casting has done.External stair shuttering work is going on.22 Nos gantry foundation has been completed at 132/11 kV switch yard. 16.02.2017 -Rod binding work is going on for base foundation in XFR (02 No).Beam,Roof shuttering work is going on in control building. -Rod binding work is going on for external & internal stairs in control building.16 Nos of column casting has been completed. 23.02.2017 Control building :Roof slab beam shuttering work complete,Roof slab wooden shuttering placing work.Re bar fabrications work is going on.Celling plaster work is going on in grnd floor.Switchyard :pile cap casting for gantry tower,Rebar fabrication for pile caps in short column,Gantry tower pastel column shuttering's anchor bolt settings work.XFR pad:Rebar fabrication work going on,beam & wall rebar setting work.Boundary wall:Pile curing work going on,All casting curing work going on,Metarials available at this site. 02.03.2017 Control room building: Gr. Floor-All Columns, beams & Gr. floor roof slab concreting completed , plastering of ceiling is going on.1st floor: Casting of column ,. Re-bar setting works for all beams going on.Stair concreting 80℅ done.Gantry Towers: Total Piles: 88nos completed. Pile Cap: 100% completed. Column concreting: 60/ 88 Nos. Remaining works for column: 16 Nos.Power Transformer Foundation:Base completed out of 2 nos foundation.Boundary Wall Pilings:-123 / 130 nos pile completed. Remaining(7 Nos.) Pilings work has been stopped by P.G.C.B 09.03.2017 -Control room building roof RCC casting done.23 Nos Equipment foundation base done.9 Nos column done.Soil excavation going on. 16.03.2017 -No further update. 23.03.2017 -100m grade beam, pile cap work has done for base foundation.28 Nos base done for Equipment foundation.27Nos column work done for boundary wall. 30.03.2017 -XFR all work complete for installation.150m grade beam,28 Nos base done for Equipment foundation.Nos column work done for boundary wall. 06.04.2017 -All Equipment's foundation has been done.96 Nos column work done for boundary wall.first floor brick work 40% done.320m grade beam work has been done. 13.04.2017 -Brick wall & plaster has been completed in 11kV Control building.Brick wall has been completed up to lintel in 132kV Control building.Battery room plaster work has been completed. 20.04.2017 -45m Power cable trench work has been done.30m Base work has been finished.03 Nos column casting done for XFR. Base,column works has been done for 04 Nos PI. 27.04.2017 -10 Nos base & column cast has been completed. 25m grad beam work has been completed for boundary wall.Tiles work is continuing at 11kV control building panel room. 04.05.2017 -Inner & outer stair post casting work has been completed.30m beam work done for boundary wall. 11.05.2017 -15m Brick work has been completed for boundary wall.90m parapet wall making work has been done in control building roof.25m parapet wall making work has been done in control building up side at external stair. 18.05.2017 -12 Nos Gantry tower with 12Nos beam fabrication work has been completed.01 No bay total equipment & 01 No XFR wiring has been completed. Control panel fittings work has been finished in 132kV & 11kV site. 25.05.2017 25 Nos base CC cast has been completed. 01.06.2017 20 m long power cable trench wall has been completed.40m long base cast work has been finished at power cable trench. 08.06.2017 Cable trench wall casting has done 30m.18m base casting has been done. 15.06.2017 60 meter long cable trench wall has been completed. 22.06.2017 -Cable trench wall making work is going on. 29.06.2017 -Cable trench work is going on. 06.07.2017 -Cable trench work has been completed. | 13.07.2017 -150 Pc’s cable trench cover slab has been done.
[7 empty] | Engr Rashad |  | 1755633887 | - | - | Contract Date
[7 empty] | SE,nurhasan |  | 1708453300 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
24 | Design,supply,erection,testing and commissioning of 132/22kV AIS S/S at amnura with 132kV single circuit T/Lon Turnkey basis under bidder finance | PGCB | Design,supply,erection,testing and commissioning of 132/22kV AIS S/S at amnura with 132kV single circuit T/Lon Turnkey basis under bidder finance Client - PGCB | 24 | Amnura | Project Manager Engr Alamgir 01787680482 Mr Rahim-01787680497 Shahin- 01709650210 | Engr Alamgir | Project Manager | 1787680482 | - | - | Deed Agreement | Amnura Project Manager Project Manager Engr Alamgir 01787680482 Mr Rahim-01787680497 Shahin- 01709650210 | 23.10.2016 - 4 Nos out of 24 piles completed -Protection Scheme almost complete & will be submitted within 24-10-16 after attending meeting with PGCB's Protection Division. 27.10.2016 -12 No's out of 24 No's piles completed. 03.11.2016 All gantry tower piles are completed. Pile cap work will be started within 9/11/2016. 10.11.2016 Excavation of 24 Nos pile completed and pile cap work started. Excavation for equipment foundation started 17.11.2016 -Total equipment foundation 13 nos done.30% pile cap completed.equipment foundation work running. 24.11.2016 Gantry Tower: Excavation & Breaking of 24 Nos pile completed. PCC completed for 1 no Tower Foundation. 01.12.2016 Gantry Tower: PCC completed for all 24nos piles. 08.12.2016. Raft of 1 No tower out of 6 Nos completed. 15.12.2016 -Anchor bolt setting work is going on for tower. 22.12.2016 - 8 Nos column casting completed. 29.12.2016 Tower No 3 Rebar & Bolt setting work completed and will be casted on 01 Jan,2017. 05.01.2017 -06 Nos Gantry tower work has been completed. 12.01.2017 -Excavation for equipment foundations work is going on. 19.01.2017 -Excavation work is going on. 26.01.2016 -Excavation for equipment foundations work is going on. 02.02.2017 -Equipment foundations work is going on. 09.02.2017 -06 Nos gantry structure PCC has done at 230/132 kV site. 16.02.2017 -Earth excavation work stopped due to Excavator machine. 23.02.2017 Control room :-Total pile-88/88,pile cap-44/44, ground beam completed .column for ground floor-44/44,Ground floor slab casting completed. column for first & second floor 33/33,Switchyard: Pile -88/88,pile cap-22/22,pile uplift test completed for gantry tower,total short column for gantry-60/88 Nos column,XFR:pile-68/68,pile cap-00/04,XFR base pad completed-2/2,pile load test completed for XFR. 02.03.2017 -Gantry Tower Foundation: 6 Nos. completed out of 6 Nos. -Gantry Column Concreting with anchor bolts: 24 Nos completed out of 24 nos. -Equipment Foundation: -Earth Excavation works: 30% completed. -PCC Works done: 30% completed. -Re-bar works of base and columns: Going on. 09.03.2017 -06 Nos RCC base casting done for DS.Equipment earth excavation work done, 16.03.2017 -DS earth excavation completed.RCC base casting of DS done. 23.03.2017 -Earth excavation ,CC work has been for DS.RCC base casting done. 30.03.2017 -06 Nos column casting for DS (75% per column). -08 Nos column casting work has been done for GCB. 06.04.2017 -12 Nos base casting has been done for LA & IVT. 13.04.2017 -12 Nos column casting has been done for LA & IVT.20 Nos column casting has been done for VCB & DS. 20.04.2017 -IVT 22 Nos column casting has been done for VCB & DS. 27.04.2017 -No further update. 04.05.2017 -Earth excavation work is going on. 11.05.2017 -CC cast work has been done for Cable trench.Rod binding work is going on. 18.05.2017 -Earth excavation work and PCC casting work has been completed. 25.05.2017 -30/60 Nos WCP work has been completed.Tiles work is going on at guard room. 01.06.2017 45/60 Nos WCP work has been completed.Tiles work is going on at guard room.Preparation work for pile is going on. 08.06.2017 70m long Surface drain work has been completed.05 Nos pile has been done for gantry tower(T1). 15.06.2017 04 Nos WCP has been completed.30m long boundary wall plaster work has been done. 22.06.2017 -Paint work in Boundary wall.Surface drain finishing work has done. 12 Nos Piling work has been completed. 29.06.2017 -No further update. 06.07.2017 -04 Nos pile has been completed at switchyard.Panel wiring work is continuing. | 13.07.2017 -Piling work 4nos completed.
[7 empty] | Mr Rahim- |  | 1787680497 | - | - | Contract Date
[7 empty] | Shahin- |  | 1709650210 | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
25 | Turnky contract for Design,supply,construction,istalation,testing and commissioning work for Extension of 33kV new bay at 132/33kV Jamalpur grid sub ststion for Jamalpur PBS under BREB. | BREB | Turnky contract for Design,supply,construction,istalation,testing and commissioning work for Extension of 33kV new bay at 132/33kV Jamalpur grid sub ststion for Jamalpur PBS under BREB. Client - BREB | 25 | Jamalpur | Project Manager Engr Muntasir Dipto 01755633881 Fazlehasan-01716114406 | Engr Muntasir Dipto | Project Manager | 1755633881 | - | - | Deed Agreement | Jamalpur Project Manager Project Manager Engr Muntasir Dipto 01755633881 Fazlehasan-01716114406 | 27.10.2016 -Transmission line piling 98%, Pile Cap 33%, Open Cast Base 57%, Open Cast Chimney 44%,Switchyard Pile 81%, Switchyard Pile Cap- 78%, Open Cast-32%, Chimney-45%,Boundary Wall Piling Done- 88%. Control room gnd & 1st roof and gnd floor side wall & 1st floor side wall completed. 03.11.2016 Transmission Line Piling 100%, Pile Cap 46%, Open Cast Base 66%, Chimney 49%. No pole erected and no stringing are done.Switchyard pile 80%, Pile Cap 78%, Open Cast Base 37%, Chimney 50%, Cable trench (Meter) 5%. Boundary Wall Pile 90%. Control Room - Its going plaster outside of the Control building. 10.11.2016 Transmission Line Piling 100%, Pile Cap 34%, Open Cast Base 58%, Chimney 39%. No pole erected and no stringing are done.Switchyard pile 100%, Pile Cap 100%, Open Cast Base 79.35%, Chimney 85.12%, Cable Trench(Meter) 13.08%. Boundary Wall Pile 92%. Control Room -outside plaster of the Control building going on.23.10.2016 Pile work nearly finish.Open casting work running.Switchyard Gantry 33kV done.Boundary wall work done. 17.11.2016 Transmission Line: Piling 100%, Pile Cap 39%, Open Cast Base 60%, Chimney 41%. No pole erected and no stringing are done. Switchyard: pile 100%, Pile Cap 100%, Open Cast Base 93.50%, Chimney 94.64%, Cable Trench(Meter) 13.08%. Boundary Wall Pile 96%. Control Room -Finishing work 40% done. 24.11.2016 -Transmission Line: Piling 100%, Pile Cap 45%, Open Cast Base 63%, Chimney 45%. Switchyard: pile *80%, Pile Cap *78%, Open Cast Base 66%, Chimney 70%, Cable Trench(m) 13.08%. Boundary Wall Pile **65%. Control Room -Finishing work 80% done. 01.12.2016 -Transmission Line: Piling 100%, Pile Cap 50%, Open Cast Base 67%, Chimney 49%.Switchyard: pile *80%, Pile Cap *78%,Open Cast Base 66%, Chimney 70%, Cable Trench(m) 26%.Boundary Wall Pile *100%,putting *25%. Control Room -Finishing work 85% done. 08.12.2016 Transmission Line: Piling 100%, Pile Cap 53%, Open Cast Base 73%, Chimney 51%. Switchyard: pile *80%, Pile Cap *78%,Open Cast Base 66%, Chimney 70%, Cable Trench(m) 42%.Boundary Wall: Pile *100%,Base *35%. Control Room -Finishing work 90% done. 15.12.2016 Transmission Line: Pile Cap 57%, Open Cast Base 76%,Chimney 63% done.Switchyard: Cable Trench(m) 63% has done.Control Room: -Finishing work 93% done. 22.12.2016 -Transmission Line: Pile Cap 68%,Open Cast Base 0%,Chimney 70%, Pole erection 2% done. -Switchyard: Cable Trench(m) 70% has done.Control Room: -Finishing work 96% done. 29.12.2016 -Transmission Line: Pile Cap 78%,Open Cast Base 81%,Chimney 78%, Pole erection 10% done. Switchyard: Piling 80%,Pile Cap 78%,Open Cast Base 66%,Chimney 70%, Pole erection 57% Cable Trench(m) 75% has done. Control Room: -Finishing work 97% done. 05.01.2017 -Transmission Line: Pile Cap 86%,Open Cast Base 83%,Chimney 84%, Pole erection 32% done.Switchyard: Piling 80%,Pile Cap 78%,Open Cast Base 66%,Chimney 70%, Pole erection 84% Cable Trench(m) 76% has one.Control Room: -Finishing work 97% done. 12.01.2017 -Transmission Line: Pile Cap 87%,Open Cast Base 92%,Chimney 89%, Pole erection 33% done.Switchyard: Pile Cap 78%,Open Cast Base 75%,Chimney 73%, Pole erection 84% Cable Trench(m) 76% has one.Control Room: -Finishing work 97% done. 19.01.2017 -Transmission Line: Pile Cap 93%,Open Cast Base 94%,Chimney 93%, Pole erection 36% done.Switchyard: Pile Cap 78%,Open Cast Base 75%,Chimney 76%, Pole erection 84% Cable Trench(m) 76% has one.Control Room: -Finishing work 97% done. 26.01.2017 -Transmission Line: No of Pile- 100%,P/C-94%, Open Cast Base-98 %, Chimney- 96 %, Pole erection- 36 % done .Switchyard: Pile -80%,P/C-78% Open Cast Base- 82%, Chimney-80%, Tower erection- 84% Cable Trench(m)- 76% has one. 02.02.2017 -Transmission Line: No of Pile-100%,P/C-100%, Open Cast Base-100%,Chimney-100 %, Pole erection 36% done..Switchyard: Pile -80%,P/C -78% Open Cast Base-83%, Chimney-81%, Tower erection-84 % Cable Trench(m)-76% has one. 09.02.2017 -Transmission Line: No of Pile-100%,P/C-100%, Open Cast Base-100%,Chimney-100 %, Pole erection 36%done. Switchyard : Pile -80%,P/C -78% Open Cast Base-86%, Chimney-81%, Tower erection-84 % Cable Trench(m)-76% has one. 16.02.2017 -Transmission Line: Pole erection 36% done.Switchyard : Pile -84%,P/C- 78% Open Cast Base-87%, Chimney-83%, Tower erection- 84% Cable Trench(m)-76% has Done. Control building-99%. 23.02.2017 -Transmission Line: same as before.Switchyard : Pile -84%,P/C- 78% Open Cast Base-87%, Chimney-85%,Tower erection- 84% Cable Trench(m)-76% is Done.Control building-99%. 02.03.2017 Transmission Line: Pole errection 37%.Switchyard :Same as before.,Tower erection- Same as before.Control building-Same as before. 09.03.2017 Transmission Line: Pole erection 54%. 16.03.2017 Transmission Line: Pole erection 76%. 23.03.2017 Transmission Line: Pole erection 95%. 30.03.2017 Transmission Line: Pole erection 98%. 06.04.2017 Transmission Line: Pole erection 100%. 13.04.2017 -Electrical wiring work is going on in 132kV switch yard. 20.04.2017 .Brick, soling, plaster & Gravelling work is going on in 132kV type substation. 20.04.2017 -Brick, soling, plaster & Gravelling work is going on in 132kV type substation. 27.04.2017 -Civil work is going on for Guard room.Brick wall work has been completed in boundary wall. 04.05.2017 -20m grade beam work has been done. 11.05.2017 -20 m Brick wall work has been done. 18.05.2017 -WCP work is continuing.Pipe fitting work is going on. 25.05.2017 to 29.06.2017 -No further update. 06.07.2017 -Application for Pre Commissioning has been submitted to Jamalpur Grid. | 13.07.2017 -No further update. |  |  | *- rest of the work can’t be started before shut-down. **- boundary wall drawing has been changed by PGCB.
[7 empty] | Fazlehasan- |  | 1716114406 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
26 | Turnkey contract for Design,supply,construction,installation,testing & commissioning work for extension of exiting 33 Kv indoor BAY - breaker and control room building at 132/33kV cox'sbazar grid sub-station under COX'SBAZAR PBS | BREB | Turnkey contract for Design,supply,construction,installation,testing & commissioning work for extension of exiting 33 Kv indoor BAY - breaker and control room building at 132/33kV cox'sbazar grid sub-station under COX'SBAZAR PBS Client - BREB | 26 | Cox's Bazar | Engr Muntasir Dipto 01755633881 | Engr Muntasir Dipto |  | 1755633881 | - | - | Deed Agreement | Cox's Bazar Project Manager Engr Muntasir Dipto 01755633881 | 22.10.2016 -All equipment foundation ready.Gantry & cable trench done.Equipment PLI done. 27.10.2016 -All equipment foundations ,control cable trench completed,power cable trench 12 meter out of 32 meter completed. 03.11.2016 Except Isolators all other equipment's shipped to the site, cable trench construction going on. 12.11.2016 no civil work done due to bad weather.All necessary equipment's shipped to the site. 17.11.2016 -Project work cannot run for man power issue. 24.11.2016 -Tower fabrication work done. 01.12.2016 -No further update. 08.12.2016 -Civil works complete. -Erection work started and electrical works going on. 15.12.2016 -Erection has been started. -Tower erection Pending due to shut down issue.Isolator not delivered as REB didn’t approve the PLI yet. 22.12.2016 -Mesh earthing work has been done.Grounding cable lifting & connecting for equipment.Tower erecting 50% done. 29.12.2016 -Waiting for the shut down date.Soling,Motering has done. 05.01.2017 -Waiting for the shut down date.Brick Soling,Motering work has done in construction area. 12.01.2017 -preparation work is going on for Shut down, not yet get the shut down date. 19.01.2017 -06 Nos beam & 03 Nos tower has erected. 26.01.2017 -Waiting for the shut down,after get the shut down then we will finish our erection work. 02.02.2017 -06 Nos Isolators installation has done.Isolator’s box has fittings works has done. -03 Nos Breaker’s & 03 set CT has been installed. 09.02.2017 -All equipment installation has been completed. -01 Nos Gantry structure has erected.Control cable laying work is going on. 16.02.2017 -Control cable laying work has been done from indoor to outdoor. 23.02.2017 -Control cable laying work has been done approx. 90% from indoor to outdoor. 02.03.2017 -Waiting for Shutdown. 09.03.2017 -100% mechanical work completed in outdoor switchyard. 16.03.2017 -Control Panels all erected. 23.03.2017 -Cable laying work termination 80% done. 30.03.2017 -Cable laying work termination 95% done. 06.04.2017 -Cable laying work termination 100% done. Waiting for pre commissioning date,Letter sent to REB office for get the date. 13.04.2017 -No further update. 20.04.2017 -Power cable termination work has been completed.Spare materials handover to PBS at Jamalpur. 27.04.2017 -Preparation work is going on for Precommissioning. 04.05.2017 -Factory inspection has been done for Bus section isolator. 11.05.2017 -01 No Bus coupler Isolator (2500 A,31.5 KA ) handover to Jamalpur substation 18.05.2017 -Spare materials RR reporting receipt copy collect from Jamalpur PBS. 25.05.2017 01.06.2017 -No further update. 08.06.2017 -Commissioning has been completed. 15.06.2017 -No further update. | Commissioning has been completed. |  |  | 17.11.2016 -Manpower shortage.
[10 empty] | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
27 | Turnkey contract for Design,supply,construction,installation,testing & commissioning of 33 kV Bay Breaker Installation and related works at SHERPUR 132/33 kV Grid Sub-Station for SHERPUR PBS under BREB. | BREB | Turnkey contract for Design,supply,construction,installation,testing & commissioning of 33 kV Bay Breaker Installation and related works at SHERPUR 132/33 kV Grid Sub-Station for SHERPUR PBS under BREB. | 27 | SHERPUR | SHERPUR Project Manager Engr Jafor Iqbal 01713147042 Johir,SAE-01774218232 | Engr Jafor Iqbal | SHERPUR Project Manager | 1713147042 | - | - | Deed Agreement | SHERPUR Project Manager SHERPUR Project Manager Engr Jafor Iqbal 01713147042 Johir,SAE-01774218232 | 22.10.2016 2no of breakers,1no adapter.5no of columns(out of 6)are done.shutdown approx 24oct,2016 27.10.2016 Short column done,preparing for beam casting .Estimated roof casting by 10nov,16 03.11.2016 Beam casting going on, estimated roof casting 17Nov,2016. 10.11.2016 -column casting done.estimated roof casting 28 Nov,2016. 17.11.2016 -Control room Roof casting running. 24.11.2016 -preparation work done for roof casting.Hope 28Nov,2016 will be Roof casting done. 01.12.2016 -Roof casting Completed.Cable trench work going on. 08.12.2106 -Electrical works going on. -PLI not done yet. 15.12.2016 -Cable trench work has been started.Building curing on going. Will be finished at 20,dec 2016. 22.12.2016 -Building curing has been finished.Inside of control room work has been started. -Cable trench work is going on. 29.12.2016 -Cable trench cc has been completed.Brick wall work to be started Very soon.AIS status update wasn’t clear from Reza vai. Need urgent attention. 05.01.2017 -Power cable trench work has been going on. 12.01.2017 -No up date. 19.01.2017 -Power cable trench work is going on.Panel not yet come at site,still now in Factory. 26.01.2017 -Power cable trench work is going on.Panel not yet come at site, still now in Factory. 02.02.2017 -Contractor didn’t agree to work at site,not yet get his bill. 09.02.2017 -No update. 16.02.2017 -Panel inspection not done yet.Waiting for the inspection date by PBS. 23.02.2017 -Panel inspection work has been done. -No further update. 02.03.2017 -No further update. 09.03.2017 -Shut down date is got. (20,March 2017) 16.03.2017 23.03.2017 -Same as before. 30.03.2017 -No further update -Shut-down date this Friday (7 Apr, 2017). 06.04.2017 -Waiting for pre commissioning date,Letter sent to REB office for get the date. 13.04.2017 -Same as before. 20.04.2017 to 18.05.2017 -No further update. 25.05.2017 Bus installation work completed & Bus energized already done. CT installation work has done.Jumpering work also completed.04 Nos earthing boring work has been completed. 01.06.2017 -Operating pipe & shaft has been installed.LA with plate has been installed. 08.06.2017 -80% civil works has been completed. 15.06.2017 Bus PT Installation work has been completed. 22.06.2017 29.06.2017 -No further update. 06.07.2017 Control cable laying preparation work has been completed.Existing feeder installation work has been completed. | 13.07.2017 -02 Nos PBD’s extension feeder placing to another area in same site.Civil works has been completed in VCB site.
[7 empty] | Johir,SAE- |  | 1774218232 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
28 | Design,supply,construction,installation,testing & commissioning of 33kV 04 Nos. Bay-Breaker Extension and related works at Saidpur 132/33kV Grid Sub-station for Nilphamari PBS under Turnkey contract basis. | BREB |  | 28 | SAIDPUR | SAIDPUR Project Manager Engr Jafor Iqbal 01713147042 Johir,SAE-01774218232 | Engr Jafor Iqbal | SAIDPUR Project Manager | 1713147042 | - | - | Deed Agreement | SAIDPUR Project Manager SAIDPUR Project Manager Engr Jafor Iqbal 01713147042 Johir,SAE-01774218232 | 22.11.2016 -Soil test complete. -Earth cutting. -work start. 24.11.2016 -03 nos tower foundation base Excavation work done. -Existing Gravel shifted from site. 01.12.2016 -04 Nos of Shuttering work completed of tower foundation.02 Nos of Earth cutting work done of tower foundation. 08.12.2016 -Base casting work done of 04 Nos of tower foundation. -02 Nos of tower existing base dismantling. 15.12.2016 -02 Nos of tower foundation casting work complete.02 Nos of tower structure installation done.02 Nos of base rod binding work has completed. 22.12.2016 -04 Nos of tower foundation casting work complete. -Existing tower foundation base casting 50% has done. -02 Nos of VCB base foundation has completed. 29.12.2016 -No further update. 05.01.2017 -08 Nos gantry tower structure foundation RCC work has completed. -02 Nos RCC foundation work of VCB has completed. 12.01.2017 -02 Nos VCB foundation casting work has been completed. 19.01.2017 -01 Nos VCB foundation casting work has been completed. 26.01.2017 Problem:- -TECHNICAL MANPOWER SHORTAGE. -No further update. 02.02.2017 -Gantry tower erect work has been started. 09.02.2017 -04 Nos of tower has been erected.02 Nos of Beam has erected. 16.02.2017 -04 Nos of Beam has been erected. 23.02.2017 -Request for shut-down, 02.03.2017 -Waiting for the shut-down. 09.03.2017 -Shutdown processing work is going on. 16.03.2017 -02 Nos of tower already shifted.02 Axillary XFR settings on the beam.02 Nos of XFR energized for temporary basis. 23.3.2017 -08 Nos tower installation completed. 30.03.2017 -DS,ES setting work has been completed.Auxiliary base, foundation base malting work running. 06.04.2017 -Auxiliary base and foundation base malting work has been done. 13.04.2017 -02 Nos foundation works has been completed for additional VCB & CT. 20.04.2017 -CT & PT has been erected. 27.04.2017 -02 Nos VCB has been arrived at site.03 Nos Isolator & 05 Nos Shaft has been erected. 04.05.2017 -Mk box has been installed.VCB installation work is going on. 11.05.2017 -03 Nos VCB errection work has been completed.01 Set Bus isolator with shaft & junction box has been erected. 18.05.2017 -No further update. 25.05.2017 -04 Nos tower foundation casting work has been completed.03 Nos VCB base casting work has been completed.02 Nos VCB rod binding & shuttering work has been completed.01 No shuttering rod binding work is going on. 01.06.2017 -Tower base & VCB base work has been completed. 08.06.2017 -Earthing work has been completed.Bus PT Installation work is going on. 15.06.2017 100% civil works has been completed. 22.06.2017 to 06.07.2017 -No further update. | 13.07.2017 -No further update.
[7 empty] | Johir,SAE- |  | 1774218232 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion
29 | Turnkey contract for Design,Supply,Construction,Installation,Testing & Commissioning work for extension of 33kV new Bay at 132/33kV Jhenaidah Grid sub station for Jhenaidah PBS under BREB Client –BREB | BREB | Turnkey contract for Design, Supply,Construction,Installation,Testing & Commissioning work for extension of 33kV new Bay at 132/33kV Jhenaidah Grid sub station for Jhenaidah PBS under BREB Client –BREB | 29 | JHENAIDAHA | JHENAIDAHA Project Manager Engr Jafor Iqbal 01713147042 Johir,SAE-01774218232 | Engr Jafor Iqbal | JHENAIDAHA Project Manager | 1713147042 | - | - | Deed Agreement | JHENAIDAHA Project Manager JHENAIDAHA Project Manager Engr Jafor Iqbal 01713147042 Johir,SAE-01774218232 | Drawing for soil test and boundary wall approved from BREB. Two storied Control Building design work is continuing. 25.05.2017 -Main gate rail setting works & casting work has ben completed.Labor shed 50% done.Brick wall work has been completed.Design approval works under processing at local Powroshova. 01.06.2017 -All Design has been approved by local Powroshova. 08.06.2017 10% Sand filling has been done.Main gate settings work is going on. Boundary wall drawing submitted to BREB,jenaidhah for approved.80% labor shed,temprorary office making has been completed. Building drawing has been approved. 15.06.2017 15% Sand filling has been done. Main gate settings work has been completed.100% labor shed,temprorary office making has been completed. 22.06.2017 29.06.2017 -No further update. 06.07.2017 19 Nos boundary wall putting cc casting work has done.Earth excavation work has done for putting.05 Nos pile boring and casting work has been done.Main gate setting work has been completed. Sand filling work 10% has been completed. | 13.07.2017 -15 Nos CC casting has been done boundary wall.Soil excavation work has done for 52 Nos base.13 Nos pile work has been completed.
[7 empty] | Johir,SAE- |  | 1774218232 | - | - | Contract Date
[10 empty] | - | - | Commencement Work
[10 empty] | - | - | Initial Drawings Approval
[10 empty] | - | - | Design and Drawing of eqp
[10 empty] | - | - | Civil Design and Drawing
[10 empty] | - | - | Manufacture & Delivery of eqp
[10 empty] | - | - | Civil Works
[10 empty] | - | - | Electrical Works
[10 empty] | - | - | Testing and commissiong
[10 empty] | - | - | Hand-Over
[10 empty] | - | - | Declaration of completion

## Report (hidden)
|  |  |  | DOC No: |  |  |  |  | Project Information Report |  |  | DATE: | 2017-09-07
|  |  |  | FORMAT No: | [7 empty] | PREPARED BY: | Engr. Ayshik
PROJECT AUDIT DIVISION |  |  |  | REV No: | 0 | [6 empty] | APPROVED BY: | Engr. Anisuzzaman
Slerial no | Project | Client | Name of Project | Site ID | Site name | Responsible Project Manager |  |  | Milestone | Project Status | Present Status | Deviations | Remarks
[7 empty] | Date | Description of work
1 | 132/33kV SS at Nawabganj,Srinagar, Narail, Jhenaidah & Magura | PGCB | 132/33kV SS at Nawabganj,Srinagar, Narail, Jhenaidah & MaguraClient - PGCB | 1.1 | Narail |  | May 09 '16 | Deed Agreement | May 09 '16 - Deed Agreement | Deed Agreement done on May 09 '16 | Sep 18 '16 Design & drawing of equipment done 16% | - | -
[7 empty] | Jun 30 '16 | Contract Date | Jun 30 '16 - Contract Date
[7 empty] | May 29 '16 | Commencement Work | May 29 '16 - Commencement Work | Commencement of Work- Done
[7 empty] | Jul 03 '16 | Initial Drawings Approval | Jul 03 '16 - Initial Drawings Approval | initial Drawing -Done
[7 empty] | Oct 02 '16 | Design and Drawing of eqp | Oct 02 '16 - Design and Drawing of eqp
[7 empty] | Jan 11 '17 | Civil Design and Drawing | Jan 11 '17 - Civil Design and Drawing
[7 empty] | May 22 '17 | Manufacture & Delivery of eqp | May 22 '17 - Manufacture & Delivery of eqp
[7 empty] | Feb 05 '18 | Civil Works | Feb 05 '18 - Civil Works
[7 empty] | Mar 22 '18 | Electrical Works | Mar 22 '18 - Electrical Works
[7 empty] | May 06 '18 | Testing and commissiong | May 06 '18 - Testing and commissiong
[7 empty] | May 21 '18 | Hand-Over | May 21 '18 - Hand-Over | -
[7 empty] | May 21 '18 | Declaration of completion | May 21 '18 - Declaration of completion
|  |  |  | 1.2 | Nawabganj |  |  | Deed Agreement | - Deed Agreement | July 25,2016 abc | July 25,2016 abc |  | all outdoor & indoor equipment installed. Civil works are under process. Expected completion date August'2016
[8 empty] | Contract Date | - Contract Date
[8 empty] | Commencement Work | - Commencement Work
[8 empty] | Initial Drawings Approval | - Initial Drawings Approval
[8 empty] | Design and Drawing of eqp | - Design and Drawing of eqp
[8 empty] | Civil Design and Drawing | - Civil Design and Drawing
[8 empty] | Manufacture & Delivery of eqp | - Manufacture & Delivery of eqp
[8 empty] | Civil Works | - Civil Works
[8 empty] | Electrical Works | - Electrical Works
[8 empty] | Testing and commissiong | - Testing and commissiong
[8 empty] | Hand-Over | - Hand-Over
[8 empty] | Declaration of completion | - Declaration of completion
|  |  |  | 1.3 | Srinagar |  |  | Deed Agreement | - Deed Agreement | July 25,2016 abc | July 25,2016 abc |  | all outdoor & indoor equipment installed. Civil works are under process. Expected completion date August'2016
[8 empty] | Contract Date | - Contract Date
[8 empty] | Commencement Work | - Commencement Work
[8 empty] | Initial Drawings Approval | - Initial Drawings Approval
[8 empty] | Design and Drawing of eqp | - Design and Drawing of eqp
[8 empty] | Civil Design and Drawing | - Civil Design and Drawing
[8 empty] | Manufacture & Delivery of eqp | - Manufacture & Delivery of eqp
[8 empty] | Civil Works | - Civil Works
[8 empty] | Electrical Works | - Electrical Works
[8 empty] | Testing and commissiong | - Testing and commissiong
[8 empty] | Hand-Over | - Hand-Over
[8 empty] | Declaration of completion | - Declaration of completion
| 132/33kV SS at Nawabganj,Srinagar, Narail, Jhenaidah & Magura | PGCB |  | 1.4 | Narail |  |  | Deed Agreement | - Deed Agreement |  |  |  | Equipment foundation completed, Gantry structure installation is going on, power transformer delivered at site.
[8 empty] | Contract Date | - Contract Date |  |  |  | All equipment delivered at site. Control panels could not be installed due to space constrain
[8 empty] | Commencement Work | - Commencement Work |  |  |  | Wo placed to factory, delivery deadline Sep'16
[8 empty] | Initial Drawings Approval | - Initial Drawings Approval |  |  |  | Wo placed to factory, delivery deadline Sep'16
[8 empty] | Design and Drawing of eqp | - Design and Drawing of eqp |  |  |  | Drawing design approved
[8 empty] | Civil Design and Drawing | - Civil Design and Drawing |  |  |  | WO placed to factory, delivery deadline Sep'16
[8 empty] | Manufacture & Delivery of eqp | - Manufacture & Delivery of eqp |  |  |  | preliminary stage, only NOA recived & drawing completed
[8 empty] | Civil Works | - Civil Works
[8 empty] | Electrical Works | - Electrical Works |  |  |  | commissioning supposed to be completed by Aug'16
[8 empty] | Testing and commissiong | - Testing and commissiong |  |  |  | Steel structure construction of 4th flr is to be contracted out
[8 empty] | Hand-Over | - Hand-Over |  |  |  | Delay in shipment of 33 kV GIS, Awaiting to send PSI team for termination kit inspection at CYG China
[8 empty] | Declaration of completion | - Declaration of completion |  |  |  | Timely completion depends on availibility of shut down, power transformer
|  |  |  | 1.5 | Nawabganj |  |  | Deed Agreement | - Deed Agreement |  |  |  | Equipment structure expected to be delivered from factory by Aug'16
[8 empty] | Contract Date | - Contract Date |  |  |  | Equipment structure need to be delivered by kabirpur factory by Aug'16
[8 empty] | Commencement Work | - Commencement Work |  |  |  | pending delivery of 11 kV isolator for united city center (need to check with isolator div)
[8 empty] | Initial Drawings Approval | - Initial Drawings Approval |  |  |  | need to follow up with factory, delivery deadline Aug'16
[8 empty] | Design and Drawing of eqp | - Design and Drawing of eqp
[8 empty] | Civil Design and Drawing | - Civil Design and Drawing
[8 empty] | Manufacture & Delivery of eqp | - Manufacture & Delivery of eqp
[8 empty] | Civil Works | - Civil Works
[8 empty] | Electrical Works | - Electrical Works |  |  |  | Work order placed to factory product delivery time Feb'17
[8 empty] | Testing and commissiong | - Testing and commissiong
[8 empty] | Hand-Over | - Hand-Over
[8 empty] | Declaration of completion | - Declaration of completion |  |  |  | product delivered only termination kit not made as cable size yet not confirmed by BPDB

## presentation
| Serial no | Name of Project | Site info | Project Status | Previous Status (last Week) | Current Status (This Week) | Current status of project (This week)
58 | 1.1 | DDP (Nayarhat, Birulia, Jalshiri & Nazarpur) | Nayarhat Project Manager Md.Azharul Haque 01732761574 SAE. Shahjalal 01755445178 Shafiul Azam- 01755506232 | 26.10.2016 -12 Nos of base casting is complete for control building. 03.11.2016 -12 Nos of short column casting is complete, 1000 mm sand filling going on for control building, 400 mm sand filling is complete in switchyard area to start CC work for gantry foundation. 10.11.2016 -08 Nos of base of gantry casting is complete, Sand filling is complete up to grade beam of control building area & compaction is going on, excavation complete of 03 nos of base for boundary wall column. 17.11.2016 -08 Nos column of gantry foundation casting is complete, Rod fabrication is complete for grade beam. 24.11.2016 -Control room short column casting complete.Grade beam shuttering complete.Gantry tower base and short column casting complete.One base for XFR is complete.6 Nos of bases for boundary wall complete. 01.12.2016 -Control building: grade beam and column (FGL to PL) RCC casting complete.XFR : 01 Nos RCC base and 01 Nos base PCC casting complete and reinforcement binding & shuttering complete.2 Nos of EM tower base PCC casting complete.Boundary wall: 06 Nos short column RCC casting complete. 08.12.2016 -One base of XFR's RCC casting has been completed and another base’s two pedestals’ RCC casting has been completed.02 Nos of EM tower base RCC casting has been completed.02 Nos of boundary short column RCC and 02 Nos of boundary base PCC+RCC casting has been completed.Brick work has been completed from grade beam to PL of control building's.Some sand filling completed in front of control building. 15.12.2016 Two pedestal of another base RCC casting has been completed. 02.Twi nos of EM tower column RCC casting has been completed. 03.8nos of Gantry tower Columbus RCC casting has been completed.04.four nos column of control building's RCc casting has been completed. 05.Boundary wall: 6nos base RCC +7nos short column+10 nos base PCC casting has been completed. 22.12.2016 -4 Nos column of control building RCC casting has been completed.Boundary wall: 7 Nos RCC base +9 Nos short column +RCC Grade Beam 30m long+11nos base PCC casting has been completed. 29.12.2016 Boundary wall: 7nos RCC base+14nos short column Grade beam 10m long +9nos base PCC casting has been Completed.3 Nos control building columns half of above RCC casting has been completed.Septic tank & Soak well 's Brick work has been completed.Stair base:Earth work+ base(PCC+RCC)+2nos column RCC casting has been completed.LA,CB,CT base earthwork has been completed. 05.01.2017 -Boundary wall:12nos short column and 50m long Grade beam RCC casting has been completed.Stair base and column casting has been completed and first flight shuttering has been completed.Septic tank plaster completed.First Floor shuttering going on. 12.01.2017 --Boundary wall:05 Nos short column and 30m long Grade beam RCC casting has been completed.Base casting work has done for LA,CT foundation.05 Nos of base casting has done for Boundary. 19.01.2017 -Control building first floor RCC casting has been completed. 26.01.2017 -Control Building 12nos column(half of the below) RCC casting has been completed.VCB&CT base RCC casting has been completed.Boundary wall:20nos short column & 27m long Grade beam RCC casting has been completed.+ 45m long Brick work has been completed.Setting of transformer base plate has been completed. 02.02.2017 -VCB,CT,LA &VCB,CT column casting and net finishing has been completed. Control building beam shuttering and dasha setting has been completed.60% sand filling completed and running. 09.02.2017 -24m long grade beam RCC casting & 18 m long boundary brick work has been completed.Aux.XFR soling,RCC base & brick wall has been completed.Control building Roof slab shuttering & Rod binding completed. Switchyard earthing main mesh completed. 16.02.2017 -Control building Roof slab RCC casting has been completed and Ground floor ready for casting.25.6m long boundary grade beam RCC casting & some brick work has been completed. 23.02.2017 -RCC casting in ground floor of control room,27 meter long grade beam complete for boundary.05 Nos short column done for boundary wall. 02.03.2017 -25 m out side plaster work has been done for Boundary wall.Top slab plaster and plaster with net finishing work has been completed. -Celling plaster work is going on for control building. Approx. 65% sand filling work has been done. 09.03.2017 -4 Nos base PCC & 4 Nos RCC base & 4 Nos short column RCC casting completed,Boundary wall-35 m long copying RCC casting completed.10 no column(FGL to copying) RCC casting completed. RAMPS,RCC casting completed & porch slab shuttering ,rod binding completed. -control cabletrench18 m long base RCC casting completed 25m long power cable trench PCC casting completed -sand filling 90%completed. 16.03.2017 -Control cable trench 2Nos wall 15m long RCC casting done.Guard house grade beam RCC casting completed.Control building,linten,porch,slab,sunshed,brick work (80%),ceiling plaster complete.Boundary wall:9Nos base (PCC+RCC),9Nos short column RCC casting ,boundary wall 25% has been completed. 23.03.2017 -Power cable trench wall 40m long RCC casting Completed. Stair slab casting completed. Control building Ground floor and First floor brick work, lintel,fols Chad, plaster completed, Parapet wall brick work and inside plaster Completed. Boundary wall 6 Nos base (pcc+RCC+short column) casting completed. 30.03.2017 -80% plaster work and net finishing work has been done at Side wall in power & control cable trench.25m grad beam for boundary wall has done. 06.04.2017 -100% plaster work and net finishing work at Side wall in power & control cable trench. -45m grad beam for boundary wall has been done.14 Nos short column casting has been done. 13.04.2017 -12 Nos short column & 13m grade beam work for boundary wall and 06m Cable trench wall work has been completed. 20.04.2017 -07 Nos short column for boundary wall.27m long grade beam casting completed,45m long brick work completed.Power XFR er guide wall & pedestal RCC casting with net finishing.Sand filling 95% completed.Paint work,Mosaic work,tiles work, fencing bricks work is running, 27.04.2017 -10 Nos long column for boundary wall & 23m long grade beam casting has been completed.Control building ground floor & first floor mosaic Patten stone casting & grill fitting work has been completed. Guard house floor cast has done.Control building & boundary color work is continuing.27.04.2017-10 Nos long column for boundary wall & 23m long grade beam casting has been completed.Control building ground floor & first floor mosaic Patten stone casting & grill fitting work has been completed. -Guard house floor cast has done.Control building & boundary color work is continuing. 04.05.2017 -30m long brick wall making work has been completed.23m cosing casting and 02 Nos column casting work has been completed. 11.05.2017 -Road making work has been completed in front of control building.Fancy brick work is going on.Main gate installed & Paint work has been done. 18.05.2017 -3m wide road RCC casting has been completed. Fencing base casting completed.Tiles work completed and mosaic cutting work is going on.23m long Boundary wall plaster completed in both side. 25.05.2017 Fork work at roof floor & RCC casting of retaining wall and Sand filling work is continuing.Re-bar work for retaining wall work has been completed. 01.06.2017 Brick soling work done at control building ground floor,Brick masonry done at ground floor beam to plinth level.Form work is continuing at roof floor.RCC casting & Re-bar work done at retaining all.02 Nos RCC casting of gantry tower.Sand filling is going on. 08.06.2017 5” thickness Brick masonry work has done at boundary wall.Re-Bar work has been for Roof floor & retaining wall.08 Nos RCC casting of Gantry tower.Sand filling work is going on. 15.06.2017 Levelling & dressing work,Re-bar work for roof floor.70% RCC casting of retaining wall completed. Sand filling work is going on.Re-bar work for retaining wall has 80% completed. 22.06.2017 -Roof slab casting done. Leveling & dressing work has done.RCC casting done in retaining wall. Re bar work 80% has done.Sand filling work is going on. 29.06.2017 -Eid festival holidays, so No further update. 13.07.2017 Gantry tower casting complete(8Nos). 50% sand filling complete. RCC casting of retaining wall(Continuously) 90% complete. Ceiling plaster complete(Ground floor). Brick masonry for ground floor ( ground to lintel) | 13.07.2017 -20 Nos Slab making has done for power cable trench. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
70 | 1.2 | DDP (Nayarhat, Birulia, Jalshiri & Nazarpur) | Birulia Project Manager Md.Azharul Haque 01732761574 Site Eng Usuf-01763521032 Shafiul Azam- 01755506232 | 27.10.2016 -Local problem solve.Deep tube well work done. 03.11.2016 -Store area is ready by brick soling to keep stone chips & sand, one house is also ready to keep clay of pile. 10.11.2016 -We are waiting for stone chips to start pile for retaining wall. 17.11.2016 Earth excavation and rod fabrication going on for boundary wall, construction materials arrived at site for pile. 24.11.2016 -Water leveling -Pointing & leveling of pilling for retaining wall..2 no CC casting of boundary wall base done. 01.12.2016 -RCC casting of short column (14 Nos).Sand filling of column base.Pile boring of retaining wall. 08.12.2016 -Approx. 5487 cft. Sand has been filled.Grade beam prepare work is going on. 15.12.2016 -Sand filling completed only for control building (EGL to column base).Pilling layout done.02 Nos casting done for grade beam. 22.12.2016 -30.48 meter length ,0.7 meter height and 0.250 meter thick brick work done for boundary wall (partially.) -Cast in C2 pile (12nos),drilling ,washing & casting done. 29.12.2016 -Lay out details of control building.Pile boring, washing & casting work has been done of retaining wall (total 22 Nos). 05.01.2017 -Pile work has been completed for retaining wall (33 Nos).Earth excavation has completed for control building footing (12 Nos). 12.01.2017 -10 Nos ofCC casting work has done for footing base of control building. 19.01.2017 -10 Nos RCC casting has been done for footing base in control building.10 Nos footing or short column shuttering has been completed. 26.01.2017 -10 Nos RCC casting has been done for footing or short column (control building). 02.02.2017 -12 Nos RCC footing casting work has done in control building.30 running meter grade beam casting work done for boundary wall. -Back filling,levelling and dressing work is going on. 09.02.2017 -Pile broken,Back filling,leveling and compaction work is going on.Layout of septic tank, soak well has been completed. 16.02.2017 -Brick wall is running for septic tank.Soil digging work done for Soak well.Back filling work has been finished up to Grade beam of Building.03 Nos pile broken done.15 Nos Shuttering work have been finished in boundary wall. 23.02.2017 -Pile breaking work is running.Back filling,leveling & compaction has been done.Brick work of septic tank has been done. Excavation complete of soak well.12 Nos RCC column casting done of boundary wall. 02.03.2017 -Shuttering work done for Grade beam in control building.Brick wall has been make at boundary wall.20 Nos Pile break work has been done. 09.03.2017 -Grade beam casting in control building. -15 Nos Pile cap shuttering has been done. -27 Nos pile has been done. 16.03.2017 -RCC column casting in control building. -CC casting of pile (17Nos) completed -Pile break completed. 23.03.2107 -Brick masonry 10”thikness(grade beam to plinth level).CC casting of pile has done.Final layout of switchyard.Re-bar work for pile cap. 30.03.2017 -08Nos RCC casting of pile cap.08 Nos CC base casting work has been done in 33kV gantry structure.Rebar work for pile cap & gantry column. -Brick masonry 10” thickness for soak well. 06.04.2017 -23Nos RCC casting of pile cap.Revar work has been done in 33kV gantry structure.Rebar work for pile cap & gantry column.First grad beam work has been done. 13.04.2017 -Slab casting work done at first floor.23 Nos RCC pile cap has been caste.bar work is running for retaining wall. 20.04.2017 -33 Nos RCC pile cap has been caste.Rebar work is running for Gantry structure.Shuttering work is going on for boundary wall.Sand filling work is going on. 27.04.2017 -02 Nos boundary gate column and 04 Nos guard house column casting is completed. -Mosaic work is going on.paint work is going on. -Control building right side plaster work is going on. -Control and power cable trench plaster work and tra work is completed. -02 Nos mk box work completed -Sand filling is going on. 04.05.2017 -08 Nos base casting work has been completed for Gantry tower.30ft long & 5ft height retaining wall work has been completed 08 Nos column casting work is continuing at control building 2nd floor. 11.05.2017 -04 Nos column casting work has been completed.Rebar work is going on at retaining wall. 18.05.2017 -40% retaining wall has completed. 12Nos column cast has completed at control building in first floor.Sand filling work is going on. 25.05.2017 Boundary wall plaster work, Fencing work, electrical wiring ,sanitary work for control building is going on.01 No Bath room tiles work & RCC casting work has been completed.15 Nos Fencing RCC column casting has been done. 01.06.2017 Boundary plaster work is going on.Mosaic work at first floor & Celling work has been completed.Paint work & Fencing work is going on. 01 No bathroom & complain room work is completed. 08.06.2017 Boundary plaster work, paint work is going on.Mosaic work for ground floor, celling work,2 bathroom and office and rest room work, Fire alarming work, Fencing brick work, Window Thai work for Ist floor,02 Nos pit work has been completed.Surface drain work is going on for out side of control building.Guard house 10 mm brick work is completed. 15.06.2017 Boundary plaster work, paint work & Guard house plaster work is going on.Control building front side surface drain and apron work,SS work, Window Thai work for ground floor,AC connection work,Electrical wiring, fitting work, switch yard flat soling and NFC work (half) for laying gravel stone work has been done. 22.06.2017 -Boundary plaster work and paint work is going on.Switch yard flat soling and ncf work has been completed for laying gravel stone.Guard house plaster work has completed . 29.06.2017 -Boundary plaster work & paint work is going on. -Pump house has been completed. -Earth cutting work is going on for boundary surface drain. 06.07.2017 -Boundary outside plaster work is going on. paint work is going on. swing door work is going on. guard house thai work is going on. surface drain work is going. 13.07.2017 Boundary outside plaster work is complete. Lime terracing work is going on. 4nos pit work is complete surface drain plaster work is complete. | 13.07.2017 Gantry tower casting complete(8Nos). 50% sand filling complete. RCC casting of retaining wall(Continuously) 90% complete. Ceiling plaster complete(Ground floor). Brick masonry for ground floor ( ground to lintel). | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
82 | 1.3 | DDP (Nayarhat, Birulia, Jalshiri & Nazarpur) | Jalshiri Project Manager Md.Azharul Haque 01732761574 Shafiul Azam- 01755506232 Sae-Nurislam 01883506757 | 26.10.2016 -CC work is complete, 06 Nos of base ready for casting of control building. 03.11.2016 12 Nos of short column casting is complete of control building, 05 Nos of CC work is complete for gantry foundation. 10.11.2016 -12 Nos of base casting complete of gantry foundation, preparation is going on for grade beam casting of control building. 17.11.2016 -02 Nos column of gantry foundation, one base of transformer foundation and grade beam of control building casting is complete. 24.11.2016 -Gantry tower and Main building of 04 nos of Column shuttering is completed. -XFR foundation partially complete. 01.12.2016 -Septic tank bricks work is going on. 08.12.2016 -72 m3 Back filling done for gantry tower area. -Popping work is going on for roof beam -Septic tank brick work is going on. -04 Nos column (half of above) of control building shuttering is complete.Grade beam & column stirrup. -02 pcc casting complete for CB,CT,LA and CB,CT base. -Earth excavation is going on for boundary wall. 15.12.2016 -Earth excavation work is going on for boundary wall.Casting work is complete for CB, CT, LA & CB, CT Base foundation & control room 03 nos column (half of above).Frame work is going on for 1st floor beam. 22.12.2016 Earth excavation work is going on for boundary wall. Casting work is complete for CB, LA & CB, CT column foundation & 08 Nos boundary wall column base foundation. Form work is complete for 1st floor beam & slab.Rod fabrication is going on for 1st floor beam. 29.12.2016 Earth excavation work is going on for boundary wall north side. Casting work is complete for 04 Nos CB wall 01 Nos CT, LA column.Form work is complete for first floor beam,slab and satir.we are ready for first floor slab casting. 13 Nos boundary column base pcc casting is complete. 05.01.2017 -Earth excavation work is going on for boundary wall north side Casting work is complete for 1st floor slab,stair 08 Nos base and 6 Nos column for boundary wall. 13 Nos pcc casting is complete for boundary base. 12.01.2017 -Earthing connection works has done for power cable in Search monitor. 19.01.2017 -02 Nos XFR floor.08 Nos control room column and 15 Nos boundary base RCC casting has been completed.12 Nos PCC for boundary wall has done. 26.01.2017 -Frame work is going on for 06 Nos control building column,and 06 Nos short column for boundary wall. 02.02.2017 -Roof slab and stair slab casting is complete.03 nos column casting is complete for control building 1st floor.01 nos casting is complete for transportation foundation floor side wall. 16.02.2017 -11 Nos base,20 Nos short column RCC casting has been completed.Earth excavation in front side & 250 mm bricks works is going on for boundary wall.Sand filling and mechanical structure work is going on. 23.02.2017 -Sand filling is going on, -09 Nos base RCC casting is completed for boundary wall,Rod binding is going on for 2nd grade beam.ground floor ceiling plaster,250 mm brick works height 600mm & sand filling is completed for 08 nos gantry tower. 02.03.2017 -Ground floor brick flat soling & rod binding work has been completed.Auxiliary TR work,First floor brick work,Sand filling work and control cable trench work is going on. 09.03.2017 -11 Nos short column,01 Nos grade beam Rcc casting is complete for boundary wall. Ground floor and ramp Rcc casting is complete. 1st floor brick work is going on. 03 Nos sunshade casting is complete. Sand filling is going on. Roof top parapet brick work is complete. 16.03.2017 -13 Nos short column Rcc casting is completed for boundary wall. 1st floor & ground floor brick work is going on. 05 Nos sunshade casting is completed. -Sand filling is going on. -10 m control cable trench wall RCC casting is completed. front side boundary wall brick work is completed (1st to 2nd GB). 23.03.2017 -14 Nos long column RCC casting is completed for boundary wall. 1st floor brick work completed & ground floor brick work is going on. 04 Nos guard house short column casting is completed. Sand filling is going on.8 m control cable trench wall RCC casting is completed. 30.03.2017 -14 Nos long column RCC casting is completed for boundary wall.ist floor plaster work is completed. ground floor 2 Nos false slab and 03 Nos casting work is completed. south side brick work is going on for boundary wall.sand filling is going on. control and power cable trench work is going on.30m Grade Beam casting is completed for boundary wall. 06.04.2017 -21 Nos long column RCC casting is completed for boundary wall. Ground floor plaster work is going on. Front side brick work is going on for boundary wall.sand filling is going on. control and power cable trench work is going on.35 m g.b casting is completed for boundary wall. 13.04.2017 21 Nos long column RCC casting is completed for boundary wall.brick work is going on for boundary wall.Sand filling is going on.Control and power cable trench work is going on. 20.04.2017 -02 Nos long column RCC casting is completed for boundary wall.Brick work is going on for boundary wall. Sand filling is going on.Control and power cable trench work is going on.Sanitary work is going on. -Building plaster work is going on. 27.04.2017 02 Nos & 04 Nos RCC casting has completed for gate column & guard house column.Plaster work is continuing in Boundary wall & control building right side. 150 ft coping cast work has been done. 04.05.2017 -150 ft coping & 75 ft guide wall casting has been completed.Rain water pipe has completed.Sand filling work & mosaic work is going on at control building right side. 11.05.2017 -Boundary coping casting work and Duct work has been completed. Mosaic work,Paint work, Fencing brick work is going on. 3 side control building apron work is completed. Sand filling and internal road guide wall has been completed. 18.05.2017 -Road guide wall & leveling dressing is completed.herring brick work is going on.Facing tiles & paint work is going on.Mosaic cutting has completed.Guard room drop wall casting is completed.Deck wall plaster,boundary plaster is going on. 25.05.2017 25 Nos pile cast has been done.15 Nos short column cast work has done at top of grade beam. 01.06.2017 16 Nos pile casting for control room.01 No grade beam casting for boundary south side.03 Nos long column casting for boundary north side. Earth work is continuing for retaining wall. 15.06.2017 73 m base cast work for retaining wall.05 Nos long column casting has been completed for boundary. 22.06.2017 -02 Nos long column cast has been completed.01 m height & 43 m length retaining wall steam has done. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -45m lenth,01m height retaining wall work has done.Brick work has done at boundary wall.05 base CC casting has done. 13.07.2017 Retaining wall stem casting length -25m, height-1m.Control building 6 base casting.CC casting for another retaining wall road side. | 13.07.2017 Boundary outside plaster work is complete. Lime terracing work is going on. 4nos pit work is complete surface drain plaster work is complete. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
94 | 1.4 | DDP (Nayarhat, Birulia, Jalshiri & Nazarpur) | Nazarpur Project Manager Md.Azharul Haque 01732761574 SAE. Monjurul-01766736720 Shafiul Azam- 01755506232 | 20.10.2016 26.10.2016 03.11.2016 Site is under water. 10.11.2016 Soil test is going on from 07Nov,2016. 17.11.2016 -Soil test is complete and earth filling preparation is going on. 24.11.2016 -Pipe setting (7400 ft ) work done for dredger.Land measure work doing for doing the remaining sand filling. 01.12.2016 -Approximate 18600 cft Sand filling work done. 08.12.2016 -Sand filling done approx. 1,23,300 cft. 15.12.2016 -Sand filling done approx 2,25,000 ( 1,09,700 cft this week). 22.12.2016 -Sand filling done approx. 36,300 cft. 29.12.2016 -Sand filling done approx. 83300 cft. 05.01.2017 -Earth filling work has done. 12.01.2017 -Temporary Office room,Labour shed and Materials shed has maked. 19.01.2017 -House for piling is under process. 02.02.2017 -Pile work & boundary wall work is going on. 09.02.2017 -No further update. 16.02.2017 -Submersible pump has been installed. 23.02.2017 -No further update. 02.03.2017 -Making of new platform for rod placing(70’ x 30’). -Site layout has been completed. 09.03.2017 -Soil digging work done for pile point. -Rod,Cement arrived at site. 16.03.2017 -No further update. 23.3.2017 -70 Nos pile point has make,Stone,Sand arrived at site. 30.03.2017 -25 Nos pile point has been made-Stone, Sand arrived at site. 06.04.2017 -Soil excavation work done for base foundation both (north,south) side, 13.04.2017 20 Nos base shuttering work has been done at boundary wall. 20.04.2017 19 Nos CC work has been done in base at boundary wall.10 Nos rod binding work has been done in base at boundary wall. 27.04.2017 -14 Nos base casting work has been done for boundary wall.Rod binding work is going on. 04.05.2017 -04 Nos base and 19 Nos short column casting work has been done for boundary wall. 11.05.2017 -03 Nos base casting work has been done for boundary. 01 No grade beam casting & 09 Nos short column cast has been completed in up grade beam.01 No pile has been cast (size-400*400*700). 18.05.2017 -35 Nos pile work has been cast.02 Nos grade beam cast in boundary wall. 25.05.2017 Air conditioner fitting work is going on. New electrical wiring work is continuing. 01.06.2017 Air conditioner fitting work and Electrical work is continuing. 08.06.2017 Air conditioner fitting work is continuing. 15.06.2017 -Air conditioner fitting work is going on. 22.06.2017 -No further update 29.06.2017 -No further update. (01 Air conditioner yet to be installed.) PDB Division-04 will be shift to Bindur more. 06.07.2017 13.07.2017 -No further update, | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
106 | 2 | Bindur Mour, Rajshahi | Rajshahi Project Manager Md.Azharul Haque 01732761574 Selim 01787680493 | 26.10.2016 -Control wiring is delayed due to control cable and it's accessories. 03.11.2016 -Control cable arrived at site, wiring going on, 33 & 11 kV GIS panels are waiting for vacuum pump for gas filling and electrical operation, order of power cable plug placed to Engr Reza, 33 kV 300 rm & 11 kV 500 rm Power cable arrived at site, slab for septic tank & sock well casting complete. 10.11.2016 Panel wiring complete, remaining earthing work going on, gas filling start from 08 Nov,2016. 17.11.2016 -Gas filling complete except one panel,Power cable laying processing going on. 24.11.2016 -Auxiliary Transformer carrying to site.Power cable (300rm,500rm) laying done for 33kV & 11kV. 01.12.2016 -33/11 kV electrical site GIS test completed.Cable ladder making work going on.XFR shifted to katakhali from Bindurmour. 08.12.2016 -TR:1 XFR have been installed.Control cable wiring is completed in Tap changer MRL box.02 Nos Fan fitting completed.02 Nos of dropout wall mount fuse have been installed for auxiliary XFR. 15.12.2016 -260 m Cable laying (120rm) from auxiliary XFR to AC distribution panel going on.Pipe fittings completed for auxiliary XFR.Jumping wire/ hook up work done for LA to isolator. 22.12.2016 -Auxiliary & 11kV out site power cable termination completed. 29.12.2016 -Termination has been done for XFR (11kV,33kV) part in side of control room. 05.01.2017 -Motor coil repair work has done in side of GIS. 12.01.2017 -Earthing work has done for power cable near pole area. 19.01.2017 -No update yet. 26.01.2017 -Fire fighting work is going on. 02.02.2017 -Fire fighting work is continuing in control building. 09.02.2017 -Fire fighting set-up work is continuing in control building. 16.02.2017 -04 Nos Air-conditioner has been installed. 23.02.2017 -Air-conditioner work is going on. 02.03.2017 -Channel work for Air-conditioner work is going on. 09.03.2017 Fire fighting set-up work is continued in control building. 16.03.2017 23.03.2017 30.03.2017 -No further update. 06.04.2017 -CC work is going on in ground floor. 13.04.2017 -GIS termination work is going on.Pad stone work has been for 2Nos XFR & Auxiliary XFR. 20.04.2017 -GIS termination and Pad stone work has been completed. 27.04.2017 -Pre commissioning work is going on. 04.05.2017 -Pre commissioning work has been finished. 11.05.2017 -Air conditioner fitting work is going on.PVC pipe has been laid from ground floor MDB box to first floor DB box. 18.05.2017 -No further update. 25.05.2017 Retaining wall second lift has completed. Plaster work has been completed in control building first floor. As installed work has done.CC cast work done for all cable trench. 01.06.2017 Plaster work is going on at first floor in control building.Brick work has been finished at ground floor in control building. 08.06.2017 Plaster work is going on at ground floor in control building.Facing brick work is going on.Slab work is continuing for cable trench. 15.06.2017 Ground floor plaster work done.First floor tiles work done, Safety tank brick work done. DS & CB erection work done. 22.06.2017 -Tiles work has done at control building. Facing brick work done at out side. Ground floor plaster work has been done.Window setting work has been completed. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -Plaster work has been done.Facing brick work has been completed. 13.07.2017 Control room building out side plaster work running.Retaining wall grad beam 2 casting running.Erection work running.Earth boring work running. | 13.07.2017 -No further update, | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
| 3 | Supply,Installation,Testing & Commissioning of 33/11 kV, 2x10/14 MVA, Substation on Turnkey under Dhaka PBS-1 | SAVAR-16(Nabinagor) Project Manager Md Azharul Haque 01732761574 Sae,Shahjalal 01755445178 | Supply,Installation,Testing & Commissioning of 33/11 kV, 2x10/14 MVA, Substation on Turnkey under Dhaka PBS-1 Client-BREB | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
| 4 | Turnkey contract for design,supply,construction,Installation,Testing & Commissioning for 33kV Bay Extension work and Bus-Bar related works at PABNA 132/33 kV Grid substation for PABNA PBS-1 & 2 under BREB. Client–BREB | PABNA Project Manager Md Azharul Haque 01732761574 Sae,Rahul bishwas 01708131718 | Turnkey contract for design,supply,construction,Installation,Testing & Commissioning for 33kV Bay Extension work and Bus-Bar related works at PABNA 132/33 kV Grid substation for PABNA PBS-1 & 2 under BREB. Client–BREB | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
118 | 5.1 | CSDP (Banskhali, Dagonbhuyan ,Daudkandi ,Sylhet) | Banskhali Project Manager Shafiq Ahmed 01713147024 | 16.10.2016 Earth filling is going on.Materilas mobilization started. Pilling team also mobilized. Hope the piliing can be started from 18 Oct 2016. 23.10.2016 -Civil works started. 27.10.2016 -Pilling work start. 03.11.2016 Pilling work going on. 10.11.2016 -Pilling work running. 17.1.2016 -Boundary wall piling is continued (46 Nos complete.) -Land filling halted for local govt. administration interference. 24.11.2016 -Civil works continued. 01.12.2016 -90 Nos of piling completed of boundary wall out of 111 Nos. -Land Filling continues. 08.12.2016 -Pile work for Boundary wall have been completed. 15.12.2016 -Pile head breaking work has been completed in retaining wall area.Sand filling continuing. 22.12.2016 -Boundary retaining wall work is continued.Building pile work has been done.-Back filling work is going on for switch yard area. 29.12.2016 -Switch yard Gantry foundation work has been continued. 05.01.2017 -Boundary wall Piling Head broken has Continue. -Land Filling stop, For local administration. -4 Nos base has complete for Gantry foundation. 12.01.2017 -Sand filling has continued. -Boundary wall Piling Head broken has Continued. -Gantry foundation. 50% has complete. 19.01.2017 -XFR foundation work is continued.VCB foundation work is going on.Pile cap breaking work of control building is continued. 26.01.2017 -Building pile head broken work has completed. -01 No foundation & base work has been done for XFR.Sand Filling is continuing. 02.02.2017 -Sand filling is continuing. -Building pile cap CC work has completed.Civil works for CB foundation has been completed. 09.02.2017 -02 Nos CB foundation work has been done.06 Nos building base has been completed. 16.02.2017 -Same as before. 23.02.2017 -Back filling work done approx.3500ft.01 No XFR pad making done. Base,grade beam,long column,short column is completed in control building. 02.03.2017 -Preparation work has been done for Roof top Casting. -XFR set on pad. -Gantry structure ,tower beam has been completed. 09.03.2017 -Retaining wall works is going on. -Slab works is going on for building 2nd floor, -Structure has been completed for tower beam. 16.03.2017 -Preparation work for 2nd floor casting. 23.03.2017 -Retaining wall work is going on. 30.03.2017 -Casting work for Retaining wall is going on. 06.04.2017 -Casting work for Retaining wall is going on. Brick work for control building has been continued.Cable work is going on. 13.04.2017 53m Retaining wall work has been completed. Building bricks works & cable trench works is going on.Safety tank & soak coil work going on. 20.04.2017 -Retaining wall and Building bricks works is going on. 27.04.2017 -Brick work is continuing for control building.Retaining wall work has been done in control building. 04.05.2017 -13m base casting done for cable trench work.Brick wall work has been done first floor of Control room building.XFR base-2 column has been completed.All Base work has been completed in ground floor of control building. 11.05.2017 -Brick wall work is continuing for control building.RCC casting work has been done in Cable trench at Switchyard.RCC casting work has been completed in retaining wall. 18.05.2017 -Plaster work is going on at control building. Cable trench work is going on. 25.05.2017 Out side Plaster work is going on at control building. Cable trench work has been completed. 01.06.2017 Tiles work is going on.Column casting at XFR foundation. 08.06.2017 Tiles work is going on. Surface drain & Toilet tank making work is going on. 15.06.2017 Brick wall making work is going on.Column work has been completed for XFR.Surface drain work and Sand filling work is continuing. 22.06.2017 -Sand filling work is continuing.Brick wall work is going on. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 XFR foundation base column,Sand filling work is going on.Building brick work is going on. 13.07.2017 Wiring work running. Mechanical work running.Earth-ing 85% work finished.Building paint work running. | 13.07.2017 Control room building out side plaster work running. Retaining wall grad beam 2 casting running. Erection work running. Earth boring work running. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
130 | 5.2 | CSDP (Banskhali, Dagonbhuyan ,Daudkandi ,Sylhet) | Dagonbhuyan, Feni Project Manager Shafiq Ahmed 01713147024 | 16.10.2016 -Earth Filling is going on. Started mobilization, Layout given. Pilling works can be started at the earliest. 23.10.2016 -Civil works started. 27.10.2016 -Mobilization complete. 03.11.2016 - Pile work will be started on 08 Nov,2016 (Expected) 10.11.2016 -Pilling work going on. 17.11.2016 -Boundary Piling Continues. -Land Filling not continued for payment. 24.11.2016 -Civil works continued. 01.12.2016 -Building & Boundary wall Piling Completed.Land Filling is continuing. 08.12.2016 -Switchyard foundation work is going on. 15.12.2016 -Pile head broken work has completed in retaining wall area.Switchyard foundation work is going on.Sand filling continuing. 22.12.2016 -Boundary retaining wall work is continued.Switchyard foundation work is going on -Back filling work is going on for switch yard area. 29.12.2016 -Switch yard Gantry foundation work has been continued. 05.01.2017 -Boundary Retaining wall RCC complete only top cover incomplete.Transformer foundation has continue -Building Colum Base CC has completed.Land Filling stop, For local administration.4 Nos base has complete for Gantry foundation. 12.01.2017 -Switchyard foundation work has 70% completed. -Rod cutting and other preparation work has started for Control building. 19.01.2017 -Column and base work has been completed in control building.Sand filling continued for switch yard. 26.01.2017 -Building grade beam & shutter column work has completed.Sand Filling is continuing. 02.02.2017 -Column work has been done in first floor.Beam shuttering work is going on in first floor. 09.02.2017 -Slab work & rod binding work is continuing at first floor. 16.02.2017 -Preparation work is going on for RCC Casting.Tower erection work is going on. 23.02.2017 -RCC casting is going on in control building first floor roof.XFR top base plate setting work is going on, 02.03.2017 -Rod binding work has been doing for column.Column Structure work done for beam. 09.03.2017 -Slab works is going on for building 2nd floor, -Structure has been completed for switchyard. 16.03.2017 -2ND floor casting has been done. 23.03.2017 -Brick work for building and Electrical work is going on. 30.03.2017 -Brick work for control building.Coffin cast for retaining wall. 06.04.2017 -Brick work is going on for control building.Coffin cast for retaining wall. 13.04.2017 Building bricks works & cable trench works is going on. 20.04.2017 Building bricks works is continuing. 27.04.2017 Bas errection work is continuing.Brick work is continuing for control building. 04.05.2017 -Bas bar errection work has been completed.Brick wall work is continuing for control building.Power cable trench work is going on. 11.05.2017 Plaster work is going on at control building.Cable trench work is going on. 18.05.2017 Plaster work is going on at control building. Cable trench work is going on. 25.05.2017 Control building brick work. Lenten & sun shed RCC cast work has been done. 01.06.2017 Control room brick work & plaster work has been done.Grill fittings work has been done at ground floor in control building.Filling work is going on.Brick work & plaster work for retaining wall is going on. 08.06.2017 Plaster work for control building,Base wall cast has been done for Retaining wall & guide wall. Limestone cast has been done at control building roof top. Sand filling work is continuing. 15.06.2017 Control room first floor plaster completed.Tiles work & Cable trench work is going on.Roof slab lime terracing Pump boring has been completed. Approach road filling work filling work on going. 22.06.2017 -Tiles work & Cable trench work is going on. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -Boundary wall rod binding work is going on.Plaster work for control building. 13.07.2017 Civil work running. Control room plaster work running. Boundary wall plaster running.Fencing post column running. | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
142 | 5.3 | CSDP (Banskhali, Dagonbhuyan ,Daudkandi ,Sylhet) | Daudkandi Project Manager Shafiq Ahmed 01713147024 Site Engr Golam Morshed-01787687953 | 16.10.2016 -Layout given on Oct09, 2016 but it was changed by REB on Oct10,2016. As per new layout earth filling area will be increased & civil design needs to be changed. Letter given to REB .Contractor:Builders Aid 23.10.2016 27.10.2016 -No further update 03.11.2016 -Revised drawing submitted. 10.11.2016 -Earth filling start. 17.11.2016 -Site Mobilization Complete. -Land Filling continues. 24.11.2016 -No further update. 01.12.2016 -Electricity line, Labor Shade, Temporary Water Pump are complete.Land Filling continued. 08.12.2016 -Earth filling is going on. -Approach road making work is continued. 15.12.2016 -Switchyard foundation work is going on.Sand filling continuing. 22.12.2016 -Switchyard foundation work is continued.Sand filling work is continued. 29.12.2016 -Building finishing work has been continued. 05.01.2017 -6 Nos base has complete for Gantry foundation.Transformer foundation has continue. -CB foundation work has continued.Land Filling has continue. 12.01.2017 -Foundation of gantry structure has completed. -VCB foundation work has been completed. -XFR foundation work has done approx. 70%. -Sand filling has continued. 19.01.2017 -Sand filling is going on. 26.01.2017 -Cable trench slab making work is continuing. -Sand Filling is continuing. 09.02.2017 -Pile work has completed for control building. 16.02.2017 -Pile work has been done for control building & retaining wall.Cable trench work is going on in side of switchyard. 23.02.2017 -Cable trench work has been done in side of switchyard.06 Nos pile cap work is done at control room.approx.50% Back filling work is done. 02.03.2017 -Grade beam of control room RCC casting work has been done.01 No XFR top pad RCC casting work done. 09.03.2017 -Slab works is going on for building 1st floor, 16.03.2017 -Roof casting work is going on,Earth excavation for retaining wall is going on. XFR arrived at site. 23.03.2017 -10m Column casting work has done for retaining wall.Gantry structure work is going on. 30.03.2017 -Partial Column casting work has done for retaining wall.12 Nos column has done in Ist floor for control building. 06.04.2017 -Creeker work for column, Roof slab work has been done.CC casting work is going on for Safety tank. 13.04.2017 -Second floor casting has been completed.Retaining wall & Boundary wall work is going on. 20.04.2017 -Retaining wall work is going on.Ceiling plaster work has been done. 27.04.2017 -Brick work is continuing for Boundary wall. 04.05.2017 -Sand filling work is going on in control building.Retaining wall work is continuing (brick work, base foundation, grade beam etc.) 11.05.2017 -Plaster work has been completed at Control building.Guide wall making work is going on. 18.05.2017 -Brick work for control building is going on.Boundary wall brick work, column work & beam work is going on. 25.05.2017 Lenten and Brick work is going on at ground floor. Cable trench CC & Rod binding work has been completed.Sand filling work is going on. 01.06.2017 Brick work is going on at first floor in control building.Centering open work has been completed at first floor. 08.06.2017 Brick work has been finished for control building 2nd floor.Cable trench wall casting work has been done. 15.06.2017 Plaster work has been completed at ground & first floor in control building. 22.06.2017 -Plaster work & finishing work has been done at control building. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 Saftitank,Toilet making work has been completed.Electrical wiring preparation work is going on. 13.07.2017 Building outside plaster, Toilet roof , parapet wall work running. | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
154 | 5.4 | CSDP (Banskhali, Dagonbhuyan ,Daudkandi ,Sylhet) | Sylhet Project Manager Shafiq Ahmed 01713147024 | 23.10.2016 -Contractor not yet started mobilization. 27.10.2016 -Mobilization Started. 03.11.2016 -Mobilization completed. 10.11.2016 -Mobilization going on 24.11.2016 -No further update. 01.12.2016 -Site Mobilization Complete. -Pile Purpose soil digging continued. 08.12.2016 -Switchyard foundation: soil digging work is going on. 15.12.2106 -Building pile work is going on. 22.12.2016 -Switchyard gantry foundation work is going on.Boundary pile work is continued.Pile for building work has been completed. 29.12.2016 -XFR base RCC work has going on. -Foundation work is continued. 05.01.2017 -03 Nos Gantry base RCC work has done.43 Nos of Boundary Pile has done. -Building pile head broken work has continuing. 12.01.2017 -CC casting work has continued for Retaining wall. -CC work has started after pile cap broken. 19-01-2017 -Retaining wall work is continued.04 Nos Switchyard gantry foundation work is completed.Building column’s CC casting work completed. 26.01.2017 -06 Nos Building base has been completed. -Boundary retaining wall base has been completed. -04 Nos Switchyard gantry foundation work is completed. 02.02.2017 -Retaining wall works is going on.XFR foundation work is continuing. Building all base has been complete. 09.02.2017 -Retaining wall works is going on approx.310 ft. & 6 ft.height done.Grade beam rod binding work is going on. 16.02.2017 -Approx. 80% of Retaining wall work has done. 23.02.2017 -Approx. 90% of Retaining wall work is done. 02.03.2017 -07 Nos gantry tower foundation work done. 16.03.2017 -Foundation work is going on for XFR.Retaining wall work is going on.20% wok done for control building. 23.03.2017 -Shuttering work has been done for first floor slab. 30.03.2017 -Rod binding work is going on for control building Ist floor. 06.04.2017 -Preparation work is going on for RCC casting (centering) in control room first floor. 13.04.2017 -Tower errection work is going on.First floor slab casting has been completed. Second floor column work is going on. 20.04.2017 -Guide wall has been make in XFR.Control building 2nd floor column work is going on.Structure work has been done for gantry tower, beam switchyard. 27.04.2017 -Control building 2nd floor column work has been completed & slab shuttering work is going on.Conservator, radiator accembelling work is continuing in power XFR. Tower beam structure work has been done at switchyard. 04.05.2017 -Guide wall work has been completed for XFR-1. Shuttering work is going on at 2nd floor in control building. 11.05.2017 -First floor roof RCC casting work has been completed. Stair roof also RCC casting has been done.Sand filling work done in side the control building ground floor room.Brick wall work is going on. 18.05.2017 -RCC cast work has been done in ground floor.Brick work is continuing. 25.05.2017 13 Nos 11kv AIS breaker installed at channel. Ground floor cast has done.Road crossing work is going on. 01.06.2017 Road casting work is going on.Brick wall work is continuing.33kV control panel is placement has been completed. 08.06.2017 Control panel wiring is going on. 15.06.2017 33kV control panel wiring is continuing.Brick wall & plaster work is continuing of new building. 22.06.2017 -33kV control panel wiring work is going on.Brick wall & plaster work has been completed. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -33 kV GIS & 33 kV control Panel wiring is going on. 13.07.2017 Ground floor and 1st floor plaster completed.Outside building plaster running.Floor tiles work running. | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
166 | 6 | 33kV GIS & 11kV AIS installation at Shyampur | Shyampur Project Manager Shafiq Ahmed 01713147024 | 23.10.2016 -Contractor not yet started mobilization. 27.10.2016 -Mobilization Started. 03.11.2016 -Mobilization completed. 10.11.2016 -Mobilization going on 24.11.2016 -No further update. 01.12.2016 -Site Mobilization Complete. -Pile Purpose soil digging continued. 08.12.2016 -Switchyard foundation: soil digging work is going on. 15.12.2106 -Building pile work is going on. 22.12.2016 -Switchyard gantry foundation work is going on.Boundary pile work is continued.Pile for building work has been completed. 29.12.2016 -XFR base RCC work has going on. -Foundation work is continued. 05.01.2017 -03 Nos Gantry base RCC work has done.43 Nos of Boundary Pile has done. -Building pile head broken work has continuing. 12.01.2017 -CC casting work has continued for Retaining wall. -CC work has started after pile cap broken. 19-01-2017 -Retaining wall work is continued.04 Nos Switchyard gantry foundation work is completed.Building column’s CC casting work completed. 26.01.2017 -06 Nos Building base has been completed. -Boundary retaining wall base has been completed. -04 Nos Switchyard gantry foundation work is completed. 02.02.2017 -Retaining wall works is going on.XFR foundation work is continuing. Building all base has been complete. 09.02.2017 -Retaining wall works is going on approx.310 ft. & 6 ft.height done.Grade beam rod binding work is going on. 16.02.2017 -Approx. 80% of Retaining wall work has done. 23.02.2017 -Approx. 90% of Retaining wall work is done. 02.03.2017 -07 Nos gantry tower foundation work done. 16.03.2017 -Foundation work is going on for XFR.Retaining wall work is going on.20% wok done for control building. 23.03.2017 -Shuttering work has been done for first floor slab. 30.03.2017 -Rod binding work is going on for control building Ist floor. 06.04.2017 -Preparation work is going on for RCC casting (centering) in control room first floor. 13.04.2017 -Tower errection work is going on.First floor slab casting has been completed. Second floor column work is going on. 20.04.2017 -Guide wall has been make in XFR.Control building 2nd floor column work is going on.Structure work has been done for gantry tower, beam switchyard. 27.04.2017 -Control building 2nd floor column work has been completed & slab shuttering work is going on.Conservator, radiator accembelling work is continuing in power XFR. Tower beam structure work has been done at switchyard. 04.05.2017 -Guide wall work has been completed for XFR-1. Shuttering work is going on at 2nd floor in control building. 11.05.2017 -First floor roof RCC casting work has been completed. Stair roof also RCC casting has been done.Sand filling work done in side the control building ground floor room.Brick wall work is going on. 18.05.2017 -RCC cast work has been done in ground floor.Brick work is continuing. 25.05.2017 13 Nos 11kv AIS breaker installed at channel. Ground floor cast has done.Road crossing work is going on. 01.06.2017 Road casting work is going on.Brick wall work is continuing.33kV control panel is placement has been completed. 08.06.2017 Control panel wiring is going on. | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
190 | 7 | Gazaria S/S | Gazaria Project Manager Shafiq Ahmed 01713147024 Site Engr Golam Morshed-01787687953 | 16.10.2016 -Ground floor & 1st floor brick work completed & 2nd floor brick works completed upto 50%. Cable trench completed near about 80%. 23.10.2016 -Brick work of control room completed. 27.10.2016 -Finishing work running. 03.11.2016 Inside plaster work completed. Equipment installation going on. 10.11.2016 -Building finishing work going on. 17.11.2016 -Civil works 80% done. -Installation work 60% done. 24.11.2016 -Civil works going on. -Installation work running. 01.12.2016 -Control room Grill fixing on the windows are complete.Gantry finishing work running.cable trench finishing work 60% complete -boundary wall complete but 1 column (& 1 section).soak well works running.tiles fittings going on .parapet 70% complete. 08.12.2016 -Boring work for earthing is going on.Indoor breaker materials arrived at site. 15.12.2016 -Plaster work is going on in Control building Out side wall.Soil digging has been done for foundation wall.LA has bee Installed. 22.12.2016 -Digging work is running for surface drain.Plaster & tiles work of control building is going on.Power cables reached at site. 29.12.2016 -Mesh earthing work has been continued. -Base casting has worked in Fancy boundary. -Control building out side plaster is going on. 05.01.2017 -CC work has been done for Surface drain, Soak coil / septic tank.Brick work for guard room wall has completed. 12.01.2017 -Trench work is running in 2nd floor of control building. -Bas bar setting ,fittings work has completed.01 Nos of VCB set ,33kv relay panel outgoing has shifted to Chittagong PBS by order of System operation (KE O) office,REB ,Dhaka. 19.01.2017 -Control room paint work has been done.Control cable works is going on.Surface Drain, fencing,guide wall, stair railing , & side dressing levelling works is going on. 26.01.2017 -Surface drain work is going on.Finishing work has been completed in Guard room. 02.02.2017 -Window Thai glass materials has arrived at site.-Facing bricks work is going on.Paint work is going on in boundary wall, control room. 09.02.2017 -Patent stone CC work has completed in control building roof top.Facing brick wall work is going on. 16.02.2017 -Facing brick wall work is going on.Main entrance road making work is going on. 23.02.2017 -False ceiling work has been done in control room.Brick soling work is going on. 02.03.2017 -30% road casting work has been done. 09.03.2017 -100% road casting work has been done.Paint work is going on (final part).Finishing works is going on for Tiles. 16.03.2017 -Switchyard soling finished. -Surface drain done,building paint & tile,plumbing, electrical work is going on. 23.03.2017 -Paint and fencing work has been finished. 30.03.2017 -Brick soling work is going on for S/Y.Electrical work is going on in control building. 06.04.2017 -Preparation work has been done for Commissioning,Approx. Commissioning date will be 10 april,2017. 04.05.2017 -All civil works has been completed.(Gravel work yet to be done). 13.04.2017 -Commissioning done at 10 april,2017. 20.04.2017 to 25.05.2017 -No further update. 01.06.2017 File submitted to Comilla REB office for close out at 01 June,2017. 08.06.2017 -Close out has been completed at 08 June,2017. 15.06.2017 -As built drawing work is going on. 22.06.2017 -No further update. 29.06.2017 -As built drawing Submitted at Comilla REB office at 23 june,2017. -No further update. 06.07.2017 -Remaining bill submitted at comilla BREB office. 13.07.2017 -Same as before. | 13.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
202 | 8 | Bay Extension at Jangalia | Comilla (South) Jangalia Project Manager Shafiq Ahmed 01713147024 Site Eng. Belal- 01680850676 | 16.10.2016 -Control-protection wiring will be completed within next 2 days 23.10.2016 27.10.2016 -control protection wiring completed. 03.11.2016 -Pre commissioning test can be started within 2/3 days. 10.11.2016 -Pre-commissioning will be done by 15Nov,2016. 17.11.2016 -Pre commissioning date will be 22 Nov 2016. 24.11.2016 -Pre-Commissioning going on. 01.12.2016 -Pre-Commissioning done. 1 Incoming & 1 out-going internal connection incomplete,Bus-section DS not connected yet.Incoming overhead cable not installed yet. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 -No further update. 29.12.2016 -Requirements (3 Nos of pole with fittings) paper submitted to REB office,now file in PBS-2,Comilla. 05.01.2017 -Processing going on for Requirements (3 Nos of pole with fittings) paper submitted to REB office,now file in PBS-2,Comilla. 12.01.2017 -06 Nos of poles has been erected for bus to bus inter connection. 19.01.2017 -Preparation work done for 02 Nos Isolator installation. 26.01.2017 -2set new DS installation and 33kV bus change for interconnection, now bus to bus interconnection work is running. 02.02.2017 -33kV bus to bus inter connection work has been completed. 09.02.2017 -Pre parathion work has done for Shut down. 16.02.2017 -Jumpering work has been done for inter connection & LA , DS to LA & PI connection work done for underground feeder. 23.02.2017 -Apply for Commissioning at EX.EN, REB,Comilla. 02.03.2017 -Processing work is going on for Commissioning. 09.03.2017 -As same as before. 16.03.2017 -Processing work is going on for Commissioning. 23.03.2017 -Same as before. 30.03.2017 -Same as before. 06.04.2017 -Preparation work has been done for Commissioning, -Approx. Commissioning date will be 10 april,2017. ------------------ Commissioning done at 10 april,2017. 27.04.2017 to 18.05.2017 -No further update. 25.05.2017 -08 Nos Gas Cylinder has been installed.04 Nos halogen Light fitting work has done. 01-06.2017 Internal electrical connection work has been done between Breaker isolator-CT-PT. 08.06.2016 Panel test work has been completed. 15.06.2017 -No further update. 22.06.2017 -Pre commissioning work has been completed.Report has summited to REB office.Apply for get the Commissioning date. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 13.07.2017 -No further update. -No further update. | 20.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
214 | 9 | Feni Switching station | Feni Project Manager Shafiq Ahmed 01713147024 | 23.10.2016 -Boundary wall & store room building 40% completed. -New control room 60% completed. 27.10.2016 -Building brick works going on. 03.11.2016 -Brick work completed. Cable trench & finishing work going on. 10.11.2016 -Building finishing work going on. 17.11.2016 -Civil works 70% done. 24.11.2016 -Civil works going on. 01.12.2016 -Building finishing work going on. 08.12.2016 -Building finishing work continuing. 15.12.2016 -Brick work is continuing. 22.12.2016 -Building finishing work is going on.Tiles work has been continued. 29.12.2016 -Building finishing work is going on. 05.01.2017 -Building finishing work is continuing. 12.01.2017 -Out door fencing brick work is running for control building. 19.01.2017 -Out door fencing brick work & others finishing work is running for control building. 26.01.2017 Fencing brick works continues.False ceiling work going on. 02.02.2017 -Already took shut down for materials shifting to other place like Breaker,XFR etc. 09.02.2017 -Store room building broken work has been completed. -False ceiling work has been done. 16.02.2017 -New road making work approx. 50 % has been done.Earth excavation work run for foundation of Circuit breaker. 23.02.2017 -New road making work approx. 70 % has been done.Earth excavation work run aprox.90% for foundation of Circuit breaker. 02.03.2017 -Cable trench work is going on. 09.03.2017 -Road works is going on. 16.03.2017 -Same as before. 23.03.2017 -Road construction and Electrical work is going on. 30.03.2017 -Electrical equipment errection work has been done for 33kV AIS. 06.04.2017 -Electrical work is going on. 13.04.2017 -Civil works has been completed. Control wiring work is going on. 27.04.2017 -Control protection wiring is going on. 04.05.2017 -Control protection wiring work has been completed .Earthing work also completed. 11.05.2017 -Preparation work for shutdown. 18.05.2017 to 13.07.2017 -No further update. | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
226 | 10.1 | 3 S/S (Shitalakhya, Kamrangirchor & Dhanmondi) | Shitalakhya Project Manager Rabiul Alam , Mustafizur Rahman Mithu 01713147029 Site Engr --NAJMUL-01723598014 Kawser- 01676099541 | 23.10.2016 -No further update 30.10.2016 CT mounted on base, XFR to panel wiring done,132 kV DS measurement taken but not yet reached at site.Gantry tower installation done completely. 03.11.2016 Bus & wire hanging in tower(06pcs) is done. Old wall breaking for control panel board is going on. LA replacing to the other side, so making 03 new bases. 10.11.2016 DS setting on the structure. Cable wiring MK box to CT & circuit breaker is done. LA base reprocess(running) 17.11.2016 -LA structure,LA setting done.PI structure done. -Cable laying done from XFR MK box to main panel board. 24.11.2016 -132 kV control panel wiring. -Uper bus to DS wiring connection.Lower bus to DS wiring connection.Circuit breaker to upper bus wire connection.33kV LA & PI structure setting. 01.12.2016 -XFR breaker panel board installed. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 -Power cable is laying from XFR to panel board. -PI has been installed. -Earthing work is done for all panel. 29.12.2016 -Power cable, CT & Circuit breaker test has been completed. -Control panel board testing running. 05.01.2017 -XFR all types of test has completed.Relay test is going on. 12.01.2017 -All Relay test has done. 19.01.2017 -Paint work has been done for old Transformer.01.20 26.01.2017 -Paint work has been done for new XFR.180 m internal road has been make. 02.02.2017 -Drain work is going on beside the road. 09.02.2017 -Casting work is going on in XFR yard. 16.02.2017 -Base casting work has been done in switchyard. -02 Nos bus bar is running. -Drain work is going on the side of road. 23.02.2017 -No further update. 02.03.2017 -Gravel laid at switchyard. 09.03.2017 -No further update. 16.03.2017 -Gravel laid at switchyard. -XFR is Starting. 23.03.2017 -All work has been finished. 30.03.2017 -No further update. 06.04.2017 -GT is running. -Waiting for the Busbar protection work.(done by SIMENS). 50/75 MVA power XFR energized without bus bar protection work.(will be done by SIEMENS) 27.04.2017 to 06.07.2017 -No further update. | 20.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
238 | 10.2 | 3 S/S (Shitalakhya, Kamrangirchor & Dhanmondi) | Kamran girchar Project Manager Rabiul Alam , Mustafizur Rahman Mithu 01713147029 Site Engr -NAJMUL-01723598014 | 27.10.2016 -2 nos of towers & beams,CTs ,Breakers are installed with drive box. 03.11.2016 -C.T,Beaker, Transformer, Outdoor M.K box,132kV control panel wiring are completed .33 kV panels are installed (wiring not completed). 10.11.2016 -2 Set DS of Bus coupler are installed.33kV control panels are installed. Base for 7Nos of panel at first floor are completed. Cable trench for control cable at 1st floor completed. Ground floor mosaic.Gravel supporter grill are installed. 17.11.2016 -33kV Breakers are installed. -PI and LA structures are installed.Wiring running of 33kV Bus coupler breaker and control panel .Earth excavation for outdoor cable trench going on. 24.11.2016 -33kv breaker wearing are complete. -33kv controll panel wearing are complete (without AC distribution panel). -33kv LA are installed. 01.12.2016 -XFR ratio, winding resistance, insulation resistance,magnetic balance,HT-LT excitation, oil BDV, 33kV breaker meggar etc test completed. 08.12.2016 -132 kV CT testing has been done.33 kV CT & PT testing completed. 15.12.2016 -33kV control panel relay tasting completed.33kV PI are installed33kV power cable laying. 22.12.2016 -No further update. 29.12.2016 -No further update. 05.01.2017 -Short loop wiring has done from XFR to LA to CT to Breaker then DS. 12 Nos Power cable Termination has completed. 12.01.2017 -No up date. 19.01.2017 -Power cable termination completed.33 kV siid short loop installed. 26.01.2017 -No further update. 02.02.2017 -No further update. 09.02.2017 -No further update. 16.02.2017 -Pre-commissioning work is running.Final preparation going on for Shut down preparation. 23.02.2017 Pre-commissioning completed Upper bus feting completed. 02.03.2017 -02 Nos Isolator connector repaired. 09.03.2017 -No further update. 16.03.2017 -Gravel laid at XFR. - Shutdown preparing work is going on. 23.03.2017 -All work has finished. 30.03.2017 -No further update, 06.04.2017 -GT is running. -Waiting for the Busbar protection work.(done by SIMENS). 50/75 MVA power XFR energized without bus bar protection work.(will be done by SIEMENS) 27.04.2017 to 06.07.2017 -No further update. | 20.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
250 | 10.3 | 3 S/S (Shitalakhya, Kamrangirchor & Dhanmondi) | Dhanmondi Project Manager Rabiul Alam , Mustafizur Rahman Mithu 01713147029 Site Engr-NAJMUL-01723598014 Shohidul-01714674231 | 23.10.2016 -No further update. 30.10.2016 -Power XFR on base , yet to be erected. 03.11.2016 -No further update. 10.11.2016 -Regulator installation complete in power XFR. 17.11.2016 -GT (04) 50/75 MVA Transformer installation going on. 24.11.2016 -GT (04) 50/75 MVA Transformer installed. 01.12.2016 -New XFR (04) 50/75 MVA electrical wiring going on.GT-3 XFR AIS 33kV breaker with housing panel dismantling going on. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 -Cable wring is going on in GIS & CRP. 29.12.2016 -Electrical test work is going on for CRP. -132kV power Cable plug in work has done by Chinese engineer. 05.01.2017 -132kV power Cable termination work is going on by Chinese engineer. 12.01.2017 -No further update. 19.01.2017 XFR 50/75 MVA GT-04 electrical testing has been done.33 kV control relay panel setting work is going on. 26.01.2017 -Paint work has completed of new XFR 50/75 MVA GT-04. -33 kV control relay panel electrical wiring is going on. 02.02.2017 -33 kV control relay panel electrical wiring is going on. 09.02.2017 -No further update. 16.02.2017 -No further update. 23.02.2017 -33kv SAS panel electrical wiring work going on. 02.03.2017 to 30.03.2017 -No further update. 06.04.2017 -132kV Power cable High voltage test has been completed. Awaiting for commissioning. 27.04.2017 to 06.07.2017 -No further update. | 20.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
262 | 11 | 33 kV Switching stn at ULON | ULON Project Manager Rabiul Alam , Mustafizur Rahman Mithu 01713147029 Site Engr. Khorshed 01717434647 | 23.10.2016 -No further update. 30.10.2016 -Power XFR on base , yet to be erected. 03.11.2016 -No further update. 10.11.2016 -Regulator installation complete in power XFR. 17.11.2016 -GT (04) 50/75 MVA Transformer installation going on. 24.11.2016 -GT (04) 50/75 MVA Transformer installed. 01.12.2016 -New XFR (04) 50/75 MVA electrical wiring going on.GT-3 XFR AIS 33kV breaker with housing panel dismantling going on. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 -Cable wring is going on in GIS & CRP. 29.12.2016 -Electrical test work is going on for CRP. -132kV power Cable plug in work has done by Chinese engineer. 05.01.2017 -132kV power Cable termination work is going on by Chinese engineer. 12.01.2017 -No further update. 19.01.2017 XFR 50/75 MVA GT-04 electrical testing has been done.33 kV control relay panel setting work is going on. 26.01.2017 -Paint work has completed of new XFR 50/75 MVA GT-04. -33 kV control relay panel electrical wiring is going on. 02.02.2017 -33 kV control relay panel electrical wiring is going on. 09.02.2017 -No further update. 16.02.2017 -No further update. 23.02.2017 -33kv SAS panel electrical wiring work going on. 02.03.2017 to 30.03.2017 -No further update. 06.04.2017 -132kV Power cable High voltage test has been completed. Awaiting for commissioning. 27.04.2017 to 08.06.2017 -No further update. | 20.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
274 | 12 | 33 kV GIS installation at Dhanmondi Grid S/S | Dhanmondi Mustafizur Rahman Mithu 01713147029 Site Engr. Shohidul-01714674231 | 23.10.2016 No further update. 30.10.2016 -Outdoor cable trench done 10%,CRP yet not placed.GT-2 XFR 33kV cable laying started. 03.11.2016 -Outdoor Earth work done 60%.GIS Chanel work running. 10.11.2016 -Channel installing in GIS panel.Base concrete 20 m done. 17.11.2016 -Cable trench 20m done. Panel work running in 1st floor.GIS panel not yet come. 24.11.2016 -Cable trench done 22 meter’s. 01.12.2016 -Cable trench done 25 meter’s.plumbing work going on. 08.12.2016 -GIS panel setting on base. -Control cable laying from GIS to control panel.Slab cover making done approx. 30 pcs. Casting work have been done for cable trench of approx. 20 ft. 15.12.2016 -GIS panel installation & Wiring for GIS has completed.Wiring for AC and DC supply is running. Cable trench for power cable is about to finish. Surface drain (out side the building) is running .Painting work is running Thai aluminum work for doors and windows is running. 22.12.2016 -Wiring for AC & DC supply is completed. -GIS wiring is running.ACDB & DCDB wiring is completed.-CRP & GIS earthing going on.-Battery solution processing running.-Cable hanger in cable trench is running.Cable trench for power cable is completed. -Surface drain (out side the building) is pending.Thai aluminum work for doors and windows is running. 29.12.2016 -GIS wiring is running. -Cable Port Fitting in GIS is completed.CRP & GIS earthing is completed. Battery solution processing is completed.Cable hanger in cable trench is completed. -Civil Work Surface drain (out side the building) is running.Thai aluminum work for doors and windows is completed. 05.01.2017 -GIS wiring has done.Approx. 17 Nos of earth joint has done by cad weld powder.SF6 gas refueling work has done in GIS.Surface drain work has done in out side of control building area.Power cable is laying for GT-1 XFR. 12.01.2017 -SAS Panel wiring is running. -Gas leakage in GIS(Incoming 2 & Bus 3) is located & repaired.Power Cable (3×3)=9 for XFR-2(GT-1) pulling is Completed.Power Cable (3×3)=9 for XFR-2(GT-3) pulling is completed. 19.01.2017 SAS Panel wiring is completed.Gas leakage in GIS (Incoming 2 & Bus 3) is Vacuumed .Testing of CRP panel is running.CT analyzing of GIS is running. 26.01.2017 -Gas filling in GIS is completed.Contact Resistance test is completed.CT analyzing of GIS is completed.Power Cable Connecting process of GT-1 is running. 02.02.2017 -GT -1 (XFR-1, 33kV GIS) has been completed & running properly. -Outgoing -3(H-05) Kakrail feeder cable join has completed.Outgoing -3(H-05) (Kakrail) has been completed & running properly.Earth excavation for XFR feeder has been completed.Wall dismantled for exhaust fan at seven place’s has been done. 09.02.2017 -GT-2 (XFR -1,33kV GIS) has completed & given clearance for energize. -TR-2 XFR cable laying is running.Chigger plate work of ist floor & ground floor is running.Earth excavation for XFR feeder has completed.Flower garden work at north & west side,Florecent 7 LED bulb work,Ceiling fan,Name plate setup at out side work has been completed. 16.02.2017 -Power cable laying work is going on.Out side new flower bed making has been done. 23.02.2017 -Preparation work is running for GT-3,Bashundhara outgoing feeder.Cable laying & connection to Auxiliary XFR is site building is running, 02.03.2017 -GT-3 is completed & running properly.Bashundhara outgoing feeder is completed & running properly.Both Auxiliary XFR is completed &running.Auxiliary connection to PGCB is completed.Gas filling id Taltala-1 (previously named Taltala-2)is completed which had leakage problem. -Land scraping, Apron work,Sand filling in outside cable trench is going on. 09.03.2017 -Outgoing feeder transfer to another spare outgoing feeder panel for Gas leakage solution. 25.05.2017 -No further update. -Security light (ip65) is installed on the building outside. -SAS panel wiring is running due to EEL new wiring diagram. -Flower bed guide wall plastering & finishing is complete. -Paint work is going on. -New gate make for auxiliary XFR. 16.03.2017 -Flower Bed at front side and right of GIS building is complete. -Switch Yard Brick flat soling and mortaring complete -Inside Paint work complete and Out side paint Work is running. -Water outlet pit for cable trans is complete. -Cable trans repairing work is about to finish.Excess soil removing from switch yard is under processing. 23.03.2017 -Repairing work for cementing. 30.03.2017 Maintenance work is running for GIS & SAS panel. 06.04.2017 -Same as before. Commissioning has been done at 28 February,2017 27.04.2017 to 08.06.2017 -No further update. | 20.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
| 13 | Supply,Installation,Testing & Commissioning of 33/11 kV, 1x20/28 MVA,Transformer,33 kV GIS,11 kV AIS with associated materials at Tejgaon | Mogbajar -Tejgaon Mustafizur Rahman Mithu 01713147029 AE,Mehedi 01553504429 Sprvsr,lokman 01743604719 | XFR LAY OUT WORK HAS BEEN DONE. WORK START AT 27,May,2017 21.06.2017 -50% work has been completed at XFR base foundation. -All documents approved by DPDC,(Civil wroks,33kV CRP,XFR GTP etc). | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
334 | 14.1 | 4- S/S (Baridhara, Mirpur BIHS, Mohakhali, United Tower & Dhamalkot) | Mirpur BIHS Project Manager | 18.10.2016 -Already commissioned. 23.10.2016 27.10.2016 03.11.2016 10.11.2016 -No further update 17.11.2016 -Automation system not yet come in site. 24.11.2016 -Solar system implementation work going on. 01.12.2016 -No further update. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 to 09.02.2017 -No further update. 16.02.2017 -SAS panel arrived in site. 23.02.2017 -Automation panel fitting work has been done. 02.03.2017 -Gravelling at site. 09.03.2017 -No further update. 16.03.2017 -Panels for SAS (PAS) are erected and will be commissioned soon. 23.03.2017 -Cabling going on in Pas panel. 30.03.2017 -Wiring work is going on from Panel to panel for Automation. 06.04.2017 -PAS panel and Box Panel wiring has been done. 13.04.2017 to 27.04.2017 -No further update. 04.05.2017 -Panel wiring is going on for automation. 11.05.2017 to 01.06.2017 -No further update. 08.06.2017 -Cleaning 11kV & 33kV panels.11kV PT testing work has ben done. 15.06.2017 Cleaning works has been completed for XFR’s, Battery room, AC/DC panels , charger. 22.06.2017 -No further update,Eid festival holidays, so No further update. 06.07.2017 13.06.2017 -No further update. | 20.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
346 | 14.2 | 4- S/S (Baridhara, Mirpur BIHS, Mohakhali, United Tower & Dhamalkot) | United Tower Project Manager Jane Alam Talukder 01777795201 | 23.10.2016 -No further update. 27.10.2016 -Installation complete. -Testing work going on. 03.11.2016 -33kV Have no source. 10.11.2016 -Discharge of battery,DC high pot test, AC high pot test, Relay test,And Insulation resistance test done. 17.11.2016 IR Test of CT and PT of 11kV Panels, Relay test, Dressing of control cables done. 24.11.2016 -No update. 01.12.2016 -No further update. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 -No further update. 29.12.2016 -Re fueling in new XFR. 05.01.2017 -Test work done for relay. 12.01.2017 -No further update. 19.01.2017 -XFR oil centrifuging going on.XFR testing & wiring has been done. 26.01.2017 -No further update. 02.02.2017 Commissioning has been done. 23.02.2017 -Automation panel fitting work has been done. 02.03.2017 -Current injection work has done of outgoing feeders. 09.03.2017 to 30.03.2017 -No further update. 06.04.2017 -PAS panel fitting work has been done. 13.04.2017 -Panel to panel wiring is going on for automation. 20.04.2017 -Pas panel wiring is going on for automation. 27.04.2017 -Ethernet switch installation work is going on for automation. 04.05.2017 -Ethernet switch wiring is going on.Automation cable dressing work is continuing. 11.05.2017 -Earthing work is going on of box panels & PAS panels for automation.Cable dressing work also going on. 18.05.2017 -Substation cleaning and maintenance. 25.05.2017 -Excavation work is going on. 01.06.2017 XFR foundation CC cast work has been done.Soil excavation work is going on.Rod binding work has been completed. 08.06.2017 XFR foundation CC cast work has been done.Soil excavation work is going on.Rod binding work has been completed. 15.06.2017 Base CC casting has been completed for XFR foundation. Base CC casting work is going on for Fire wall foundation. 22.06.2017 -Base CC casting has been done for XFR.-02 lift CC casting work is going on for Fire wall foundation. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -Fire wall shuttering and casting work has been done. 13.07.2017 -Casting of fire wall, Excavation work of EM tower foundation.18.10.2016 Power cable wiring for 11kV completed.Power cable wiring for 33kV paused due to structure issue.CRP almost over | 20.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
358 | 14.3 | 4- S/S (Baridhara, Mirpur BIHS, Mohakhali, United Tower & Dhamalkot) | Dhamalkot Project Manager Jane Alam Talukder 01777795201 | 18.10.2016 -Equipments GTP & GA not submitted yet. -Civil and Electrical drawings submitted, but not approved yet. 23.10.2016 -No further update. 27.10.2016 -transformer not yet ready. 03.11.2016 -Didn’t get civil order. 10.11.2016 08.12.2016 -Transformer manufacturing under process. 15.12.2016 to 19.01.2017 -No further update. 26.01.2017 -XFR to be released from factory by 31.01.2017. 02.02.2017 -XFR reached in Mohakhali site. 09.02.2017 to 30.03.2017 -No further update. 06.04.2017 -Preparation work has been done for pile. 13.04.2017 -No further update. 20.04.2017 -Boring work for pile is going on. 27.04.2017 -Pile casting work is continuing. 04.05.2017 -No further update. (Total 04 Nos pile has been completed). 11.05.2017 -No further update. 18.05.2017 -Soil excavation for XFR foundation work. 25.05.2017 -Repairing work has been completed. 01.06.2017 to 13.07.2017 -No further update. |  | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
370 | 14.4 | 4- S/S (Baridhara, Mirpur BIHS, Mohakhali, United Tower & Dhamalkot) | Mohakhali Project Manager Jane Alam Talukder 01777795201 Site Engr. Hamid-01937109167 (UZZAL) | 18.10.2016 -Equipments GTP & GA not submitted yet. -Civil and Electrical drawings submitted, but not approved yet. 23.10.2016 -No further update. 27.10.2016 -transformer not yet ready. 03.11.2016 -Didn’t get civil order. 10.11.2016 08.12.2016 -Transformer manufacturing under process. 15.12.2016 to 19.01.2017 -No further update. 26.01.2017 -XFR to be released from factory by 31.01.2017. 02.02.2017 -XFR reached in Mohakhali site. 09.02.2017 to 30.03.2017 -No further update. 06.04.2017 -Preparation work has been done for pile. 13.04.2017 -No further update. 20.04.2017 -Boring work for pile is going on. 27.04.2017 -Pile casting work is continuing. 04.05.2017 -No further update. (Total 04 Nos pile has been completed). 11.05.2017 -No further update. 18.05.2017 -Soil excavation for XFR foundation work. 25.05.2017 -Repairing work has been completed. 01.06.2017 to 13.07.2017 -No further update. | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
| 15.1 | Supply,Installation,Testing & Commissioning of 03 Nos 33/11 Kv Substation (Each 10/14 MVA, TURN-KEY) | TARONIBARI under Nilphamari PBS Jane Alam Talukder 01777795201 Excu.Sohelrana-01709650215 | project start or agreement date-06.02.2017 30.05.2017 SOIL FILLING COMPLETED 100%. 01.06.2017 -Soil Filling Has Been Competed. 08.06.2017 to 22.06.2017 -No further update. -Already get the Sub contractor, deed has been completed. -Land filling has completed. -Design, drawing has completed. 29.06.2017 13.07.2017 -No further update. | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
| 15.2 | Supply,Installation,Testing & Commissioning of 03 Nos 33/11 Kv Substation (Each 10/14 MVA, TURN-KEY) | BODA under Thakurgaon PBS Jane Alam Talukder 01777795201 Excu.Sohelrana-01709650215 | project start or agreement date-06.02.2017 30.05.2017 SOIL FILLING COMPLETED 100%. 01.06.2017 -Soil Filling Has Been Competed. 08.06.2017 to 22.06.2017 -No further update. -Already get the Sub contractor, deed has been completed. -Land filling has completed. -Design, drawing has completed. 29.06.2017 13.07.2017 -No further update. | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
| 15.3 | Supply,Installation,Testing & Commissioning of 03 Nos 33/11 Kv Substation (Each 10/14 MVA, TURN-KEY) | HORIPUR under Thakurgaon PBS Jane Alam Talukder 01777795201 Excu.Sohelrana-01709650215 | project start or agreement date-06.02.2017 30.05.2017 SOIL FILLING COMPLETED 100%. 01.06.2017 -Soil Filling Has Been Competed. 08.06.2017 to 22.06.2017 -No further update.Already get the Sub contractor, deed has been completed.Land filling has completed.Design, drawing has completed. 29.06.2017 13.07.2017 -No further update. | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
394 | 16.1 | Rahim Steel | Kachpur, N'Ganj Project Manager Abdul Hakim 01711955543 Site Engr Mr Rakib-01716275374 | 18.10.2016 -Piling cap broken. 23.10.2016 -No further update. 27.10.2016 -Civil works running. 03.11.2016 -Civil works 80% done. 10.11.2016 -Column & Base casting complete of ACR(automatic circuit reclozer) -Sand filling going on. -Site boundary wall work done. 17.11.2016 -Civil works 80% done. 24.11.2016 -Fancy boundary work going on.Civil works: Sand filling & guide wall done. 01.12.2016 -Fancy boundary work done. -XFR,CT,PT,DS, Isolator of 11 & 33 kV materials for Tower & beam arrived in site. 08.12.2016 -Beam and Tower making work have been done. 15.12.2016 -33 kV & 11kV CT,PT & LA erection has been done. 22.12.2016 -Casting work for road has been completed.Brick soling work has been completed. -XFR (5/7.0) assembling has done.Bus bar for 11 kV has installation has been done. 29.12.2016 -Internal connection, wiring, metering & jumpering work has been done for CT,PT. -HT & LT connection has been done for power transformer. 05.01.2017 -33kV source line hookup works has done. -33 kV ACR & Isolator jumpering work has done. 12.01.2017 -Site has been handed over to WZPDCL. 19.01.2017 -No further update. 26.01.2017 -No further update. Problem :-ACR,In 11kV metering system.Battery back up System fault. 02.02.2017 to 13.07.2017 -No further update. | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
| 16.2 | City Group | City Group Gondhobpur Rupshi Abdul Hakim 01711955543 Site Engr Mr Rakib-01716275376 | 23.10.2016 Bashundhara Group already starts the civil work.After completion of the boundary wall we will start our other works. 27.10.2016 Basundhora Group already starts the civil work.After completion of the boundary wall we will start our other works. 02.11.2016 Bashundhora Group already starts the civil work.After completion of the boundary wall we will start our other works. 10.11.2016 Bashundhora Group already starts the civil work. After Completing the civil work we will start out work. 17.11.2016 -Bashundhora Group already starts the civil work. -After completion of the boundary wall we will start our other works. 24.11.2016 -Boundary wall work 100% done. 01.12.2016 -No further update. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 -No further update. 29.12.2016 Do as Previous Week. 05.01.2017 TO 02.03.2017 -No further update. 09.03.2017 -Equipment not yet arrived at site like Clamp connector etc. -Design,drawing work is processing going on for earthing ,panel arrangement. 16.03.2017 -Design, drawing works is going on. 23.03.2017 -No further date. 30.03.2017 -No further update. -Waiting for electrical equipment's. 06.04.2017 13.04.2017 -Same as before. 20.04.2017 -No further update. -Waiting for electrical equipment's. to 13.07.2017 -No further update. | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
| 17 | Bashundhara Group | Bashundhara Group Project Manager Engr. Abul Kalam Azad- 01777781202 Site Eng Kabir 01711541491 | 23.10.2016 -Materials arrived at site. 27.10.2016 02.11.2016 -CSE yet Not delivered. After delivery of CSE we will start our erection work. 10.11.2016 -CSE yet not delivered. After delivery of CSE we will start our erection work. 17.11.2016 -CSE yet Not delivered at site. After delivery of CSE we will start our erection work. 24.11.2016 -CSE already arrived in Factory but Not yet delivered at site. 01.12.2016 -No further update. 08.12.2016 -No further update. 15.12.2016 -No further update. 22.12.2016 -Cable termination work is going on by Chinese Engineers. 29.12.2016 -132 kV Power cable termination and all electrical equipment's installation is completed.-Testing will be started very soon. 05.01.2017 -All necessary work has done for Power line run, without Gas refilling for Breaker. 12.01.2017 -No further update. 19.01.2017 -Equipment testing is going on. 26.01.2017 -Equipment testing is going on. 02.02.2017 -Sub Station is running now. 09.02.2017 -No further update. 16.02.2017 -No further update. 23.02.2017 -Preparation work is going on for 06 Nos of XFR parallel running for Rahim steel.(for 132kV 20/25MVA 02 Nos & 10/14 MVA 04 Nos). 02.03.2017 -75% work has been done for 06 Nos of XFR parallel running for Rahim steel. (for 132kV 20/25MVA 02 Nos & 10/14 MVA 04 Nos). 09.03.2017 -100% work has been done for 06 Nos of XFR parallel running for Rahim steel. (for 132kV 20/25MVA 02 Nos & 10/14 MVA 04 Nos). 16.03.2017 -Same as before. -Waiting for the operation. 23.03.2017 to 13.04.2017 -No further update. 20.04.2017 -All XFR is running in parallel operation. 27.04.2017 -Same as before. to 11.05.2017 -No further update. 18.05.2017 -Same as before. 25.05.2017 Panel placement drawing approval.Soil treatment instruction for earthing.DO ready for panel delivery. 01.06.2017 Panel delivery has been arrived at site.06 pc’s Breaker on the way to Bangladesh from India.PGCB control building’s floor cutting work is going on. 08.06.2017 -No further update. 15.06.2017 Panel placement drawing approval.Soil treatment instruction for earthing. Panel delivery at Site.33kv CT,PT delivery at site will be 21 june,17 22.06.2017 29.06.2017 -No further update. 06.07.2017 -Clamp & connector has been arrived at site at 03 july,2017 from India.PGCB end panel arrangement punching work has been handed over to Innovate company as a subcontractor.Punching work is going on then panel will be Erection. 13.07.2017 -No further update. | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
454 | 18 | 132/33 kV S/S at Matarbari | 132/33 kV S/S at Matarbari Client - Coal Power Co Ltd | 27.10.2016 GA & GTP of 132 kV CB approved.GA & GTP of 33 kV CB resubmitted for approval.1st & grn floor plan submitted for approval.sand filling 65 %. 07.11.2016 GA & GTP of 132 kV CB and GA & GTP of Aux.TFR approved. GA & GTP of 33 kV CB and GA & GTP of 132 & 33 kV CT & IVT resubmitted for approval.1st & ground floor plan approved.sand filling 65% 11.11.2016 GA & GTP of 132 KV CB & GA and GTP of Aux.TFR and GA & GTP of 33 kV CB are approved.GA & GTP of 132 & 33 kV CT & IVT resubmitted for approval.Slope protection drawing approved.1st & gnd floor plan approved. Architectural drawing of control room submitted for approval.sand filling 70 % (~4600000cft) done. 17.11.2016 -GA & GTP of 132 kV CB, 33 kV CB, 132 & 33 kV CT & IVT , Aux. TFR approved.GA & GTP of Bus bar conductor submitted for approval.Slope protection drawing approved. Ist & gnd floor plan approved. -Architectural drawing of control room submitted for approval. -sand filliong 70 % (~4600000cft) done. 24.11.2016 -No update. 01.12.2016 -No further update 08.12.2016 -Sand filling work is going on. 15.12.2016 -One bulldozer added in site. -Sand slope making work going on. 22.12.2016 -Dam work is going on -Sloping work is continued -1 Nos Excavator and 1 Nos of Bulldozer is deployed for this work. 29.12.2016 -No further update. 05.01.2017 -No further update. 12.01.2017 -Slope and ambak/byke work is going on by 03 nos excavator and 02 nos Drager. 26.01.2017 -Slope and ambak/ byke work going by -03 nos excavator & 02 Nos Draggers are working. -Earth protection work by using wooden bully is going on. 02.02.2017 -No further update. 09.02.2017 -Sand filling work has restart.Slope and ambak/ byke work has completed. 16.02.2017 -Same as before. 23.02.2017 -Sand filling work is going on. 02.03.2017 -Same as before. 09.03.2017 -Dragging work,Labor shed making work and Leveling work has been done. 16.03.2017 -Security guard room making. Sand filling is going on. 23.03.2017 -Sand filling work is going on. 30.03.2017 -Sand filling work has been stopped for billing issue. 06.04.2017 -Sand filling work is going on. 13.04.2017 -Sand filling work is going on.Dresser work is going on.Block (brick chip)arrived at site. 20.04.2017 -Sand filling has been completed.Block & brick chip has been arrived at site. 27.04.2017 -Shed making work is continue.Block setting, drecing,leveling & compaction work is going on.Block production work also going on. 04.05.2017 -Shed making work is completed for cement. Block setting, drecing,leveling & compaction work is going on.Block production work also going on. 11.05.2017 Block setting, drecing, leveling & compaction work is going on.Block production work also going on. 18.05.2017 -Block carrying, dressing, leveling & compaction work is going on.Block production work also going on.Labor shed work has been completed. Cement shed extension work has done. Site toilet making work is going on. 25.05.2017 08 Nos pile has been completed at switchyard.Centering work is going on for roof cast at Ansar barrack.05 Nos base casting has been completed at 33kV. 01.06.2017 11 Nos base casting has been completed at control building.Re-bar work is continuing.Pile head broken work 75% has been completed at 132 control building.15 Nos base casting has completed for boundary wall.76/112 Nos pile has been completed. 08.06.2017 33kv control building grade beam casting completed.06 out of 12 Nos pile has been complete for XFR.86 Nos out of 112 Nos pile work has ben completed. Boundary wall.20 Nos column casting has been completed at 132 kV switchyard. 15.06.2017 33kv control building column casting completed.84 Nos out of 112 Nos pile work has ben completed at 132 Kv S/Y.50 Nos Boundary wall column,base Gb casting has been completed. 22.06.2017 -33kv control building first floor slab casting completed.30 Nos Boundary wall column casting done. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 200m long Boundary wall has been completed. Ansar barrack roof casting has completed. 33kV control building ground floor roof casting has completed.33kV control building first floor roof casting will be completed at 15 july,2017 . 132kV control building ground floor roof casting will be completed at 30 jul,2017.Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site.15 Nos pudding has done at 132kV control building. 11Nos column has been completed at 33kV control building. | 0 | From 14.07.2017 to 20.07.2017 last 01 (One) Week. | UPTO 27.10.2016 THURSDAY
466 | 19.1 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram | SHERPUR (BOGRA) Design Supply,Installation, Testing commissioning of 132/33kV S/S. | 23-10-2016 - Sand Filling work is on progress. Approximately 225,000 cft Sand has been filled. 03.11.2016 -Sand Filling on Progress. 10.11.2016 -Sand Filling from a new point (Jorgacha) which is 11km from the site has started. 17.11.2016 -Approx. 250000 cft. Sand has been filled.GA & GTP of 132kV LA has been approved.GA & GTP of 33kV LA has been approved. 24.11.2016 -Sand Filling on Progress. -Overall Site Layout Approved. -Bore Hole Layout Approved. 01.12.2016 -Sand Filling work on progress. 08.12.2016 -Approx. 470,000 cft. Sand has been filled.Site mobilization work on progress.Site boundary & other site work on progress. 15.12.2016 -Sand has been filed aprox. 55000cft sand.new gate setting, electricity line connected.Soil test report approved. 22-12-2016 -Approx. 650000cft sand has been filled.Soil Test equipment's has been mobilized & ready for initiation.-GA & GTP of 132kV DS approved.-GA & GTP of 132kV IVT approved.-GA & GTP of 33kV IVT approved. 29.12.2016 -Approx. 700000cft sand has been filled.Soil Test On going.GTP of 132kV CB Submitted. 05-01-2017 -Approx. 780000cft sand has been filled. Soil Test On Going (29 boring out of 40 Completed ).GTP & GA of 33kV VCB Submitted.Control Room CRP Layout design submitted -HFL level approved by PGCB. 12-01-2017 Soil Test 40 nos completed -Control Room CRP Layout design approved. 26.01.2017 -132/33kV new grid S/S Road level sand filing complete and flood level reference sand filing continue. 02-02-2017 -Approx. 1100000 cft sand has been filled.PDB Pole Removal on progress.Soil Test Completed.GA & GTP of 33V DS Approved.CRP Panel of 132kV & 33kV Control room.Approved ..Pre pilling work on progress. 09.02.2017 ----- 16.02.2017 -Approx. 13 Lac cft sand has been filled. New REB & PDB Pole installed. Existing Poles will be removed very soon.GA & GTP of Thermal ACSR Approved. 23.02.2017 -Approx. 14lac cft sand has been filled.GA & GTP of 33kV VCB & 132kV CB has been Approved.Labor Shed, Cement Store & Toilet building on progress.RL Level has been confirmed.Pilling House completedPilling Rig has been mobilized. 02.03.2017 -Approx. 15lac cft sand has been filled.GA & GTP of 33kV VCB & 132kV CB has been Approved.Ground floor plan of 132 & 33 kV control building drawing has been approved. Labor Shed, Cement Store & Toilet building on progress.RL Level has been confirmed.Pilling House completed -04 Nos Pilling Rig has been mobilized. 09.03.2017 -39 Nos pile work has been done for 132 kV & 33kV control building. 16.03.2017 -31 Nos pile work has been done for 132 kV & 33kV control building.sand filling continuing. 23.03.2017 -All Pile work has been done for 132 kV & 33kV control building. Sand filling continuing.Pile work is going on for Boundary wall. 30.03.2017 -Pile and sand-filling is going on. 06.04.2017 -15/112 Nos pile has been done for switchyard.100/216 Nos pile has been done for boundary. 13.04.2017 -20/112 Nos pile has been done for switch yard.112/216 Nos pile has been done for boundary.04 Nos base foundation has been done for Ansar barrack. 20.04.2017 -60% pile work has been done for switch yard.80% pile has been done for boundary.30% base foundation has been done for Ansar barrack.GTP & GA of Power XFR has been approved. Drawing of 33kV CT has been approved. 27.04.2017 -35Nos pile has been done at switchyard.10 Nos putting base work has been completed at ansar brack.140 Nos pile has been done for boundary wall. 04.05.2017 -01 Nos pile has been done at Switchyard.Pile head broken work is continuing at 33kV & ansar barrack area. 11.05.2017 -Total 39 Nos out of 112 Nos pile has been completed at S/Y.Earth filling work in ansar barrack.11 Nos pile cap broken work has been done at 33kV control building. 18.05.2017 -07 Nos out of 112 Nos pile has been completed at S/Y.Earth filling work is going on at ansar barrack. All pile cap broken work has been done at 33kV control building. 25.05.2017 -14 Nos pile work has done for boundary wall.06 Nos base earth excavation work has done at 33kV control building. Pile cap ballast & CC work has been completed. 01.06.2017 32 Nos boundary wall pile has been completed.33kV control building:11Nos base earth excavation pile cap ballast & cement concrete 06 Nos complete. Ansar barrack :07 Nos earth excavation & 03 Nos cement concrete has been completed. 08.06.2017 33kV control building: 11Nos pile cap casting has completed.Ansar barrack :soil excavation & footing casting, short column casting work has been done.58 Nos boundary wall pile has been completed. 15.06.2017 22 Nos boundary wall pile,03 Nos TR pile & 33kV control building grade beam casting completed.Ansar barak grade beam casting,5 Nos pile cap earth excavation for 132kV,15 Nos pile ballast & 05 Nos pile cap casting has been done. 22.06.2017 52 Nos pile work done at boundary wall. 01 Nos TR pile work has dpne.11 Nos column casting has been done at 33kV control building.First slab casting has done at Ansar barak.5 Nos pile cap,05 Nos pile ballast work & 11 Nos casting and earth excavation work has been completed at 132kV. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 15m long Boundary wall has been completed.Ansar barrack roof casting has completed.33kV control building ground floor roof casting will be completed at 18jul,2017.132kV control building ground floor roof casting will be completed at 30jul,2017.Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 132kV Control room building 06nos RCC base casting complete. Boundary wall 30nos column base casting complete. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
478 | 19.2 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | KURIGRAM Design Supply,Installation, Testing commissioning of 132/33kV | 23-10-2016 -Sand Filling work is going on. Sand being extracted from three points.Approximately 210,000 cft Sand has been filled. 27.10.2016 03.11.2016 -Sand Filling Work on Progress 10.11.2016 -Sand Filling work on going. 17.11.2016.Approx. 300000 cft. Sand has been filled .GA & GTP of 132kV LA has been approved .GA & GTP of 33kV LA has been approved. 17.11.2016 -Approx. 300000 cft. Sand has been filled .GA & GTP of 132kV LA has been approved.GA & GTP of 33kV LA has been approved. 24.11.2016 -Sand Filling on Progress. -Overall Site Layout Approved. -Bore Hole Layout Approved. 01.12.2016 -Sand Filling work on progress. 08.12.2016 -Approx. 700000 cft. Sand has been filled.Site Mobilization on progress. 15.12.2016 Soil test on going.barbed wire make boundary.New electricity connection get Container decoration on going. 22-12-2016 Soil Test Completed.Container Office work completed.Office toilet work in progress.Site was inaugurated by PGCB MD.Gate was successfully installed.Site area cordoned with bamboo & barbed wire.Electricity line connected.GA & GTP of 132kV Disconnector approved.GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -Sand Filling on going. -GA & GTP of 132kV CB Submitted. 05-01-2017 -Sand filling nearing completion -Soil Test report submitted by the sub contractor.GTP & GA of 33kV VCB Submitted.Control Room CRP Layout design submitted.HFL level approved by PGCB. 12-01-2017 -Sand filling is completed upto Public highway.Control Room CRP Layout design approved 26.01.2017 -No update yet. 02-02-2017 -Sand Filling on going.Soil Test Completed.GA & GTP of 33V DS Approved.CRP Panel of 132kV & 33kV Control room Approved.Pre pilling work on progress. 09.02.2017 ----- 16.02.2017 -Sand Filling nearing completion.Toilet, Labor Shed , Cement Shed, Pilling House Completed.Pilling will begun very soon -Pilling materials arrived.GA & GTP of Thermal ACSR Approved. 02.03.2017 -Sand filling nearing completion.GA & GTP of 33kV VCB & 132kV CB has been Approved.Pilling work already started.13nos pile has been completed.abour shed & store has been complete.RL Level has been confirmed. 09.03.2017 -17 Nos pile has been done for 132kV control building. 16.03.2017 -N o further update. 23.03.2017 -42 Nos piles have been completed in 132 KV control room building. 30.03.2017 -12 Nos piles have been completed in 132 KV control room building. 06.04.2017 -10Nos piles have been completed in 132 KV control room building.02 Nos piles have been completed in 33 KV control room building. 13.04.2017 -07 Nos piles have been complete in 33kV control room building.02 Nos piles have been complete in 132kV switchyard. 20.04.2017 -GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved.100% piles have been complete in 33kV control room building. 100% piles have been complete in 132kV switchyard. 27.04.2017 -16 Nos piles have been complete in 132kV S/Y.13 Nos piles have been complete in 33kV control building. 04.05.2017 -14 Nos piles have been complete in 132kV S/Y. 11.05.2017 -06 Nos piles have been completed in 132kV S/Y. 18.05.2017 -Labor shed making work has been done.Site leveling work s going on. 25.05.2017 to 29.06.2017 -No further update. 06.07.2017 -No further update. -Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 -XFR pad 02 Nos pile has been completed.132kV control building 11 Nos pile cap casting has done.Total 220m pile cap & grade beam has been casting at boundary wall. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
490 | 19.3 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | THAKURGAON Capacity upgradation of existing132/33kV S/S Project Manager Imran Hossain 01713242198 | 23-10-2016 Approved Drawings: SLD, Overall Layout, Electrical Layout, Section of Electrical Layout. 27.10.2016 to 10.11.2016 -No Update 17.11.2016 -GA & GTP of 132kV LA has been approved.GA & GTP of 33kV LA has been approved. 24.11.2016 -No Update. 01.12.2016 -No further update. 08.12.2016 -Equipment of GA GTP on progress. 15.12.2016 -No update. 22-12-2016 -GA & GTP of 132kV Disconnector approved.GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -GA & GTP of 132kV CB Submitted. 05-01-2017 -Sand filling nearing completion.Test report submitted by the sub contractor.GTP & GA of 33kV VCB Submitted.Control Room CRP Layout design submitted -HFL level approved by PGCB. 12.01.2017 CT Sizing calculation submitted. 26.01.2017 -No update yet. 02.02.2017 GA & GTP of 33kV DS Approved. 09.02.2017 ----- 16.0.2.2017 -GA & GTP of Thermal ACSR Approved. 23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 02.03.2017 to 13.04.2017 -No further update. 20.04.2017 -Final inspection work has been done for CRP layout & measurement.GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved. 27.04.2017 -No further update. to 29.06.2017 -No further update. 06.07.2017 -No further update. -Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
502 | 19.4 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33 kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | PALASHBARI Capacity upgradation of existing132/33kV S/S Project Manager Md Imran Hossain 01713242198 | 17-10-2016 Site Status:Preliminary & Secondary Inspection Completed,Drawing Status: Revised SLD submitted .Revised overall site layout submitted ,Revised section of outdoor equipment submitted,Revised control panel layout has been submitted. 23-10-2016 Approved Drawings: Single Line Diagram, Overall Layout, Electrical Layout, Section of Electrical Layout. 27.10.2016 to 10.11.2016 -No Update. 17.11.2016 -GA & GTP of 132kV LA has been approved.GA & GTP of 33kV LA has been approved. 24.11.2016 -No Update. 01.12.2016 -No further update. 08.12.2016 -Equipment of GA GTP on progress. 15.12.2016 No further update. 22-12-2016 GA & GTP of 132kV Disconnector approved. -GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -GA & GTP of 132kV CB Submitted. 05.01.2017 -GTP & GA of 33kV VCB Submitted -Control Room CRP Layout design submitted -HFL level approved by PGCB. 12.01.2017 CT Sizing calculation submitted. 26.01.2017 -No update yet. 02.02.2017 GA & GTP of 33kV DS Approved. 09.02.2017 ----- 16.02.2017 -GA & GTP of Thermal ACSR Approved. 23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 02.03.2017 to 13.04.2017 -No further update. 20.04.2017 -Final inspection work has been done for CRP layout & measurement.GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved. 27.04.2017 to 29.06.2017 -No further update. 06.07.2017 -No further update. -Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
514 | 19.5 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | SHIRAJGANJ Capacity upgradation of existing132/33kV S/S Project Manager Md Imran Hossain 01713242198 | 23-10-2016 -Approved Drawings: Single Line Diagram, Overall Layout, Electrical Layout,Section of Electrical Layout. 27.10.2016 to 10.11.2016 No Update. 17.11.2016 -GA & GTP of 132kV LA has been approved GA & GTP of 33kV LA has been approved. 24.11.2016 -No Update. 01.12.2016 -2nd Site Visit Conducted along with PGCB Delegates (Design Dept.) 08.12.2016 -Final site visit completed. 15.12.2016 No further update. 22-12-2016 GA & GTP of 132kV Disconnector approved. -GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -GA & GTP of 132kV CB Submitted. 05.01.2017 -GTP & GA of 33kV VCB Submitted.Control Room CRP Layout design submitted -HFL level approved by PGCB. 12.01.2017 CT Sizing calculation submitted. 26.01.2017 -No update yet. 02.02.2017 GA & GTP of 33kV DS Approved. 09.02.2017 ----- 16.02.2017 -GA & GTP of Thermal ACSR Approved. 23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 02.03.2017 to 06.04.2017 to 13.04.2017 -No further update. 20.04.2017 -Final inspection work has been done for CRP layout & measurement.GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved. 27.04.2017 to 29.06.2017 -No further update. 06.07.2017 -No further update. -Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
526 | 19.6 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | NATORE Capacity upgradation of existing 132/33kV S/S Project Manager Md Imran Hossain 01713242198 | 17-10-2016 Site Status: Preliminary Inspection Complete Drawing Status: Ready for submission:SLD -Overall site layout.Section of outdoor equipment Control panel layout has been submitted. 23.10.2016 to 10.11.2016 -No update. 17.11.2016 -GA & GTP of 132kV LA has been approved.GA & GTP of 33kV LA has been approved. 24.11.2016 -No Update. 01.12.2016 -2nd Site Visit Conducted along with PGCB Delegates (Design Dept.) 08.12.2016 -Drawing / design approval after visit on process. 15.12.2016 No further update. 22-12-2016 GA & GTP of 132kV Disconnector approved. -GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -GA & GTP of 132kV CB Submitted.05.01.2017 -GTP & GA of 33kV VCB Submitted. 05.01.2017 -GTP & GA of 33kV VCB Submitted. 12.01.2017 26.01.2017 -No update yet. 02.02.2017 GA & GTP of 33kV DS Approved. 09.02.2017 ----- 16.02.2017 -GA & GTP of Thermal ACSR Approved. 23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 02.03.2017 to 13.04.2017 -No further update. 20.04.2017 -Final inspection work has been done for CRP layout & measurement.GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved. 27.04.2017 to 29.06.2017 -No further update. 06.07.2017 -No further update. -Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week. | From 09.06.2017 to 15.06.2017
538 | 19.7 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | CHAPAI NABABGANJ Capacity upgradation of existing132/33kV S/S Project Manager Md Imran Hossain 01713242198 | 17-10-2016 Site Status: Preliminary Inspection Completed.Drawing Status:-SLD submitted -Overall site layout submitted -Section of outdoor equipment submitted -Control panel layout has been submitted. 23.10.2016 to 10.11.2016 -No update. 17.11.2016 -GA & GTP of 132kV LA has been approved.GA & GTP of 33kV LA has been approved. 24.11.2016 -No Update. 01.12.2016 -2nd Site Visit Conducted along with PGCB Delegates (Design Dept.). 08.12.2016 -Drawing / design approval after visit on process. 15.12.2016 No update. 22-12-2016 GA & GTP of 132kV Disconnector approved. -GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -GA & GTP of 132kV CB Submitted. 05.01.2017 -GTP & GA of 33kV VCB Submitted.Control Room CRP Layout design submitted.HFL level approved by PGCB. 12.01.2017 CT Sizing calculation submitted. 26.01.2017 -No update yet. 09.02.2017 ----- 02.02.2017 GA & GTP of 33kV DS Approved. 16.02.2017 -GA & GTP of Thermal ACSR Approved.23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 02.03.2017 to 13.04.2017 -No further update. 20.04.2017 -Final inspection work has been done for CRP layout & measurement.GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved. 27.04.2017 to 22.06.2017 -No further update. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -No further update. -Local materials of 33kV switchgear: CB,CT,PT,DS already arrived at site. | 13.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
550 | 19.8 | WB Pkg 2 Design Supply,Installation, Testing commissioning of 132/33kV S/S at Sherpur (Bogra)& Kurigram; Capacity upgradation of existing132/33kV S/S at Thakurgaon ,Palashbari ,Shirajganj, Natore & Chapainababganj and 132kV Bay extension at Rangpur S/S | RANGPUR 132kV bay extension Project Manager Md Imran Hossain 01713242198 | 23-10-2016 -Approved Drawings: Single Line Diagram, Overall Layout, Electrical Layout, -Section of Electrical Layout 27.10.2016 -Bore Hole Layout has been submitted for Approval. 03.11.2016 Bore Hole Layout has been Approved. Soil Testing will begin on 6-11-2016. 10.11.2016 Soil Test Completed. 17.11.2016 -GA & GTP of ACSR (Mallard) has been approved - GA & GTP of 132kV LA has been approved. 24.11.2016 -Soil Test work Completed. 01.12.2016 -No further update. 08.12.2016 -Equipment of GA GTP on progress. 15.12.2016 No update. 22-12-2016 GA & GTP of 132kV Disconnector approved. -GA & GTP of 132kV IVT approved.GA & GTP of 33kV IVT approved. 29.12.2016 -GA & GTP of 132kV CB Submitted. 05.01.2017 -GTP & GA of 33kV VCB Submitted -Control Room CRP Layout design submitted -HFL level approved by PGCB. 12.01.2017 -CT sizing calculation approved.Civil drawing of respective civil work is approved. 19.01.2017 -Sand filling going on approx. 28300 cft. 26.01.2017 -No update yet. 02.02.2017 -Pre pilling work on progress. 09.02.2017 ----- 16.02.2017 -Pilling House, Cement Shed Completed.Some Pilling materials already arrived.GA & GTP of Thermal ACSR Approved. 23.02.2017 -Pilling materials are being mobilized.GA & GTP of 132kV CB has been Approved. 02.03.2017 to 13.04.2017 -No further update. 20.04.2017 -Final inspection work has been done for CRP layout & measurement.GTP & GA of Power XFR has been approved.Drawing of 33kV CT has been approved. 04.05.2017 48600 cft Sand filling work has been completed. 11.05.2017 111700 cft Sand filling work has been completed. 18.05.2017 Total 68 Nos out of 88 Nos Pile has been completed.13 Nos VCB arrived at site .132kV control building 19 out 32 pile cap casting has done33kV control building earth excavation has done.07Nos pile cap head broken work has done. 11.05.2017 -No further update. 18.05.2017 -No further update. 25.05.2017 -Total 76 Nos out of 88 Nos Pile has been completed.132kV control building 32 out of 32 pile cap casting has done.Total 20 Nos pile cap head broken work has been done.09 Nos pile cap cast at 33kv control building. 01.06.2017 Total 88 Nos out of 88 Nos Pile has been completed.Total 16 Nos pile cap head broken work has been done.12 Nos pile cap cast at 33kv control building. 08.06.2017 132kV control building floor,grade beam, column casting has been done.33 kV grade beam & column casting has been done. 15.06.2017 132kV CB:First floor beam shuttering on going, internal stair first landing, ground floor curing, external stair cast,132kV CB:GB casting, column trigger casting, dressing & leveling on going. 132kV S/Y:19Nos pile cap earth excavation, 10Nos pile head broken, 02 Nos pile cap cast.6200 cft Sand filling work has done, 110 Nos pile has been done at Boundary. 22.06.2017 132 kV & 33 kV CB:First floor beam & slab shuttering work is going on.132kV S/Y:All pile cap earth work has done,02 Nos cap casting has done.02 Nos CC casting work has done.12300 cft Sand filling work has done. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -Rod binding work has been done for 132 kV & 33 kV control building.Rod binding work has been done for column at 132kv gantry tower. | 13.07.2017 132kV CB:1st floor beam & slab casting done. 33kV CB:2nd floor column 2nd lift curing. 33kV SY :Earth works ongoing & 2nos base CC done.132kV SY :Column 16nos casting.Sand filling: 00nos.=00cft.XFR 2 base rod binding work done.XFR 1 earth excavation works & CC casting done. Pile cap rod binding work running.Boundary pile cap & column rod binding ( west side) running. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
562 | 20.1 | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura | NAWABGANJ Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S Project Manager Project Manager Md Enamul Haq 01708131702 Mr Farid Ahmed 01914454350 Sae. Aslam 01708131701 Rakib-01708453358 | 27.10.2016 90% Dyke construction complete.1500m dredging pipe setting complete. Dredger machine installation ongoing. Booster machine is not reached yet at site. 03.11.2016 3400ft (52% of total 6600 ft) pipe setting complete. 90% of dyke construction complete.Dredger machine installation complete.Booster machine is not reached yet at site. 10.11.2016 -No further update. 17.11.2016 -Pipe setting work running. (Dredger and Booster end). 24.11.2016 -Sand filling work started at site. 01.12.2016 -Approximate 70000 cft Sand filling done. 08.12.2016 -Approximate 10200 cft Sand filling has been done. 15.12.2016 -105000 cft of 300000 cft Sand filling completed. Sand filling will resume on 19th dec’16. 22.12.2016 -Sand filling work is going on. 29.12.2016 -Sand filling is continued. 05.01.2017 -Sand filling work is going on approx. 145700 cft. 12.01.2017 -Sand filling work is going on approx. 80000 cft. 19.01.2017 -Lay out & preparation work is going on for piling. 26.01.2017 -Weekly sand filling 167950 cft. 02.02.2017 -Sand filling going on approx.276392 cft. This week 09.02.2017 -Sand filling going on approx.377135cft. 16.02.2017 -Sand filling going on approx.259086 cft. 23.02.2017 -GA & GTP of 33kV VCB & 132kV CB has been Approved. 02.03.2017 -Sand filling going on approx.92300 cft. 09.03.2017 -Sand filling going on approx.98100 cft. 16.03.2017 -Sand filling going on approx. 100700 cft. 23.03.2017 -Sand filling going on approx. 1,39,000 cft. 30.03.2017 -Sand filling going on approx.119700 cft. 06.04.2017 -Sand filling going on approx.100900 cft. 13.04.2017 -137700 cft Sand filling work has been completed. Lay out has been done at CB & Switchyard for 132k V & 33kV.Brick soling & hearing bond work has been completed.18Nos pile has been done. 20.04.2017 -216800 cft Sand filling work has been completed. 27.04.2017 -125000cft Sand filling work has been completed. 04.05.2017 -48600 cft Sand filling work has been completed. 11.05.2017 -111700 cft Sand filling work has been completed. 18.05.2017 Total 68 Nos out of 88 Nos Pile has been completed. 13 Nos VCB arrived at site .132kV control building 19 out 32 pile cap casting has done.33kV control building earth excavation has done.07 Nos pile cap head broken work has done. 25.05.2017 -132kV control building building:First floor slab shutter work is going on.33kV control building :Ground floor brick wall making done up to linten,Linten shutter work is running. Boundary wall:20 Nos column cast,40m gread beam and brick wall making has been done.33kV S/Y:7/22 gantry cast,03 Nos excavation & 03 Nos gantry base macadam and CC casting has been done.XFR foundation:2nd XFR over all base rod binding & shuttering complete. 01.06.2017 -132kV control building building :First floor slab shutter work has completed. Rod binding work is continuing. Ground floor slab plaster has done.Linten,brick wall & plaster work 50% has done.33kV control building:Ground floor Linten,Brick wall completed up to linten.Ground floor slab plaster completed & Brick wall 70% plaster completed. Boundary wall:07 Nos column casting done.25m grade beam 7 Brick wall making has done.132kV S/Y:Total 56/88 Nos pedestal column casting has done.33kV S/Y:16/22 gantry cast,10 Nos excavation & 10 Nos gantry base macadam &02 Nos VCB foundation base casting,03 Nos soil excavation has done.XFR foundation:2nd XFR over all base casting done 08.06.2017 132kV control building building:2nd floor slab casting,Linten,brick wall & plaster work 100%,Brick wall plaster 70% completed.33kV control building : Ground floor brick wall 100% completed with plaster work.Boundary wall:01 No column casting done, total column,pile cap,gread beam brick wall completed.132kV S/Y: 72/88 Nos pedestal column casting has been done.33kV S/Y :22/22 gantry cast 10 Nos excavation,10 Nos VCB foundation base casting, 03 Nos soil excavation has done.XFR foundation:02 Nos XFR pit wall & beam rod binding completed, 15.06.2017 132kV control building building:Brick wall plaster 100% completed at internal side.33kV control building: 04 Nos windows sun shed & drop wall casting done.Boundary wall: 50m coping casting has been done.132kV S/Y:32 Nos pedestal column casting has been done.33kV S/Y:06 Nos base & gantry casting done.12 Nos VCB foundation base casting, 07 Nos VCB bay/beam cast has been completed.50% cable trench soil excavation has done.XFR foundation:01 No XFR rail fitting work has done. 22.06.2017 132kV control building building: Window Drop wall has -Boundary wall: 40m plaster work has done.132kV S/Y:15 Nos base has done for equipment.33kV S/Y:100% cable trench soil excavation has done.XFR foundation:Beam cast has done for XFR. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 132kV control building building: First floor shuttering open work & Ground floor column plastering work has done.33kV CB building:Brick wall making done up to linten.Boundary wall: 25m plaster work & 25m coping casting has done.132kV S/Y:12 Nos equipment soil excavation done,09 Nos equipment base & column casting done.33kV S/Y:60m CC & base casting done for A type cable trench.XFR foundation: Pit wall casting done. | 13.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
574 | 20.2 | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura | SRINAGAR Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S Project Manager Enamul Haq 01708131702 Farid Ahmed 01914454350 Ziaur-01708453369 | 27.10.2016 -Sand filling on going, 34,00,000 cft complete. 03.11.2016 Approximately 30 lacs cft (asper boat,count,without wastage calculation) sand filling complete,another 10 to 12 lacs cft of sand filling required.Water level is decreasing rapidly in canel,sand dredging can be continued for next 5 to 7 days,then we have to go for truck. 10.11.2016 -31400 cft Sand filling done.Leveling work going on. 17.11.2016 -leveling work running. 24.11.2016 -6 inch Dredging pipe installation going on.Land Leveling work complete of sub station area. 01.12.2016 -Finishing work going on in sand filling area. 08.12.2016 -Sand filling work 70% done. -Slope work is going on in west side area. 15.12.2016 -Sand filling at north end going on.Levelling and slope dressing is going on. 22.12.2016 -Sand filling work is going on. 29.12.2016 -Labor & Materials shed is making.Power connection has done at site .Installation work is going on for Submersible pump. 05.01.2017 -Materials shed,guard room,labor tin shed,wood fitting,soling & plasterworks, Water house (for pile) has completed. Generator room tin fitting works 90%,toilet tin & wood fitting and Boundary fencing briars,all room & out side electric cable wiring & light fittings 75%, Soil test work 80% has been completed. 12.01.2017 -Sand filling work is going on approx. 80000 cft. 19.01.2017 -46 Nos of pile casting work done for boundary.10 Nos footing & short column casting.in Ansar barrack.11 Nos CC ,Pile cap casting,GB casting in 33 Kv control building.09 Nos CC & pile cap casting for 132kV switch yard. -GB & 15 Nos short column work done for 132kV control building. 26.01.2017 -40nos pile work done. -2nos pile house for 132/33kV switch yard.33kV control building for 1 pile house. 33kv layout pile point costing. 1No labor water reserve house completed. 1nos cube querying work done.Road construction 12Nos for material carry done. 02.02.2017 -50 Nos pile casting work has done.80% brick wall has been done at office building. 09.02.2017 -Office building civil works has completed.83 Nos pile casting work has done. Labor shed,kitchen has make. 16.02.2017 -Pile work is going on for switchyard.Wall making work is running in Temporary office house.10 Nos CC work & 5 Nos column work has been done in 132kV control building.Rod binding & pile head broken work is going on. 23.02.2017 -36 Nos pile has done in 132kV Switchyard.28 Nos pile cap work done in 132kV control building.82 Nos pile head broken work has been done. 02.03.2017 -28/32 Nos pile cap casting at 132 kV switchyard.8/11 Nos pile cap casted load test complete at 132 kV switch yard.Grad beam casting completed at 132kV switch yard. 09.03.2017 -132kv control building : 30/32 now pile cap casting.Grade beam casting with out load test portion.30/32 now short column casting.4nos full column and 10nos first lift casting.Stair footing soil excavation and CC casting.Load test complete.33 kV building :11/11 numbers pile cap casting , grade beam casting without west side 3 pile 8/11 column casting . Stair column footing casting.132kV switch yard :22nos pile cap soil excavation, 18nos CC casting complete,12 Nos pile head backing complete -Load test complete . Boundary wall 73/104nos pile casting. 16.03.2017 -No update yet. 23.03.2017 -16 no column casting and Ground floor RCC casting work has been done.132/33 KV stairs first step 30.03.2017 -Boundary wall:50M grade beam & 20 Nos pile and 10 boundary column casting done.132 kV S/Y:13 Nos pile cap casting done. 132kV control building:2 Nos stair first lift casting done,beam shuttering done,slab shuttering running.33kV control building:stair first lift casting done,shuttering done. 06.04.2017 -Boundary wall:60M grade beam & 20 Nos boundary casting,200 sft brick wall work is making done.132 kV S/Y:19 Nos pile cap casting done.132kV control building:2 Nos stair first lift casting done,beam shuttering done,first floor slab shuttering,rod binding work has been done.33kV control building:stair first lift casting done,shuttering,rod binding has done. 13.04.2017 -132kV control building:Casting work is going on in first floor. 33kV control building: Casting work is going on in first floor.earth excavation work is going on.Boundary wall brick work,grade beam & pile cap work has been done. 20.04.2017 Boundary wall: 30Nos column,pile cap casting done. 40m brick wall work is making done.132 kV S/Y:16Nos pedestal column shuttering 7 ring ,tie binding work has been done.-33kV S/Y: Soil excavation work is going on.132kV control building:2No s stair first lift casting done,beam shuttering done,first floor slab shuttering ,rod binding work has been done. 33kV control building :stair first lift casting done,shuttering, rod binding has done. 27.04.2017 Boundary wall:18 Nos column,pile cap casting done. 45m grad beam & 50m brick wall work is making done.132 kV S/Y 12/88 Nos pedestal column shuttering work has been done.33kV S/Y: layout & 03 Nos base soil excavation done.132kV control building:25 No column first lift casting done, beam shuttering opening work has been done.33kV control building:11 Nos column casting & Ist floor out side beam shuttering open. 04.05.2017 Boundary wall:18 Nos column,pile cap casting done.45m grad beam & 50m brick wall work is making done.132 kV S/Y 12/88 Nos pedestal column shuttering work has been done.33kV S/Y: layout & 03 Nos base soil excavation done.132kV control building:25 No column first lift casting done,beam shuttering opening work has been done.33kV control building:11 Nos column casting & Ist floor out side beam shuttering open. 11.05.2017 Boundary wall:01 No column done.10m brick wall work is making done.132 kV S/Y:16/88 Nos pedestal column shuttering work has been done.33kV S/Y: 02 Nos base & 04 Nos gantry column casting done.132kV control building:27 No column 2nd lift casting done,internal Stair third lift casting done,33kV control building:External stair slab casting done. 18.05.2017 -132kV control building:11 Nos column 2nd lift casting done, total 27/27.ground floor slab shutter opening work completed,external stair slab cast & first floor slab cast work has done. 33kV control building: First floor slab casting,stair slab shuttering & rod binding and casting as been completed.XFR foundation:1st XFR 3 nos pile cap & overall base casting and 2nd XFR soil excavation has done.132 kV S/Y:12Nos pedestal column shuttering done.33kV S/Y:Layout &03 Nos base & gantry cast,01No gantry base macadam & CC casting has done. 25.05.2017 -XFR foundation work is continuing.Cable trench casting work is going on for 132kV & 33kV switchyard.Brick work & plaster work is continuing at 132kV & 33kV Control building first floor.Electrical & sanitary work is going on at Ansar barrack. 01.06.2017 02 Nos base slab casting in XFR foundation.Base & guide wall cast has been done at 33kV cable trench.CC & base cast has done at 132 kV switchyard.Brick work 7 plaster work has been done at 132kV & 33kV. Finishing work is going on at Ansar Barack. 08.06.2017 XFR foundation rail beam casting work is going on.132kV switchyard guide wall casting work is continuing.132kV & 33kV control building first floor in side wall plaster work is going on. 15.06.2017 132kV S/Y:cable trench base slab & guide wall casting.33 kV SY:earth back filling.132 & 33 kV CB:1st floor brickwork, plaster,drop wall casting. Ansar barrack floor curing &door fitting.Transformer rail beam & oil pit wall casting.Blast wall pile head break & cc casting. 22.06.2017 -Earth excavation work is going on at 33kV switchyard. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -Switchyard sand back filling & leveling work is going on at 33kv & 132 kv area.Rail beam (shuttering,rod binding) work has done for XFR foundation.Ballast wall shuttering work is going on. | 13.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
586 | 20.3 | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura | NARAIL Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S Project Manager Enamul Haq 01708131702 Farid Ahmed 01914454350 Site Engr. Ruhulamin 01708453368 | 22.10.2016 Post work measurement done. lay out of 132 kV control room building done.lay out of 33kV control room building done. 132kV switchyard layout done. 33kV switchyard layout done. Soil test work done. 27.10.2016 Post work measurement of earth development work taken on 19th Oct'16.Substation layout given by total station on 20th Oct'16,Compection test of earth work done. 03.11.2016 -PGCB stopped all types of activities by mail as per world bank guide line, but we continue for labor and material shade construction. 10.11.2016 -Labor shed,metarials shed & main gate make. 17.11.2016 -Labor shed,Security room,Metarials shed are built. -Temporary Boundary wall built. 24.11.2016 -Pile work started at site. 01.12.2016 -21 Nos of pile completed in control building.Boundary wall work going on in office building area. 08.12.2016 -All (64 Nos) of the pile completed in control building. -08 Nos pile out of 48 Nos are completed in switchyard. 15.12.2016 -36 Nos pile out of 48 Nos of 32 Kv gantry complete.Earth Excavation for pile cap of 132 kV control building started. 22.12.2016 -Pile work is continuning for 33kV switchyard building. -Soil digging & civil work has been running.Office building tiles work is continued. 29.12.2016 -Soil digging work is running for pile cap in 132 kV control building.29 Nos out of 64 Nos pile head has broken. 05.01.2017 -Pile work has done in 132 kV & 33 kV switchyard. -13 Nos CC work has done of 132 kV control building. -15 Nos of pile cap casting work has done in control building. 12.01.2017 -Main gate has fixed at site. -Brick soling road is making from main road to site. 19.01.2017 -46 Nos of pile casting work done for boundary.10 Nos footing & short column casting.in Ansar barrack.11 Nos CC ,Pile cap casting,GB casting in 33 Kv control building.09 Nos CC & pile cap casting for 132kV switch yard. -GB & 15 Nos short column work done for 132kV control building 26.01.2016 132 kV control building : 14nos column casting done.132kV switch yard : 02nos CC + Pile cap casting.33kV control building : 05nos column casting done.Ansar barrack: 10nos column casting done. Boundary pile: 60nos pile casting. 02.02.2017 -Pile load has been tested in 132 kV control building & switch yard.60nos pile cap casting for boundary wall. 09.02.2017 -01 No pile cap gb & column casting done in 132kV control building.60 Nos pile cap & 40m GB and 40 Nos column casting work has done. 16.02.2017 -01 No stair & ground floor casting & first floor beam shuttering work has been done in 132 kV control building.95 Nos pile cap casting,340 meter’s grade beam casting & 70 Nos column casting,300 meter’s brick work has been done. 23..02.2017 -stair 2nd lift shuttering & first floor beam & slab shuttering work has been done in 33 kV control building.Boundary wall 62 Nos pile cap casting,48 m grade beam casting & 40 Nos column casting,70 m brick work has been done. 02.03.2017 -33 kV control building:Stair 2nd lift casting & first floor beam & slab rod binding,Ansar barrack roof slab rod binding has been done.Boundary wall:total brick work done,03 Side plaster work has been done.132 kV control building :External stair final flight casting work,Ist floor shuttering & slab rod binding work has been done. 09.03.2017 -132 kV control building:Ist floor slab casting done. -33 kV control building-:Ist floor slab casting done.Column Ist & 2nd lift casting done for roof floor.-Ansar barrack:Roof slab casting work has done. 16.03.2017 -All column casting done for 2nd floor,Stair roof slab shuttering & rod binding done,boundary wall north side plaster done,33kV S/Y layout, excavation & CC work done. 23.03.2017 -132 kV control building:-External stair roof slab & internal stair third flight casting done,33 KV control building;- Stair roof slab casting done,33 kV Switch yard:-18 Nos gantry tower base casting done, 30.03.2017 -132 kV control building:-Shuttering work is going on for roof slab.33 KV control building;- Shuttering work is going on.Ansar barrack :Brick work & plaster work is going on. 06.04.2017 -132 kV control building:-Brick work,silling work,Shuttering work is going on for roof slab.Lenten casting done.33 KV control building;-Rod binding & Shuttering work is going on.Ansar barrack :Brick work & linten work is going on. 13.04.2017 -132 kV Control Building:-Roof slab casting has been done.33 KV Control Building;Roof slab casting has been done.Ansar barrack: Brick work is going on.33kV Switch yard: Gantry foundation casting has been completed. 20.04.2017 -132 kV Control Building:-Curing on going.33 KV Control Building: Curing on going.Ansar barrack : Plaster work is going on. 132kV/33kV Switch yard: Equipment foundation casting on going. 27.04.2017 -132 kV Control Building:-Second floor Roof slab Curing on going.33 KV Control Building: Second floor Roof slab Curing on going.Ansar barrack : Plaster work is continuing.132kV/33kV Switch yard: Equipment foundation casting on going.Blast wall & XFR pile work has been done. 04.05.2017 -132 kV & 33 KV Control Building: Roof slab Curing is continuing.132kV/33kV S/Y: Equipment foundation casting work is going on.Blast wall & XFR foundation pile work is continuing. 11.05.2017 -Equipment foundation work has been done for 32kV switchyard. 18.05.2017 XFR foundation work on going.Cable trench work is going on for 132kV & 33kV switchyard. Brick work is continuing at 132kV & 33kV Control building. 25.05.2017 to 08.06.2017 -No further update. 15.06.2017 Magura-2 bay gravel & brick soling removing has been completed.10 Nos foundation base earth excavation done. 06 Nos foundation base casting has been done. completed.Earth excavation work is going on. 22.06.2017 -Earth excavation work is going on. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -Cable trench base,guide,cover slab work is going on. | 13.07.2017 -Cable trench base, guide, cover slab work has been completed. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
598 | 20.4 | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura | JHENAIDAHA Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S Project Manager Enamul Haq 01708131703 Farid Ahmed 01914454350 | 22.10.2016 -Approved of GA & GTP Continued (40% done) 27.10.2016 to 16.03.2017 23.03.2017 -Soil excavation work is going on. -Wait for Anchor bolt for work. 30.03.2017 Soil excavation work is going on. 06.04.2017 Soil excavation work is going on.CC work is going on for LA,IVT,CT. 13.04.2017 JENAIDHA-1 BAY:Bay casting & column casting is continuing.JENAIDHA-2 BAY:Brick soling remove work has been done. NORAIL-2 BAY: Earth excavation work is going on 20.04.2017 -JENAIDHA-1 BAY:Bay casting & column casting has been finished. JENAIDHA-2 BAY:Cc casting & earth excavation work is going on.NORAIL-2 BAY:Base casting work has been completed, Column casting work is going on. 27.04.2017 -NORAIL-2 BAY:Base casting work has been completed, Column casting work has been completed.JENAIDHA-2 BAY:Cc casting & earth excavation work has been completed. 04.05.2017 -JENAIDHA-2 BAY: All Column casting work has been completed. 11.05.2017 -Earth excavation work has been done for Cable trench at JENAIDHA-1 BAY & JENAIDHA-2 BAY.CC work has been done at JENAIDHA -2 BAY.Rod binding & shuttering work at JENAIDHA -2 BAY site. Cable trench bas casting at JENAIDHA-2 BAY site. 18.05.2017 Base casting has been completed at JENAIDHA-1 bay area.Earth excavation & CC casting work has been done at Norail-2 Bay site. 25.05.2017 -Shuttering & Rod binding work has been completed at Norail-2 Bay site.Cable trench one side shuttering work has been done at JENAIDHA-1 bay area. 01.06.2017 -Base casting & shuttering work has been completed at Norail-2 Bay. 08.06.2017 -Guide wall casting work & back filling work has been completed at Norail-2 Bay. 15.06.2017 06.07.2017 -No further update. | 13.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
610 | 20.5 | WB PKG 4 Design Supply,Installation, Testing commissioning of 132/33kV AIS S/S at Nawabganj, Srinagar, Narail, Jhenaidah & Magura | MAGURA Design Supply, Installation, Testing commissioning of 132/33kV AIS S/S Project Manager Enamul Haq 01708131704 Farid Ahmed 01914454350 SAE alamin-01799997296 | Panel layout, SLD, GA, GTP, Bore-Hole design and DS of 132 & 33kV approved. CT-33kV approved Land sloping of 3 sides from 4 of the sides has been done. Sectional drawing approved,civil design is ready. -subsoil investigation done. 18.10.2016 -No further upgrade 22.10.2016 -Approval of GT & GTP CONTINUED (40%) DONE. 27.10.2016 TO 16.03.2017 -No further update. 23.03.2017 -Soil excavation work is going on.Wait for Anchor bolt for work. 30.03.2017 Soil excavation work is going on. 06.04.2017 Soil excavation work is going on.CC work is going on for LA,IVT,CT. 13.04.2017 JENAIDHA-1 BAY:Bay casting & column casting is continuing.JENAIDHA-2 BAY:Brick soling remove work has been done. NORAIL-1 BAY:Earth excavation work is going on. 20.04.2017 -JENAIDHA-1 BAY:Bay casting & column casting has been finished. JENAIDHA-2 BAY:Cc casting & earth excavation work is going on.NORAIL-2 BAY:Base casting work has been completed,Column casting work is going on. 27.04.2017 -NORAIL-2 BAY:Base casting work has been completed, Column casting work has been completed. JENAIDHA-2 BAY:Cc casting & earth excavation work has been completed. 04.05.2017 -JENAIDHA-2 BAY:All Column casting work has been completed. 11.05.2017 -Earth excavation work has been done for Cable trench at JENAIDHA-1 BAY & JENAIDHA-2 BAY.CC work has been done at JENAIDHA-2 BAY.Rod binding & shuttering work at JENAIDHA-2 BAY site.Cable trench bas casting at JENAIDHA-2 BAY site. 18.05.2017 Base casting has been completed at JENAIDHA-1 bay area.Earth excavation & CC casting work has been done at Norail-2 Bay site. 25.05.2017 -Earth cutting for Pile CC work is going on.5 nos. of Pile CC has been completed. 01.06.2017 -Soil excavation work is continuing for Pile.Back filling work is going on at pond area. 08.06.2017 10 Nos pile has been done for 32kv gantry tower.House making work & sand filling work is continuing at control building area. 15.06.2017 20 nos. of pile casting work has been completed for 132kV Gantry Tower.90% Earth filling has been completed & Compaction work is continuing. 22.06.2017 -30 Nos of pile casting work has been completed for 132kV Gantry Tower. -90% Earth filling has been completed and Compaction work is continuing. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -04 Nos Rig is running for pile work. | 13.07.2017 -Pile work is going on. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
622 | 21.1 | JICA PKG 3 Plant Design Supply, Installation of JICA Pakage 3 132/33kV S/S at BHALUKA , Mymensiing , Baroirhat and Ramganj on Turnkey Basis | BHALUKA 132 / 33KV Substation Project Manager Kh Belal Hossain 01730075384 Mr Pratik Roy 01717338637 | Sand filling done approximately 3500000 cft. 27.102016 -Land not yet handover. 03.11.2016 -Land Handover is not done yet. 10.11.2016 -Site hand over done. 17.11.2016 -Land Handover not done yet properly. 24.11.2016 -No update. 01.12.2016 -Officially been handed over -Tree cutting and cleaning is going on.Soil test and pre-section within a week. 08.12.2016 -Preparation work is going on for pre-section. 15.12.2016 -Pre Sectional work is over. 22.12.2016 -Lay out work is going on. 29.12.2016 -Land dispute is going on, so work is stopped. 05.01.2017 -Land dispute is going on, Created by landowner. -Sand fill contract goes to two(02)Nos of contractor. (05 janu,17). 12.01.2017 -Work has stopped still now. 19.01.2017 -Land disputes are going on. 26.01.2017 Earth filling has been started. 3% (1lakh. Cft.) soil filling has been done. 02.02.2017 -Sand filling works has been done approx. 6%. 09.02.2017 -Sand filling works has been done approx. 7%. 16.02.2017 -Sand filling works has been done approx. 10%. 23.02.2017 -Sand filling works has been done approx. 18%. 02.03.2017 -Sand filling works has been done approx. 21%. 09.03.2017 -Earth excavation work is going on. 16.03.2017 -50 % Earth excavation work has been done. 23.03.2017 -90319 cft Earth excavation work has been done by Arosh Enterprise.274949 cft Earth excavation work has been done by Ms Khan Enterprise. 30.03.2017 -13,96,879 cft Earth excavation work has been done by Arosh Enterprise. -8,81,022 cft Earth excavation work has been done by Ms Khan Enterprise. 06.04.2017 -No further update. 13.04.2017 -Soil compact work has been done. 20.04.2017 Earth filling has been Completed.Soil test or Borehole soil compaction test will going on from 21 April,17 27.04.2017 -Earth filling has been completed and Compaction work is going on. 04.05.2017 -Compaction & rolling work is going on. 11.05.2017 -Compaction & rolling work is continuing. 18.05.2017 -Earth filling has been completed and Compaction work is continuing. Materials for the fencing work are supplying to the site. 25.05.2017 Earth filling has been completed and Compaction work is continuing.Layout of the 132 kV gantry tower and 33 kV gantry tower has been completed.3 Nos of Rigs for piling works are supplied by M. A. Hashem Enterprise and preparation of piling work is going on. 01.06.2017 -06 Nos Base casting has been completed.06 Nos equipment earth excavation has been done. 08.06.2017 14 Nos Base casting has been completed for equipment. 15.06.2017 18 nos. of base casting has been completed for the 132 kV gantry tower.4 nos. of Column casting with anchor bolt fittings has been completed. 22.06.2017 -18 Nos of base casting has been completed for the 132 kV gantry tower. 15 Nos of Column casting with anchor bolt fittings has been completed.Tower structure has been mobilized at site. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -22 Nos column with base has been completed. | 13.07.2017 -04 Nos column with base has been completed. | From 14.07.2017 to 20.07.2017 last 01 (One) Week. | UPTO 27.10.2016 THURSDAY
634 | 21.2 | JICA PKG 3 Plant Design Supply, Installation of JICA Pakage 3 132/33kV S/S at BHALUKA , Mymensing , Baroirhat and Ramganj on Turnkey Basis | MYMENSINGH 132 / 33KV Substation Project Manager Kh Belal Hossain 01730075384 Mr Pratik Roy 01717338637 | Civil works completed 55%.pile head broken is stopped.PLI on foundation bolt is pending. 27.10.2016 Soil resistivity measurement done, Anchor bolt PLI.Civil works will be start at 31 oct,2016. 03.11.2016 -Anchor bolt PLI has been completed.sand,stone, rod is supplying to site. 10.11.2016 -Tower's Base & Column casting work going on. 17.11.2016 -Tower's Base & Column casting work 80% done. 24.11.2016 -Tower's Base & Column casting work 100% done. 01.12.2016 -Substation cleaning and soil cutting is going on (excess soil removal). 08.12.2016 -Soil excavation for equipment foundation is going on. 15.12.2016 22.12.2016 -No further update. 29.12.2016 -Soil excavation work has hold by PGCB GRID people. 05.01.2017 -Land excavation has been stop till now. 12.01.2017 -No further update. 19.01.2017 -Earth excavation is going on.Land disputes are going on. 26.01.2017 -Earth excavation is going on.Land dispute is going on. 02.02.2017 09.02.2017 -No further update. 16.02.2017 -No further update. 23.02.2017 -No further update. 02.03.2017 -No further update. 09.03.2017 -Soil excavation work is going on. 16.03.2017 -Equipment foundation construction preparation work is going on. 23.03.2017 to 06.04.2017 -No further update. 13.04.2017 -Temporary shed repairing work has been done. 20.04.2017 27.04.2017 -No further update. 04.05.2017 -350 bag’s cement arrive at site.Tower base layout drawing has been prepared. 11.05.2017 -Material supply work is going on.Tower base layout drawing work is going on for approval. 18.05.2017 -Work will be start very soon. 25.05.2017 -For control building, 50% Grade beam casting work has been completed and else is going on.For 132 kV Gantry Tower, All (29 nos.) column casting with anchor bolt fittings has been completed.21 nos of equipment foundation has been completed and else is going on for 132kV gantry. XFR foundation Pile Cap (Base) work has been completed. 01.06.2017 20 Nos base cast has been done for equipment foundation.Total grade beam work has been completed at control building. 08.06.2017 Rod binding for column at control building.Wall casting work has been done at XFR.Equipment foundation casting work has been completed. Short & long column casting work has been done at control building. 15.06.2017 For control building, 1st Floor Slab casting will be held on 22,june,2017. 36 nos. of equipment foundation base has been completed and else is going on for 132kV gantry Tower.Transformer foundation Pile Cap and base work has been completed. 22.06.2017 For control building, preparation for 1st Floor Slab casting is going on.36 nos. of equipment foundation base has been completed and else is going on for 132kV gantry Tower.Transformer foundation Pile Cap and base work has been completed. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -No further update, | 13.07.2017 -Base & column cast work has been completed at switchyard.33kv Base foundation has done. Column/rebar work is going on at control building. | From 14.07.2017 to 20.07.2017 last 01 (One) Week. | UPTO 27.10.2016 THURSDAY
646 | 21.3 | JICA PKG 3 Plant Design Supply, Installation of JICA Pakage 3 132/33kV S/S at BHALUKA , Mymensing , Baroirhat and Ramganj on Turnkey Basis | BAROIRHAT 132 / 33KV Substation Project Manager Kh Belal Hossain 01730075384 Mr Pratik Roy 01717338637 | ………………. -Sand filling done approximately 350000 cft. -pump sinking. 27.10.2016 Site mobilization start.Pump motor (2hp) installed now work stop for local Mayor. 03.11.2016 -Due to land disputes, Stoppage of work is going on. 10.11.2016 -Land dispute is going on with MAYOR. 17.11.2016 01.12.2016 -No further update. 08.12.2016 -Dismantling work done for existing building. 15.12.2016 -One existing building had broken already. 22.12.2016 -preparation work is running for pile. 29.12.2016 -Pile construction work has been started. 05.01.2017 -08 Nos pile work has been done for tower foundation. 12.01.2017 -22 Nos pile work has been done for tower foundation. 19.01.2017 -52 Nos pile work has been done for tower foundation. 26.01.2017 -92nos pile out of 116 have been done for tower foundation. 02.02.2017 -114 Nos pile out of 114 have been done for tower foundation.04 Nos pile out of 64 Nos have been done for control building. 09.02.2017 -39 Nos pile out of 64 Nos have been done for control building. 16.02.2017 -64 Nos pile out of 64 Nos have been done for control building. 23.02.2017 -16 Nos pile out of 16 Nos have been done for XFR. 02.03.2017 -Blast wall pile done 5 out of 5. 09.03.2017 -Pile load test preparation work has been done. -Gantry tower,base foundation ,pile head broken work has been done. 16.03.2017 -Pile load test has been done. 23.03.2017 -Pile cap work is going on for gantry tower.20 Nos CC work done at control building.Soil excavation work done for XFR. 30.03.2017 -CC work done in control building.Creeker done for column. 06.04.2017 -CC work done in 2Nos XFR.Creeker work is going on for gantry tower. 13.04.2017 -Base foundation/pile cap work has been done at 01 no XFR.02 Nos gantry tower has been completed. 20.04.2017 -2 Nos.of pile cap work has been completed for control building.All base foundation/pile cap has been completed and 07 Nos.of column has been completed. .XFR foundation Pile CC work is also going on and 01 no of pile CC is completed. 27.04.2017 13 Nos of Pile Cap work has been completed for control building.11 Nos of column and Anchor bolt fittings has been completed and else going on for Gantry Tower.XFR foundation Pile CC work has been done & preparing for Pile Cap. 04.05.2017 -09 Nos of Pile Cap work has been completed for control building.03 Nos of column and Anchor bolt fittings has been completed and else going on for Gantry Tower.XFR1 rod binding work has been done. 11.05.2017 -Pile cap work has been completed for control building.19 Nos column and anchor bolt fittings has been completed for gantry tower. Transformer base has been completed. 18.05.2017 For control building, Grade beam shuttering and casting work is going on.For Gantry Tower,27 Nos.of column casting with anchor bolt fittings has been completed and else going on. Transformer foundation Pile Cap(Base) work has been completed. 25.05.2017 -In the Control Building, All (32 nos.) Column has been completed and stair casting work preparation is going on. In the 132kV Gantry Tower, 10 nos. of Tower column has been completed with Anchor Bolt fittings.33kV gantry Tower, 6 nos. of tower has been completed. 01.06.2017 -10 Nos gantry tower’s all civil works has been finished at 33kV site.24 Nos gantry tower’s all civil works has been finished at 132kV site. 08.06.2017 Equipment soil excavation & CC casting work is continuing.33 kV gantry tower civil works has been completed.XFR pile head broken work has started. 15.06.2017 In the Control Building, 1st Floor slab casting will be held on 19.06.2017.In the 132kV Gantry Tower, 69 nos. of equipment foundation CC works has been completed. Transformer and Blast wall earth excavation and pile CC work is going on. 22.06.2017 -In the Control Building, 1st Floor slab casting has been done on In the 132kV Gantry Tower, -All equipment foundation CC works has been completed. -Transformer and Blast wall earth excavation and pile head break has been done. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -15 Nos Base casting has done for equipment.18 Nos column has done for control building at first floor. | 13.07.2017 -All column work has been completed at control building.26 Nos base cast work has been done 132kV equipment site.02 XFR CC work has been done. | From 14.07.2017 to 20.07.2017 last 01 (One) Week. | From 12.05.2017 To 18.05.2017
658 | 21.4 | JICA PKG 3 Plant Design Supply, Installation of JICA Pakage 3 132/33kV S/S at BHALUKA , Mymensing , Baroirhat and Ramganj on Turnkey Basis | RAMGANJ 132 / 33KV Substation Project Manager Kh Belal Hossain 01730075384 Mr Pratik Roy 01717338637 | ……………… -Sand filling done 49%. 27.10.2016 -from 14.10 to till date work stop, tomorrow will be meeting then work will be start. 03.112016 filling has been started from 31.10.2016, 54% filling has been completed. 10.11.2016 -Sand filling 60% done. 17.11.2016 -Sand filling 70% done. 24.11.2016 -Sand filling 70% done. -Soil test has been completed. 01.12.2016 -Soil test and pre-section measurement done. 08.12.2016 -90% sand filling work done. -Site office installation preparation work is going on. 15.12.2016 93% sand filling work done.Site Office construction is going on. 22.12.2016 -Lay out work is going on. -Site office, labor shed, sanitation work is going on. 29.12.2016 -93% sand filling work has been done.Materials shed & Labor shed making is going on. 05.01.2017 -Submersible pump has installed.Materials shed & Labor shed making is going on.Mobilization work has started for pile instrument. -95% sand filling work has been done. 12.01.2017 -96% filling work has done. -Materials shed & Labor shed making has finished. 19.01.2017 -99% filling work has done. 26.01.2017 -100% filling work has been done.Control building pile-30Nos done. 02.02.2017 -30Nos pile has done at Control building. 09.02.2017 -64 Nos pile has done at Control building.30 Nos out of 116 Nos pile has been completed at Gantry tower. 16.02.2017 -58 Nos out of 116 Nos pile has been completed at Gantry tower. 23.02.2017 -80 Nos out of 116 Nos pile has been completed at Gantry tower. 02.03.2017 -95 Nos out of 120 Nos pile has been completed at Gantry tower. 09.03.2017 -Pile work has done for gantry tower and transformer. 16.03.2017 -112 Nos out of 120 Nos pile has been completed at Gantry tower.9 Nos out of 21Nos pile has been completed at XFR. 23.03.2017 -120 Nos out of 120 Nos pile has been completed at Gantry tower.21 Nos out of 21Nos pile has been completed at XFR.All pile head cap broken at control building. 30.03.2017 -10 Nos rod binding has done for base.CC complete for control building.10 Nos CC has been completed for gantry tower. 06.04.2017 -Rod binding work is going on for gantry & Control building.16 Nos pile work has been complete for control building.27/30 Nos head broken work has been completed for gantry tower. 13.04.2017 -08 Nos pile work has been complete for control building.10 Nos base foundation/pile cap has been completed. 20.04.2017 32 Nos. (All) of Pile Cap work has been complete for Control building and Grade Beam Rod binding work is going On.17 Nos base foundation/pile cap has been completed.33kV gantry Tower earth excavation work is also going on. 27.04.2017 -50% Grade Beam casting work has been completed and going on the else for the Control Building.All (30 nos.) base foundation/pile cap work has been completed and preparing for the Anchor Bolt fittings.2 nos. of 33kV gantry Tower Pile CC work has been completed and else going on. 04.05.2017 -44082 ft Grade Beam casting work has been completed.18 Nos of 33kV gantry Tower Pile CC work has been completed. 11.05.2017 -Column casting work is going on for the control building.33kV gantry tower base has been completed. 132kV gantry tower column and anchor bolt fittings work is going on. 18.05.2017 In the Control Building, 19 nos. of Column has been completed and else Column casting work is going on.In the 132kV Gantry Tower,16 nos of Column has been completed with Anchor Bolt fittings.33kV gantry Tower base foundation has been completed and shuttering for column and template fittings work is going on. 25.05.2017 50 m long grade beam work has done.08 Nos column has been completed for Gantry tower base.Rebar work for Column in Control building.06 Nos shuttering work has done for roof column at first floor in control building.18 Nos cracker work for column at control building.20 Nos pile cap has been cast. 01.06.2017 First floor column casting going on.Boundary wall pile cap casting 120 nos.completed out of 220 & grade beam casting going on (125 meter completed)Gantry Tower pile cap casting 17 nos. completed out of 30 Nos.& Gantry Tower short column casting going on. 08.06.2017 70m grade beam,Gantry tower column 04 Nos.10 Nos boundary bass.Star casting & roof saturating processing work is continuing. 15.06.2017 10m long grade beam cast work has been done.20 Nos base casting done for boundary.01 No bass cast has done for gantry. Rod placing work is going on for beam. 22.06.2017 -10m grade beam cast has done. -Rod binding work has done for Roof. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -12 Nos pile cap casting has done for boundary wall.10m long Grade beam casting has done. | 13.07.2017 -02 Nos pile cap casting has done for boundary wall.20m long Grade beam casting has done. 10 Nos column casting has done for boundary wall.08 Nos gantry base column work has been completed. | From 14.07.2017 to 20.07.2017 last 01 (One) Week. | UPTO 27.10.2016 THURSDAY
670 | 22.1 | JICA PKG 4 EPC for Jaldhaka & Mohastangor; Bay extension at Saiedpur & Barisal | Jaldhaka Project Co-ordinator Md Abdul Khaleque 01712204871 Dilip,Sae- 01708131729 | 27.10.2016 -Civil Design & Drawing is going on.Sand filling is going on & 92% Completed.Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned person.Waiting to receive GTP & Drawing.Soil Test is going on. 03.11.2016 Soil Test has been done.Sand filling is going on & 97% Completed.Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned person.Waiting to receive GTP & Drawing.Civil Design & Drawing is going on. 10.11.2016 -Earth filling completed. -Transformer & DS drawing received. 17.11.2016 -Soil Test Completed. -site office is under construction. -Site Construction material rate is under negotiation. 24.11.2016 -No update. 01.12.2016 -Site Office & Labor shade work is going on. 08.12.2016 -GTP & Drawing of DS ES, Search Eristor and Circuit breaker’s submitted to PGCB for approval. -Site Office making work is going on. -Labor shade work completed. 15.12.2016 -GTP & Drawing of DS ES, Search Eristor and Circuit breaker’s submitted to PGCB for approval it’s processing going on.Site Office construction is going on.Piling has started for control building. 22.12.2016 -Pile has been done 22 Nos out of 152 Nos. 29.12.2016 -93% sand filling work has been done.Materials shed & Labor shed making is going on. 05.01.2017 -Piling is going on and 63 nos. Completed out of 152 nos. 12.01.2017 -Design submitted for approval to PGCB for CB & LA.Piling is going on and 90 Nos. Completed out of 152 Nos. 19.01.2017 -Got Approval GTP & GA of LA & 132 KV CB.GTP & GA of DS/ES submitted for approval to PGCB.Piling is going on and 112 Nos. completed out of 152 Nos. 26.01.2017 -GTP & GA of Conductor submitted for approval to PGCB.Control building piling has been completed.Gantry Tower piling is going on & 61 nos. completed out of 88 nos. 02.02.2017 -Got approval GTP & GA of 132 KVA DS/ES.GTP & GA of CT, IVT & 33 KV.GCB submitted for approval to PGCB.Control building piling is completed. Gantry Tower piling is going on & 76 nos. completed out of 88 nos. 09.02.2017 -Gantry Tower piling is going on & 82 nos. completed out of 88 nos. 16.02.2017 -Got approval GTP & GA of Auxiliary Transformer from PGCB.Control building piling is completed. Gantry Tower piling is going on & 86 nos. completed out of 88 nos. 23.02.2017 Pile load test for Control Building has been done.All Pile head broken. 02.03.2017 -Control building pile cap casting going on (15 Nos completed out of 32 Nos). 09.03.2017 -Control building pile cap casting completed & Grade beam casting going on. -Boundary wall Piling going on. 16.03.2017 -Boundary Pile 47 Nos out of 217 are complete. 23.03.2017 -98 Nos pile of boundary wall. 30.03.2017 -117 Nos pile has been done of boundary wall.14Nos grade beam casting has been done of control building. 06.04.2017 -115/220 Nos pile has been done of boundary wall.All Grade beam casting has been done of control building. 13.04.2017 -220/220 Nos pile has been done of boundary wall.50 Nos pile head broken work has been done for boundary wall.10 Nos CC casting has been completed for Gantry tower.12 Nos pile broken done for Gantry tower. 20.04.2017 -20 Nos pile base done for boundary.04 Nos Gantry base done.20 Nos pile work has been done for XFR.Shuttering work has been done in 1st floor roof &stair.150 Nos pile head broken work has been done.All column works has been done in Control building. 27.04.2017 -04 Nos Gantry tower base has done.30 Nos Pile cap casting work has been done for boundary wall.06 Nos pile casting work has been done for XFR.90% Shuttering work has been done in 1st floor roof. 04.05.2017 -03 Nos Gantry tower base has done.30 Nos Pile cap casting work has been done for boundary wall.03 Nos pile casting work has been done for gantry tower.100% Shuttering work has been done in 1st floor roof. 11.05.2017 -Rod binding work has been completed for pile cap.02 Nos stairs casting work has been completed. 18.05.2017 -First roof casting work has been completed.15 Nos pile cap casting has been done. 25.05.2017 -XFR & blast wall pile 16 Nos has been completed out of 16 Nos.Control room pile cap 08 Nos has been completed out of 32 No. 01.06.2017 -Control building pile cap casting going on. (14 nos. completed out of 32 nos.)Boundary wall pile head breaking going on.Gantry tower pile head breaking going on. 08.06.2017 32 Nos out of 32 Nos pile cap has been completed at control building. Grade beam reinforcement banding work is continuing.05 Nos out of 206 Nos pile cap has been completed at control building. 15.06.2017 Control building grade beam casting 25% done.10 Nos Boundary wall pile cap casting done with 22 Nos reinforcement banding continue out of 206 Nos. 22.06.2017 -Control building grade beam casting 100% done.56 Nos out of 206 Nos pile cap with beam casting has been completed. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -07 Nos boundary column casting has done.13 Nos pile cap casting has done up to beam. | 13.07.2017 Control building short column-32 nos. Long Column -06 nos. Boundary wall- pile cap-187nos out of 206nos . Grade beam 151nos. Column 90nos. Brick work-40gap. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
682 | 22.2 | JICA PKG 4 EPC for Jaldhaka & Mohastangor; Bay extension at Saiedpur & Barisal | Mohastangor Project Coordinator Md Abdul Khaleque 01712204871 Fulon- 01713608774 | 30.10.2016 Civil Design & Drawing is going on.Sand filling is going on & 45% Completed (Apx.).Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned person.Waiting to receive GTP & Drawing. 03.11.2016 Civil Design & Drawing is going on.Sand filling is going on & 48% Completed (Apx.),Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned person.Waiting to receive GTP & Drawing. 10.11.2016 -Earth filling complete 50%. -Transformer & DS drawing received. 17.11.2016 -Earth Filling Progress is 52%. 24.11.2016 -Earth Filling Progress is 57%. 01.12.2016 -Earth Filling Progress is 62%. 08.12.2016 -GTP & Drawing of DS ES, Surge arrester and Circuit breaker’s submitted to PGCB for approval.Earth Filling Progress is 67%. 15.12.2016 -Earth Filling Progress is 70%. 22.12.2016 -Earth Filling Progress is 72%. 29.12.2016 -Pile has been done 40 Nos out of 152 Nos. 05.01.2017 -Earth Filling is going on and 75% Completed. 12.01.2017 -Design submitted for approval to PGCB for CB & LA.Earth Filling is going on and 77% Completed. 19.01.2017 -Got Approval GTP & GA of LA & 132 KV CB.GTP & GA of DS/ES submitted for approval to PGCB.Earth Filling is going on. 26.01.2017 -GTP & GA of Conductor submitted for approval to PGCB.Sand Filling is going on. 02.02.2017 -Got approval GTP & GA of 132 KVA DS/ES.GTP & GA of CT, IVT & 33 KV GCB submitted for approval to PGCB.Sand Filling is going on & 83% Completed (Apx.) 09.02.2017 -As same as before. 16.02.2017 -Got approval GTP & GA of Auxiliary Transformer from PGCB.Soil Compaction Test Completed.Soil Test going on. 23.02.2017 -Soil test & soil compaction test has been done. 02.03.2017 -Labor Shade and Site Office Construction is going on. 09.03.2017 -Labor Shade and Site Office Construction is going on. 16.03.2017 -Labor shed & house are complete. 23.03.2017 -Pile 19 Nos out of 64 are complete.Gantry tower Pile 06 Nos out of 120 are complete. 30.03.2017 -Pile 37 Nos out of 64 are complete.Gantry tower Pile 15 Nos out of 120 are complete. 06.04.2017 -Pile 54 Nos out of 64 are complete.Gantry tower Pile 29 Nos out of 120 are complete.12/205 Nos pile has been done of boundary wall. 13.04.2017 -Pile 64 Nos out of 64 are complete in control building. Gantry tower Pile 39 Nos out of 120 are complete.39/205 Nos pile has been done of boundary wall. 20.04.2017 -39 Nos out of 120 Pile has been complete in Gantry tower.71/206 Nos pile has been done of boundary wall. 27.04.2017 -78 Nos out of 120 Pile has been complete in Gantry tower.103/206 Nos pile has been done of boundary wall. 04.05.2017 -98 Nos out of 120 Pile has been complete in Gantry tower.138/206 Nos pile has been done of boundary wall. 11.05.2017 -18 Nos Pile has been complete in Gantry tower.60 Nos pile has been done of boundary wall. 18.05.2017 -04 Nos Pile has been complete in Gantry tower. 08 Nos pile has been done of boundary wall.05 Nos out of 16 Nos pile has been done at XFR.03 Nos pile cap has completed at control building. 25.05.2017 -Same as before. 01.06.2017 -Gantry tower pile head breaking going on. 08.06.2017 Earth excavation and Pile head broken work has been done.Pre parathion work is going on for CC casting. 15.06.2017 04 Nos gantry tower base CC work has been done.Preparation work has been completed for gantry base,Rod binding & cutting.20m long grade beam & 10 Nos boundary bass casting work has been completed.3rd steps stair shuttering & cast done.Stair column & stair four slab casting done.2nd roof shuttering done. 22.06.2017 -04 Nos gantry base casting has been completed. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -04 Nos column casting has done at gantry tower base. | 13.07.2017 Control building short column-32 nos. Long Column -06 nos. Boundary wall- pile cap-187nos out of 206nos . Grade beam 151nos. Column 90nos. Brick work-40gap. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
694 | 22.3 | JICA PKG 4 EPC for Jaldhaka & Mohastangor; Bay extension at Saiedpur & Barisal | Saidpur Project Coordinator Md Abdul Khaleque 01712204871 Dilip,SAE-01708131729 | 20.10.2016 30.10.2016 -Civil Drawing Submitted to PGCB for Approval.Soil Test Completed.Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned person.Waiting to receive GTP & Drawing. 03.11.2016 Civil Drawing has been Approved.Soil Test Completed.Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned. person.Waiting to receive GTP & Drawing. 10.11.2016 Preparation for pilling in site office area. 17.11.2016 -S/S-Yard Construction area is cleaned. All tree and grass removed.Labor shed and site office is ready. Water pump is installed. Preparing to start Pilling work. 24.11.2016 -Pilling work is started. 01.12.2016 -Pilling work is going on. 08.12.2016 -GTP & Drawing of DS ES, Surge arrester and Circuit breaker’s submitted to PGCB for approval.13 Nos out of 16 Nos Pilling work has been done. 15.12.2016 -Piling work has completed. 22.12.2016 -No further update. 29.12.2016 -Earth Filling Progress is 74%. 05.01.2017 -Mixture Machine, Rod cutter & Vibrator Machine reached in site. 12.01.2017 -Design submitted for approval to PGCB for CB & LA. 19.01.2017 -Got Approval GTP & GA of LA & 132 KV CB.GTP & GA of DS/ES submitted for approval to PGCB.Earth Filling is going on. 26.01.2017 -GTP & GA of Conductor submitted for approval to PGCB. 02.02.2017 -Got approval GTP & GA of 132 KVA DS/ES. GTP & GA of CT, IVT & 33 KV GCB submitted for approval to PGCB. 09.02.2017 -As same as before. 16.02.2017 -As same as before. to 06.04.2017 -Same as before. 13.04.2017 -Same as before. 20.04.2017 -Same as before.16 Nos pile work has been done,but pile head broken work not yet start.. 27.04.2017 to 25.05.2017 -No further date. 01.06.2017 -Gantry tower piling going on & 05 Nos completed out of 40 Nos. 08.06.2017 Gantry tower piling going on & 12 Nos completed out of 40 Nos. 15.06.2017 08 Nos completed out of 40 Nos for gantry tower. 22.06.2017 -32 Nos completed out of 40 Nos pile work has done for gantry tower. 29.06.2017 -Eid festival holidays, so No further update. 06.07.2017 -No further update. | 13.07.2017 -02 Nos gantry base column casting has done. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
706 | 22.4 | JICA PKG 4 EPC for Jaldhaka & Mohastangor; Bay extension at Saiedpur & Barisal | Barisal Project Coordinator Md Abdul Khaleque 01712204871 Hasnat-01708131709 | 30.10.2016 -Civil Design & Drawing is going on.Soil Test Completed.Waiting for Equipment drawing from Daewoo.EEL Factory Item W/O handed over to concerned person.Waiting to receive GTP & Drawing. 03.11.2016 10.11.2016 -No further update. 10.11.2016 26 Nos out of 88 Nos pile are completed. 17.11.2016 -Searching for Contractor. 24.11.2016 -No update. 01.12.2016 -Searching Contractor for pilling work. 08.12.2016 -GTP & Drawing of DS ES, Search Eristor and Circuit breaker’s submitted to PGCB for approval.Till now Searching Contractor for piling work. 15.12.2016 22.12.2016 -No further update. 29.12.2016 -Requisition submitted to purchase section for Mixer machine & Shuttering materials. 05.01.2017 -Got Approval Piling Drawing from PGCB. 12.01.2017 -Design submitted for approval to PGCB for CB & LA. 19.01.2017 -Got Approval GTP & GA of LA & 132 KV CB.GTP & GA of DS/ES submitted for approval to PGCB. 26.01.2017 -GTP & GA of Conductor submitted for approval to PGCB. 02.02.2017 -Got approval GTP & GA of 132 KVA DS/ES. GTP & GA of CT, IVT & 33 KV GCB submitted for approval to PGCB. 09.02.2017 -Same as before. 16.02.2017 -Got approval GTP & GA of Auxiliary Transformer from PGCB. 23.02.2017 -As same as before. to 30.03.2017 -No further update, 06.04.2017 -Labor shed & side office construction work is going on. 13.04.2017 -Labor shed & side office’s construction work is continuing. 20.04.2017 -Labor shed & side office’s construction work has been finished. 27.04.2017 -No further update. 04.05.2017 -Water house making work has been completed for pile work. 04.05.2017 -Water house making work has been completed for pile work. 11.05.2017 -Pile lay out work has been completed. 18.05.2017 -No further update. 25.05.2017 -50% floor casting work has been done at ground floor in control building.Brick soling work has been done in switchyard.Cable trench excavation work done.07Nos base 7 column work has completed for boundary wall.08 Nos gantry tower casing completed. 01.06.2017 100% floor casting work at ground floor in control building.70% plaster work & Tiles work has been completed at control building.All Air conditioner has been installed. Electrical wiring & False ceiling work has been completed at control building. 08.06.2017 40m base cast has done for cable trench.06 Nos pit has been completed for WCP.07 Nos COLUMN & 15m brick work has been done.55m road soling, herring bond has done.Facing bricks work has done at south side.West side drop wall has been completed. 15.06.2017 20m base cast has done for cable trench.10 Nos pit has been completed for WCP with PVC pipe setting.Safety tank brick work has done.5*20 m road soling with herring bond has done. 1.5m wide,55m long RCC road casting has been completed 40m*10m soling mortar has done. 22.06.2017 150m coping /RCC casting work has done.04 Nos pit has been completed for WCP with PVC pipe setting.1.5m wide,10m long RCC road casting has been completed.5m wide,22m long RCC road casting has been done.Control building west side facing brick work has completed.Sanitary work 60% has done. -20m Coper slab work has done at cable trench. 29.06.2017 Cable trench work has been done. (Type A 20m,Type B 58m,Type C 05m,) 06.07.2017 -Road brick soling work has done.58 m long brick work has done at switchyard. West side of CB brick soiling work has been completed.Plaster work for boundary wall has done. | 13.07.2017 150m long plaster work for boundary wall.(in & out side) 20 Nos Water cast meant pit (W C P) has been completed for Bay-2 & Bay-3.levling,soling, motering work has been completed at Bay-2 & Bay-3.90m long Surface drain has been completed. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
718 | 23.1 | Design, Supply, Erection, Testing & Commissioning of New 132/33kV AIS S/S at Ruppur and Extension of 132kV bays at existing Ishurdi 230/132kV S/S on Turnkey basis | RUPPUR Project Manager Project Manager Eng Moazzem 01714217922 Engr Rashad 01755633886 Sae-Romijul, 01787690462, | 23.10.2016 94% Sand Filling Completed,Civil Drawings will be submitted within 31-10-2016. 27.10.2016 Sand Filling work is complited. Leveling & dressing works are going on. 15,000-20,000 cft additional sand filling may be required after leveling the area.Approval of drawings are halted due to training of PGCB's Engineers (PD: S.M Shafiqul Islam, X-Eng: Bellayet & A.E: Mizan). From next Sunday (30-10-2016) PGCB's engineers will be available to check & approve the submitted drawings. 03.11.2016 -Piling work will be started on 05Nov,2016. Control Room Building: Total pile 88 nos as per our work schedule all 88 piles should be completed within 16/11/2016. Pile work will be addressed by PGCB's MD sir & EEL's CEO sir on 6/11/2016. 10.11.2016 -26 Nos out of 88 Nos pile are completed. 17.11.2016 -Total pile work (88 nos) completed.Site office,site bathroom work 80% completed. -Excavation for 24 nos of piles started. 24.11.2016 CRB: 18 Nos pile excavation completed and pile cap works going on Gantry Tower: 16 Nos out of 88 Nos pile completed Site Office: Completed. 01.12.2016 -A/y:66 Nos out of 88 Nos pile completed.CRB:24 Nos out of 44Nos PCC works completed. 8 Nos out of 44 Nos Column rebar works completed. 08.12.2016 S/Y: 82 Nos out of 88 Nos Pile have been completed -CRB: 36 Nos out of 44 Nos PCC works completed. -12 Nos out of 44 Nos Column Rebar binding works completed. 15.12.2016 -88 Nos Gantry pile completed -8 Nos transformer piles completed 21 Nos out of 44 Nos pile cap of control room building completed. 22.12.2016 -42 Nos out of 44 Nos pile cap completed.8 Nos column casting completed.pile of boundary work started. 29.12.2016 -02 Nos out of 24 Nos Tower Foundation PCC Completed.185 RM Grade Beam Rebar Work completed. 05.01.2017 -Grade beam and 06 Nos Gantry tower pile cap work has been completed. 12.01.2017 -Out of 44,5 Nos short column is casting remain. shuttering work of slab beam started,03 Nos gantry tower foundations work has completed, 19.01.2017 Slab beam shuttering work & 04 Nos gantry tower foundation work has been completed.Roof slab shuttering & 01 Nos XFR foundation work is going on. 26.01.2017 1st floor slab casting has been completed.One no XFR base casting has been completed.12 Nos out of 44 Nos gantry tower casting has been completed. 02.02.2017 -10 Nos of column has completed at Ist floor of control building.26 Nos gantry tower foundation has done.1 No XFR base foundation has been completed. 09.02.2017 -32 Nos column casting has done.External stair shuttering work is going on.22 Nos gantry foundation has been completed at 132/11 kV switch yard. 16.02.2017 -Rod binding work is going on for base foundation in XFR (02 No).Beam,Roof shuttering work is going on in control building. -Rod binding work is going on for external & internal stairs in control building.16 Nos of column casting has been completed. 23.02.2017 Control building :Roof slab beam shuttering work complete,Roof slab wooden shuttering placing work.Re bar fabrications work is going on.Celling plaster work is going on in grnd floor.Switchyard :pile cap casting for gantry tower,Rebar fabrication for pile caps in short column,Gantry tower pastel column shuttering's anchor bolt settings work.XFR pad:Rebar fabrication work going on,beam & wall rebar setting work.Boundary wall:Pile curing work going on,All casting curing work going on,Metarials available at this site. 02.03.2017 Control room building: Gr. Floor-All Columns, beams & Gr. floor roof slab concreting completed , plastering of ceiling is going on.1st floor: Casting of column ,. Re-bar setting works for all beams going on.Stair concreting 80℅ done.Gantry Towers: Total Piles: 88nos completed. Pile Cap: 100% completed. Column concreting: 60/ 88 Nos. Remaining works for column: 16 Nos.Power Transformer Foundation:Base completed out of 2 nos foundation.Boundary Wall Pilings:-123 / 130 nos pile completed. Remaining(7 Nos.) Pilings work has been stopped by P.G.C.B 09.03.2017 -Control room building roof RCC casting done.23 Nos Equipment foundation base done.9 Nos column done.Soil excavation going on. 16.03.2017 -No further update. 23.03.2017 -100m grade beam, pile cap work has done for base foundation.28 Nos base done for Equipment foundation.27Nos column work done for boundary wall. 30.03.2017 -XFR all work complete for installation.150m grade beam,28 Nos base done for Equipment foundation.Nos column work done for boundary wall. 06.04.2017 -All Equipment's foundation has been done.96 Nos column work done for boundary wall.first floor brick work 40% done.320m grade beam work has been done. 13.04.2017 -Brick wall & plaster has been completed in 11kV Control building.Brick wall has been completed up to lintel in 132kV Control building.Battery room plaster work has been completed. 20.04.2017 -45m Power cable trench work has been done.30m Base work has been finished.03 Nos column casting done for XFR. Base,column works has been done for 04 Nos PI. 27.04.2017 -10 Nos base & column cast has been completed. 25m grad beam work has been completed for boundary wall.Tiles work is continuing at 11kV control building panel room. 04.05.2017 -Inner & outer stair post casting work has been completed.30m beam work done for boundary wall. 11.05.2017 -15m Brick work has been completed for boundary wall.90m parapet wall making work has been done in control building roof.25m parapet wall making work has been done in control building up side at external stair. 18.05.2017 -12 Nos Gantry tower with 12Nos beam fabrication work has been completed.01 No bay total equipment & 01 No XFR wiring has been completed. Control panel fittings work has been finished in 132kV & 11kV site. 25.05.2017 25 Nos base CC cast has been completed. 01.06.2017 20 m long power cable trench wall has been completed.40m long base cast work has been finished at power cable trench. 08.06.2017 Cable trench wall casting has done 30m.18m base casting has been done. 15.06.2017 60 meter long cable trench wall has been completed. 22.06.2017 -Cable trench wall making work is going on. 29.06.2017 -Cable trench work is going on. 06.07.2017 -Cable trench work has been completed. | 13.07.2017 -150 Pc’s cable trench cover slab has been done. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
730 | 23.2 | Design, Supply, Erection, Testing & Commissioning of New 132/33kV AIS S/S at Ruppur and Extension of 132kV bays at existing Ishurdi 230/132kV S/S on Turnkey basis | ISHURDI Project Manager Project Manager Eng Moazzem-1714217922 Engr Rashad 01755633887 SE,nurhasan 01708453300 | 23.10.2016 - 4 Nos out of 24 piles completed -Protection Scheme almost complete & will be submitted within 24-10-16 after attending meeting with PGCB's Protection Division. 27.10.2016 -12 No's out of 24 No's piles completed. 03.11.2016 All gantry tower piles are completed. Pile cap work will be started within 9/11/2016. 10.11.2016 Excavation of 24 Nos pile completed and pile cap work started. Excavation for equipment foundation started 17.11.2016 -Total equipment foundation 13 nos done.30% pile cap completed.equipment foundation work running. 24.11.2016 Gantry Tower: Excavation & Breaking of 24 Nos pile completed. PCC completed for 1 no Tower Foundation. 01.12.2016 Gantry Tower: PCC completed for all 24nos piles. 08.12.2016. Raft of 1 No tower out of 6 Nos completed. 15.12.2016 -Anchor bolt setting work is going on for tower. 22.12.2016 - 8 Nos column casting completed. 29.12.2016 Tower No 3 Rebar & Bolt setting work completed and will be casted on 01 Jan,2017. 05.01.2017 -06 Nos Gantry tower work has been completed. 12.01.2017 -Excavation for equipment foundations work is going on. 19.01.2017 -Excavation work is going on. 26.01.2016 -Excavation for equipment foundations work is going on. 02.02.2017 -Equipment foundations work is going on. 09.02.2017 -06 Nos gantry structure PCC has done at 230/132 kV site. 16.02.2017 -Earth excavation work stopped due to Excavator machine. 23.02.2017 Control room :-Total pile-88/88,pile cap-44/44, ground beam completed .column for ground floor-44/44,Ground floor slab casting completed. column for first & second floor 33/33,Switchyard: Pile -88/88,pile cap-22/22,pile uplift test completed for gantry tower,total short column for gantry-60/88 Nos column,XFR:pile-68/68,pile cap-00/04,XFR base pad completed-2/2,pile load test completed for XFR. 02.03.2017 -Gantry Tower Foundation: 6 Nos. completed out of 6 Nos. -Gantry Column Concreting with anchor bolts: 24 Nos completed out of 24 nos. -Equipment Foundation: -Earth Excavation works: 30% completed. -PCC Works done: 30% completed. -Re-bar works of base and columns: Going on. 09.03.2017 -06 Nos RCC base casting done for DS.Equipment earth excavation work done, 16.03.2017 -DS earth excavation completed.RCC base casting of DS done. 23.03.2017 -Earth excavation ,CC work has been for DS.RCC base casting done. 30.03.2017 -06 Nos column casting for DS (75% per column). -08 Nos column casting work has been done for GCB. 06.04.2017 -12 Nos base casting has been done for LA & IVT. 13.04.2017 -12 Nos column casting has been done for LA & IVT.20 Nos column casting has been done for VCB & DS. 20.04.2017 -IVT 22 Nos column casting has been done for VCB & DS. 27.04.2017 -No further update. 04.05.2017 -Earth excavation work is going on. 11.05.2017 -CC cast work has been done for Cable trench.Rod binding work is going on. 18.05.2017 -Earth excavation work and PCC casting work has been completed. 25.05.2017 -30/60 Nos WCP work has been completed.Tiles work is going on at guard room. 01.06.2017 45/60 Nos WCP work has been completed.Tiles work is going on at guard room.Preparation work for pile is going on. 08.06.2017 70m long Surface drain work has been completed.05 Nos pile has been done for gantry tower(T1). 15.06.2017 04 Nos WCP has been completed.30m long boundary wall plaster work has been done. 22.06.2017 -Paint work in Boundary wall.Surface drain finishing work has done. 12 Nos Piling work has been completed. 29.06.2017 -No further update. 06.07.2017 -04 Nos pile has been completed at switchyard.Panel wiring work is continuing. | 13.07.2017 -Piling work 4nos completed. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
742 | 24 | Design,supply,erection,testing and commissioning of 132/22kV AIS S/S at amnura with 132kV single circuit T/Lon Turnkey basis under bidder finance | Amnura Project Manager Project Manager Engr Alamgir 01787680482 Mr Rahim-01787680497 Shahin- 01709650210 | 27.10.2016 -Transmission line piling 98%, Pile Cap 33%, Open Cast Base 57%, Open Cast Chimney 44%,Switchyard Pile 81%, Switchyard Pile Cap- 78%, Open Cast-32%, Chimney-45%,Boundary Wall Piling Done- 88%. Control room gnd & 1st roof and gnd floor side wall & 1st floor side wall completed. 03.11.2016 Transmission Line Piling 100%, Pile Cap 46%, Open Cast Base 66%, Chimney 49%. No pole erected and no stringing are done.Switchyard pile 80%, Pile Cap 78%, Open Cast Base 37%, Chimney 50%, Cable trench (Meter) 5%. Boundary Wall Pile 90%. Control Room - Its going plaster outside of the Control building. 10.11.2016 Transmission Line Piling 100%, Pile Cap 34%, Open Cast Base 58%, Chimney 39%. No pole erected and no stringing are done.Switchyard pile 100%, Pile Cap 100%, Open Cast Base 79.35%, Chimney 85.12%, Cable Trench(Meter) 13.08%. Boundary Wall Pile 92%. Control Room -outside plaster of the Control building going on.23.10.2016 Pile work nearly finish.Open casting work running.Switchyard Gantry 33kV done.Boundary wall work done. 17.11.2016 Transmission Line: Piling 100%, Pile Cap 39%, Open Cast Base 60%, Chimney 41%. No pole erected and no stringing are done. Switchyard: pile 100%, Pile Cap 100%, Open Cast Base 93.50%, Chimney 94.64%, Cable Trench(Meter) 13.08%. Boundary Wall Pile 96%. Control Room -Finishing work 40% done. 24.11.2016 -Transmission Line: Piling 100%, Pile Cap 45%, Open Cast Base 63%, Chimney 45%. Switchyard: pile *80%, Pile Cap *78%, Open Cast Base 66%, Chimney 70%, Cable Trench(m) 13.08%. Boundary Wall Pile **65%. Control Room -Finishing work 80% done. 01.12.2016 -Transmission Line: Piling 100%, Pile Cap 50%, Open Cast Base 67%, Chimney 49%.Switchyard: pile *80%, Pile Cap *78%,Open Cast Base 66%, Chimney 70%, Cable Trench(m) 26%.Boundary Wall Pile *100%,putting *25%. Control Room -Finishing work 85% done. 08.12.2016 Transmission Line: Piling 100%, Pile Cap 53%, Open Cast Base 73%, Chimney 51%. Switchyard: pile *80%, Pile Cap *78%,Open Cast Base 66%, Chimney 70%, Cable Trench(m) 42%.Boundary Wall: Pile *100%,Base *35%. Control Room -Finishing work 90% done. 15.12.2016 Transmission Line: Pile Cap 57%, Open Cast Base 76%,Chimney 63% done.Switchyard: Cable Trench(m) 63% has done.Control Room: -Finishing work 93% done. 22.12.2016 -Transmission Line: Pile Cap 68%,Open Cast Base 0%,Chimney 70%, Pole erection 2% done. -Switchyard: Cable Trench(m) 70% has done.Control Room: -Finishing work 96% done. 29.12.2016 -Transmission Line: Pile Cap 78%,Open Cast Base 81%,Chimney 78%, Pole erection 10% done. Switchyard: Piling 80%,Pile Cap 78%,Open Cast Base 66%,Chimney 70%, Pole erection 57% Cable Trench(m) 75% has done. Control Room: -Finishing work 97% done. 05.01.2017 -Transmission Line: Pile Cap 86%,Open Cast Base 83%,Chimney 84%, Pole erection 32% done.Switchyard: Piling 80%,Pile Cap 78%,Open Cast Base 66%,Chimney 70%, Pole erection 84% Cable Trench(m) 76% has one.Control Room: -Finishing work 97% done. 12.01.2017 -Transmission Line: Pile Cap 87%,Open Cast Base 92%,Chimney 89%, Pole erection 33% done.Switchyard: Pile Cap 78%,Open Cast Base 75%,Chimney 73%, Pole erection 84% Cable Trench(m) 76% has one.Control Room: -Finishing work 97% done. 19.01.2017 -Transmission Line: Pile Cap 93%,Open Cast Base 94%,Chimney 93%, Pole erection 36% done.Switchyard: Pile Cap 78%,Open Cast Base 75%,Chimney 76%, Pole erection 84% Cable Trench(m) 76% has one.Control Room: -Finishing work 97% done. 26.01.2017 -Transmission Line: No of Pile- 100%,P/C-94%, Open Cast Base-98 %, Chimney- 96 %, Pole erection- 36 % done .Switchyard: Pile -80%,P/C-78% Open Cast Base- 82%, Chimney-80%, Tower erection- 84% Cable Trench(m)- 76% has one. 02.02.2017 -Transmission Line: No of Pile-100%,P/C-100%, Open Cast Base-100%,Chimney-100 %, Pole erection 36% done..Switchyard: Pile -80%,P/C -78% Open Cast Base-83%, Chimney-81%, Tower erection-84 % Cable Trench(m)-76% has one. 09.02.2017 -Transmission Line: No of Pile-100%,P/C-100%, Open Cast Base-100%,Chimney-100 %, Pole erection 36%done. Switchyard : Pile -80%,P/C -78% Open Cast Base-86%, Chimney-81%, Tower erection-84 % Cable Trench(m)-76% has one. 16.02.2017 -Transmission Line: Pole erection 36% done.Switchyard : Pile -84%,P/C- 78% Open Cast Base-87%, Chimney-83%, Tower erection- 84% Cable Trench(m)-76% has Done. Control building-99%. 23.02.2017 -Transmission Line: same as before.Switchyard : Pile -84%,P/C- 78% Open Cast Base-87%, Chimney-85%,Tower erection- 84% Cable Trench(m)-76% is Done.Control building-99%. 02.03.2017 Transmission Line: Pole errection 37%.Switchyard :Same as before.,Tower erection- Same as before.Control building-Same as before. 09.03.2017 Transmission Line: Pole erection 54%. 16.03.2017 Transmission Line: Pole erection 76%. 23.03.2017 Transmission Line: Pole erection 95%. 30.03.2017 Transmission Line: Pole erection 98%. 06.04.2017 Transmission Line: Pole erection 100%. 13.04.2017 -Electrical wiring work is going on in 132kV switch yard. 20.04.2017 .Brick, soling, plaster & Gravelling work is going on in 132kV type substation. 20.04.2017 -Brick, soling, plaster & Gravelling work is going on in 132kV type substation. 27.04.2017 -Civil work is going on for Guard room.Brick wall work has been completed in boundary wall. 04.05.2017 -20m grade beam work has been done. 11.05.2017 -20 m Brick wall work has been done. 18.05.2017 -WCP work is continuing.Pipe fitting work is going on. 25.05.2017 to 29.06.2017 -No further update. 06.07.2017 -Application for Pre Commissioning has been submitted to Jamalpur Grid. | 13.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
| 25 | Turnky contract for Design,supply,construction,istalation,testing and commissioning work for Extension of 33kV new bay at 132/33kV Jamalpur grid sub ststion for Jamalpur PBS under BREB. | Jamalpur Project Manager Project Manager Engr Muntasir Dipto 01755633881 Fazlehasan-01716114406 | 22.10.2016 -All equipment foundation ready.Gantry & cable trench done.Equipment PLI done. 27.10.2016 -All equipment foundations ,control cable trench completed,power cable trench 12 meter out of 32 meter completed. 03.11.2016 Except Isolators all other equipment's shipped to the site, cable trench construction going on. 12.11.2016 no civil work done due to bad weather.All necessary equipment's shipped to the site. 17.11.2016 -Project work cannot run for man power issue. 24.11.2016 -Tower fabrication work done. 01.12.2016 -No further update. 08.12.2016 -Civil works complete. -Erection work started and electrical works going on. 15.12.2016 -Erection has been started. -Tower erection Pending due to shut down issue.Isolator not delivered as REB didn’t approve the PLI yet. 22.12.2016 -Mesh earthing work has been done.Grounding cable lifting & connecting for equipment.Tower erecting 50% done. 29.12.2016 -Waiting for the shut down date.Soling,Motering has done. 05.01.2017 -Waiting for the shut down date.Brick Soling,Motering work has done in construction area. 12.01.2017 -preparation work is going on for Shut down, not yet get the shut down date. 19.01.2017 -06 Nos beam & 03 Nos tower has erected. 26.01.2017 -Waiting for the shut down,after get the shut down then we will finish our erection work. 02.02.2017 -06 Nos Isolators installation has done.Isolator’s box has fittings works has done. -03 Nos Breaker’s & 03 set CT has been installed. 09.02.2017 -All equipment installation has been completed. -01 Nos Gantry structure has erected.Control cable laying work is going on. 16.02.2017 -Control cable laying work has been done from indoor to outdoor. 23.02.2017 -Control cable laying work has been done approx. 90% from indoor to outdoor. 02.03.2017 -Waiting for Shutdown. 09.03.2017 -100% mechanical work completed in outdoor switchyard. 16.03.2017 -Control Panels all erected. 23.03.2017 -Cable laying work termination 80% done. 30.03.2017 -Cable laying work termination 95% done. 06.04.2017 -Cable laying work termination 100% done. Waiting for pre commissioning date,Letter sent to REB office for get the date. 13.04.2017 -No further update. 20.04.2017 -Power cable termination work has been completed.Spare materials handover to PBS at Jamalpur. 27.04.2017 -Preparation work is going on for Precommissioning. 04.05.2017 -Factory inspection has been done for Bus section isolator. 11.05.2017 -01 No Bus coupler Isolator (2500 A,31.5 KA ) handover to Jamalpur substation 18.05.2017 -Spare materials RR reporting receipt copy collect from Jamalpur PBS. 25.05.2017 01.06.2017 -No further update. 08.06.2017 -Commissioning has been completed. 15.06.2017 -No further update. | Commissioning has been completed. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
| 26 | Turnkey contract for Design,supply,construction,installation,testing & commissioning work for extension of exiting 33 Kv indoor BAY - breaker and control room building at 132/33kV cox'sbazar grid sub-station under COX'SBAZAR PBS | Cox's Bazar Project Manager Engr Muntasir Dipto 01755633881 | 22.10.2016 2no of breakers,1no adapter.5no of columns(out of 6)are done.shutdown approx 24oct,2016 27.10.2016 Short column done,preparing for beam casting .Estimated roof casting by 10nov,16 03.11.2016 Beam casting going on, estimated roof casting 17Nov,2016. 10.11.2016 -column casting done.estimated roof casting 28 Nov,2016. 17.11.2016 -Control room Roof casting running. 24.11.2016 -preparation work done for roof casting.Hope 28Nov,2016 will be Roof casting done. 01.12.2016 -Roof casting Completed.Cable trench work going on. 08.12.2106 -Electrical works going on. -PLI not done yet. 15.12.2016 -Cable trench work has been started.Building curing on going. Will be finished at 20,dec 2016. 22.12.2016 -Building curing has been finished.Inside of control room work has been started. -Cable trench work is going on. 29.12.2016 -Cable trench cc has been completed.Brick wall work to be started Very soon.AIS status update wasn’t clear from Reza vai. Need urgent attention. 05.01.2017 -Power cable trench work has been going on. 12.01.2017 -No up date. 19.01.2017 -Power cable trench work is going on.Panel not yet come at site,still now in Factory. 26.01.2017 -Power cable trench work is going on.Panel not yet come at site, still now in Factory. 02.02.2017 -Contractor didn’t agree to work at site,not yet get his bill. 09.02.2017 -No update. 16.02.2017 -Panel inspection not done yet.Waiting for the inspection date by PBS. 23.02.2017 -Panel inspection work has been done. -No further update. 02.03.2017 -No further update. 09.03.2017 -Shut down date is got. (20,March 2017) 16.03.2017 23.03.2017 -Same as before. 30.03.2017 -No further update -Shut-down date this Friday (7 Apr, 2017). 06.04.2017 -Waiting for pre commissioning date,Letter sent to REB office for get the date. 13.04.2017 -Same as before. 20.04.2017 to 18.05.2017 -No further update. 25.05.2017 Bus installation work completed & Bus energized already done. CT installation work has done.Jumpering work also completed.04 Nos earthing boring work has been completed. 01.06.2017 -Operating pipe & shaft has been installed.LA with plate has been installed. 08.06.2017 -80% civil works has been completed. 15.06.2017 Bus PT Installation work has been completed. 22.06.2017 29.06.2017 -No further update. 06.07.2017 Control cable laying preparation work has been completed.Existing feeder installation work has been completed. | 13.07.2017 -02 Nos PBD’s extension feeder placing to another area in same site.Civil works has been completed in VCB site. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
| 27 | Turnkey contract for Design,supply,construction,installation,testing & commissioning of 33 kV Bay Breaker Installation and related works at SHERPUR 132/33 kV Grid Sub-Station for SHERPUR PBS under BREB. | SHERPUR Project Manager Engr Jafor Iqbal 01713147042 Johir,SAE-01774218232 | 22.11.2016 -Soil test complete. -Earth cutting. -work start. 24.11.2016 -03 nos tower foundation base Excavation work done. -Existing Gravel shifted from site. 01.12.2016 -04 Nos of Shuttering work completed of tower foundation.02 Nos of Earth cutting work done of tower foundation. 08.12.2016 -Base casting work done of 04 Nos of tower foundation. -02 Nos of tower existing base dismantling. 15.12.2016 -02 Nos of tower foundation casting work complete.02 Nos of tower structure installation done.02 Nos of base rod binding work has completed. 22.12.2016 -04 Nos of tower foundation casting work complete. -Existing tower foundation base casting 50% has done. -02 Nos of VCB base foundation has completed. 29.12.2016 -No further update. 05.01.2017 -08 Nos gantry tower structure foundation RCC work has completed. -02 Nos RCC foundation work of VCB has completed. 12.01.2017 -02 Nos VCB foundation casting work has been completed. 19.01.2017 -01 Nos VCB foundation casting work has been completed. 26.01.2017 Problem:- -TECHNICAL MANPOWER SHORTAGE. -No further update. 02.02.2017 -Gantry tower erect work has been started. 09.02.2017 -04 Nos of tower has been erected.02 Nos of Beam has erected. 16.02.2017 -04 Nos of Beam has been erected. 23.02.2017 -Request for shut-down, 02.03.2017 -Waiting for the shut-down. 09.03.2017 -Shutdown processing work is going on. 16.03.2017 -02 Nos of tower already shifted.02 Axillary XFR settings on the beam.02 Nos of XFR energized for temporary basis. 23.3.2017 -08 Nos tower installation completed. 30.03.2017 -DS,ES setting work has been completed.Auxiliary base, foundation base malting work running. 06.04.2017 -Auxiliary base and foundation base malting work has been done. 13.04.2017 -02 Nos foundation works has been completed for additional VCB & CT. 20.04.2017 -CT & PT has been erected. 27.04.2017 -02 Nos VCB has been arrived at site.03 Nos Isolator & 05 Nos Shaft has been erected. 04.05.2017 -Mk box has been installed.VCB installation work is going on. 11.05.2017 -03 Nos VCB errection work has been completed.01 Set Bus isolator with shaft & junction box has been erected. 18.05.2017 -No further update. 25.05.2017 -04 Nos tower foundation casting work has been completed.03 Nos VCB base casting work has been completed.02 Nos VCB rod binding & shuttering work has been completed.01 No shuttering rod binding work is going on. 01.06.2017 -Tower base & VCB base work has been completed. 08.06.2017 -Earthing work has been completed.Bus PT Installation work is going on. 15.06.2017 100% civil works has been completed. 22.06.2017 to 06.07.2017 -No further update. | 13.07.2017 -No further update. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
| 28 | Design,supply,construction,installation,testing & commissioning of 33kV 04 Nos. Bay-Breaker Extension and related works at Saidpur 132/33kV Grid Sub-station for Nilphamari PBS under Turnkey contract basis. | SAIDPUR Project Manager Engr Jafor Iqbal 01713147042 | 03.01.2017 -WORK START one no bay extension,vcb foundation and VCB,CT structure drawing approved. 10.01.2017 -installation work start week -vcb,CT and DS,ES,installation/setting has done. Power Cable work done. Control Pannel setting in exixting control building control cable laying work completed. pre commissioning done at 26,janu. 02.02.2017 -now work has stopped. 01 No of BAY extension work has been completed. Energigation / commissioning done at 1,janu,2017.Successfully energized.future plane :-03 Nos of BAY Extension work.as per approved drawing they are not agree to do thid work as per our approved drawing for this reason another place out of grid boundary wall at pdb location area need to be arrange.REB SE ,GM , EXEN they will be sittng for a meeting for this case, 09.03.2017 -Same as before. | 13.07.2017 -15 Nos CC casting has been done boundary wall.Soil excavation work has done for 52 Nos base.13 Nos pile work has been completed. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
| 29 | Turnkey contract for Design,Supply,Construction,Installation,Testing & Commissioning work for extension of 33kV new Bay at 132/33kV Jhenaidah Grid sub station for Jhenaidah PBS under BREB. Client –BREB | Jhenaidah Project Manager Engr Jafor Iqbal 01713147042 | Turnkey contract for Design,Supply,Construction,Installation,Testing & Commissioning work for extension of 33kV new Bay at 132/33kV Jhenaidah Grid sub station for Jhenaidah PBS under BREB. Client –BREB | 13.07.2017 -15 Nos CC casting has been done boundary wall.Soil excavation work has done for 52 Nos base.13 Nos pile work has been completed. | From 14.07.2017 to 20.07.2017 last 01 (One) Week.
#NAME?